## Sheet1
Task |  | Members | Week 0 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Discovery
1 | Initial project research
2 | Email potential sponsors
3 | Initial sponsor meeting
4 | Sign NDA
5 | Project proposal submission
6 | Create and update Wiki page
MILESTONE 1 - Project proposal due
7 | Preliminary data exploration
8 | Exploring analysis tools
9 | Request for additional data
10 | Initial presentation to sponsor
Data Preparation
11 | Data consolidation
12 | Data cleaning
Model Planning
13 | 2nd round of data exploration
14 | Model selection
15 | Initial visualisation
16 | Review findings with sponsor
17 | Finalise project objectives
18 | Revise project proposal
19 | Update Wiki page
20 | Finalise interim report
21 | Finalise analytical sandbox
22 | Prepare presentation
MILESTONE 2 - Interim Report and Presentation
Model Building
23 | Model calibration
24 | Model assessment
25 | Interpretation of analysis results
26 | 2nd round of visualisation
27 | Review findings with sponsor
28 | Update report
29 | Update Wiki page
Final Preparation
30 | Prepare final report
31 | Prepare final poster
32 | Prepare final presentation
MILESTONE 3 - Final Report and Presentation
MILESTONE 4 - Poster Presentation