## Sheet1
Task | W1 | W2 Milestone 1 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 Milestone 2 | W11 | W12 | W13 | W14 | W15 | W16 Milestone 3
| 28 Dec-3 Jan | 4-10 Jan | 11-17 Jan | 18-24 Jan | 25-31 Jan | 1-7 Feb | 8-14 Feb | 15-21 Feb | 22-28 Feb | 29 Feb-6 Mar | 7-13 Mar | 14-20 Mar | 21-27 Mar | 28 Mar-3 Apr | 4-10 Apr | 11-17 Apr
Discussion with prospective project sponsors | A
Prospect Analysis | TEAM
Prospect Confirmation | TEAM
Detailed discussion on project motivation and objectives |  | TEAM
Obtain Project Data |  | A
Exploration of possible analysis methodology |  | TEAM
Research on Data Retrieval Techniques: 1. Google calendar public holiday pull 2. Google trends data pull |  | H
Complete Proposal |  | TEAM
Complete Wiki Page |  | TEAM
Data Cleaning |  |  | H
Research on Analysis Techniques: RapidMiner |  |  | J
Research on Analysis Techniques: SAS Text Mining |  |  | A
Perform Exploratory Data Analysis |  |  |  | TEAM
Project review before consultation with Prof Kam |  |  |  | TEAM
Meeting with Prof Kam |  |  |  |  | 2016-01-29
Meeting with Client to clarify project objectives, understand client team operations briefing on analysis methodology | [5 empty] | 2016-02-02
Team review of project objectives and analysis methodology | [5 empty] | ALL
Data pull from GA (paid and unpaid sources) | [6 empty] | A
Web crawling of article attributes based on urls pulled from GA | [7 empty] | H
Web crawling of share counts for articles based on urls pulled from GA and merging with huy's dataset | [7 empty] | J
Update Wiki Page | [7 empty] | H
Perform Exploratory Data Analysis | [7 empty] | H
Attribute Metric Correlation modelling | [8 empty] | A
Regression modelling on organic sources | [8 empty] | A
Odds ratio senstivity analysis across various sources | [8 empty] | A
Identifying most valuable (UVP and ATOP) paid source | [8 empty] | J
K-means clustering (article content) | [8 empty] | J
Cluster Labelling (article content) | [8 empty] | J
Validation of present set of CT | [8 empty] | J
Mapping of clusters to CT | [8 empty] | J
Identification of top 3 CT | [8 empty] | J
z score comparison across CT | [8 empty] | J
Complete Mid Term Report | [8 empty] | A & J
Update Wiki Page | [8 empty] | H
Model Findings and Revision with Client | [9 empty] | 2016-03-01
Integration of newly formed article content CT label into data cube | [9 empty] | H
Conversion of numerical metrics to categorical variables | [9 empty] | A
K-means clustering (title) | [9 empty] | J
Cluster Labelling (title) | [10 empty] | H
Identification of top 3 clusters | [10 empty] | H
z score comparison across clusters | [10 empty] | H
Update Wiki Page | [10 empty] | H
Model Revision works | [10 empty] | TEAM
Update Wiki Page | [10 empty] | A
Model Revision with Client | [11 empty] | 2016-03-15
Update Wiki Page | [11 empty] | H
Model Revision works | [12 empty] | TEAM
Update Wiki Page | [12 empty] | J
Model Revision works | [13 empty] | TEAM
Update Wiki Page | [13 empty] | A
Team review before client meeting | [14 empty] | TEAM
Update Wiki Page | [14 empty] | H
Final Client Meeting | [14 empty] | 2016-04-05
Paper review for Final Report | [15 empty] | TEAM
Presentation review for Final Report | [15 empty] | TEAM
Final Wiki Updates | [15 empty] | H
Final Report Presentation | [15 empty] | 2016-04-17