## Schedule Metric
The schedule metric measures how well is the schedule planned. The schedule metrics is updated on a weekly basis by the project manager. The project manager will check the Schedule Performance Index weekly and also after every iteration.
Weekly Action Plan
Per Iteration Action Plan
SCHEDULE METRIC
This measurement of actual against estimated time in days is called the Schedule Performance Index (SPI) and the calculation or formula is as follow:
SPI =
AT
ET
SPI - Schedule Performace Index (SPI)
AT - Actual time (in days) taken for task completion
ET - Estimated time (in days) taken for task completion

## Weekly SPI
Duration | Week | SPI
27 June - 3 July | 1 | 1
4 July - 10 July | 2 | 1
11 July - 17 July | 3 | 0.89683
18 July - 24 July | 4 | 0.93304
25 July - 31 July | 5 | 1
1 Aug - 7 Aug | 6 | 1.2041
8 Aug - 14 Aug | 7 | 1.0556
15 Aug - 21 Aug | 8 | 2
22 Aug - 28 Aug | 9 | 1.625
29 Aug - 4 Sep | 10 | 1.7
5 Sep - 11 Sep | 11 | 1.0417
12 Sep - 18 Sep | 12 | 1.119
19 Sep - 25 Sep | 13 | 1
26 Sep - 2 Oct | 14 | 1
3 Oct - 9 Oct | 15 | 1.3468
10 Oct - 16 Oct | 16 | 1
17 Oct - 23 Oct | 17 | 1.75
24 Oct - 30 Oct | 18 | 1.0714
31 Oct - 6 Nov | 19 | 1
7 Nov - 13 Nov | 20 | 1
14 Nov - 20 Nov | 21 | 1.25
21 Nov - 27 Nov | 22 | 1
28 Nov - 4 Dec | 23 | 1

## SPI Iterations
Week | Tasks | AT | ET | SPI
Iteration 1 - Inception Phase
Project Management & Planning
1 | Define main roles & responsibilities | 1 | 1 | 1
1 | Set team expectations & goals | 1 | 1 | 1
1 | Risk management plan | 2 | 2 | 1
1 | Define rough project schedule | 2 | 2 | 1
Requirements
1 | Understand and discuss project functional/non-functional requirements | 1 | 1 | 1
1 | Project vision | 1 | 1 | 1
1 | Technology Exploration 1 (Adobe Flex/Facebook) | 1 | 1 | 1
1 | Update wiki page check | 1 | 1 | 1
Project Management
2 | Milestone: Project Proposal | 4 | 4 | 1
2 | Milestone: End of Inception Phase | 1 | 1 | 1
| Iteration 2 - Elaboration 1 Phase |  |  |  | Iteration | SPI
| Business Modeling |  |  |  | 1 | 1
2 | Class Diagram | 1 | 1 | 1 | 2 | 0.92783
| Requirements |  |  |  | 3 | 1.0952
3 | Technology Exploration 2 (Adobe Flex/Facebook) | 5 | 7 | 0.71429 | 4 | 1.2586
3 | ER Diagram / Database Logical Diagram | 2 | 3 | 0.66667 | 5 | 1.166
3 | Update wiki page check | 3 | 3 | 1 | 6 | 1.1
Implementation
Coding
Project Framework
B1G1 World Facebook application
3 | Database Connectivity | 1 | 1 | 1
4 | Facebook App Permissions for Wall post/Information | 2 | 2 | 1
4 | Syncing Facebook and B1G1 account | 3 | 4 | 0.75
B1G1 World
3 | Database Connectivity | 2 | 2 | 1
3 | Google map implementation | 2 | 2 | 1
4 | Geocoding for latitude/longtitude of address | 2 | 2 | 1
4 | Plotting of entities on map | 3 | 3 | 1
4 | Animation framework for displaying a single entity | 3 | 3 | 1
4 | B1G1 World Widget implementation framework | 2 | 2 | 1
User Interface
4 | Draft interface layout (Prototype for B1G1 World and Facebook App) | 5 | 7 | 0.71429
Database
4 | Deployment | 3 | 3 | 1
Project Management
5 | Knowledge Sharing (Adobe Flex/Facebook) | 5 | 5 | 1
Milestone: Project Acceptance
Review Project Schedule
Milestone: End of Elaboration 1 Phase
Iteration 3 - Elaboration 2 Phase
Business Modeling
5 | Review Class Diagram | 1 | 1 | 1
Requirements
5 | Review Project Requirements | 1 | 1 | 1
5 | Update wiki page check | 1 | 1 | 1
Design
5 | Review LD/ER Diagram | 1 | 1 | 1
Implementation
Coding
B1G1 World
5 | XML Structure Standardization for plotting markers on map | 1 | 1 | 1
5 | XML Structure Standardization for details for a particular marker | 1 | 1 | 1
6 | XML Structure Standardization for relationships for a particular marker | 1 | 1 | 1
6 | Populating geocode data | 2 | 1 | 2
B1G1 World Facebook application
6 | Automated Wallpost Notifications Framework | 7 | 7 | 1
User Interface
6 | B1G1 World Layout | 8 | 7 | 1.1429
5 | Individual entities' icons | 7 | 7 | 1
B1G1 World Facebook application
6 | Facebook application layout | 9 | 7 | 1.2857
Testing
6 | Test B1G1 World database connectivity | 3 | 3 | 1
6 | Test B1G1 World Facebook application wall post function | 3 | 3 | 1
Project Management
7 | Knowledge Sharing (Adobe Flex/Facebook) | 2 | 2 | 1
Milestone: End of Elaboration 2 Phase
Iteration 4 - Construction 1 Phase
Business Modeling
7 | Review Class Diagram | 1 | 1 | 1
Requirements
7 | Review Project Requirements | 1 | 1 | 1
7 | Update wiki page check | 1 | 1 | 1
Design
7 | Review LD/ER Diagram | 1 | 1 | 1
Implementation
Coding
B1G1 World
7 | Filter: By Regions | 4 | 3 | 1.3333
8 | Filter: Projects that the member gives | 6 | 3 | 2
8 | Filter: Projects that the worthy cause member has | 7 | 3 | 2.3333
9 | Filter: Members and Worthy Cause Member that the project has | 3 | 2 | 1.5
10 | Filter: Leverage of an individual member | 9 | 5 | 1.8
B1G1 World Facebook application
8 | Facebook like function | 5 | 3 | 1.6667
9 | Facebook share function | 7 | 4 | 1.75
10 | Facebook invite function | 8 | 5 | 1.6
11 | Wall post function (for contribution by companies) | 5 | 5 | 1
12 | Causes Listing Page | 15 | 14 | 1.0714
13 | Individual Cause Page | 7 | 7 | 1
13 | Facebook Analytics - Retriving Number of Likes Cron Job | 7 | 7 | 1
User Interface
B1G1 World
11 | Details Layout for individual entities | 5 | 5 | 1
11 | Giving Information Layout for B1G1 World | 9 | 8 | 1.125
B1G1 World Facebook Application
12 | Main Page and Feedback Page | 8 | 7 | 1.1429
12 | Causes Listing and Individual Cause Page Layout | 8 | 7 | 1.1429
Testing
13 | Test B1G1 World filters | 3 | 3 | 1
13 | Test Facebook functions | 3 | 3 | 1
13 | Test B1G1 World giving information/mapping effect | 3 | 3 | 1
Project Management
14 | Knowledge Sharing (Adobe Flex/Facebook) | 3 | 3 | 1
Milestone: User Acceptance Test 1
Milestone: Midterm Review
14 | Review Project Schedule | 3 | 3 | 1
Milestone: End of Construction 1 Phase
Iteration 5 - Construction 2 Phase
Business Modeling
14 | Review Class Diagram | 1 | 1 | 1
Requirements
14 | Review Project Requirements | 1 | 1 | 1
14 | Update wiki page check | 1 | 1 | 1
Design
14 | Review LD/ER Diagram | 1 | 1 | 1
Implementation
Coding
B1G1 World
15 | Filter: Keyword Search | 9 | 5 | 1.8
15 | B1G1 World Genric Widget | 14 | 9 | 1.5556
15 | B1G1 World Customized Widget | 14 | 9 | 1.5556
15 | Recommendation Module | 17 | 15 | 1.1333
Adminstrative Module
15 | Geocoding control panel | 10 | 8 | 1.25
15 | Recommendation List | 17 | 15 | 1.1333
15 | Login/Logout | 3 | 3 | 1
16 | B1G1 World Widget with AddThis | 3 | 3 | 1
B1G1 World Facebook application
17 | Integrate B1G1 World into Facebook and B1G1 Main Site | 7 | 4 | 1.75
User Interface
B1G1 World
18 | B1G1 Customized Widget Layout | 15 | 14 | 1.0714
18 | B1G1 Generic Widget Layout | 15 | 14 | 1.0714
Testing
19 | Test B1G1 World Widget | 2 | 2 | 1
19 | Test B1G1 World Recommendation/Adminstrative Modules | 2 | 2 | 1
19 | Test B1G1 World | 2 | 2 | 1
Project Management
20 | Knowledge Sharing (Adobe Flex/Facebook) | 1 | 1 | 1
Milestone: Poster
Milestone: Heuristic Evaluation and User Acceptance Test 2
20 | Review Project Schedule | 1 | 1 | 1
Milestone: End of Construction 2 Phase
Iteration 6 - Transition Phase
Coding
21 | Debugging | 3 | 3 | 1
21 | Final Deployment | 3 | 2 | 1.5
Testing
22 | Final Testing of Complete System | 3 | 3 | 1
Project Management
23 | User Manual + Documentation | 5 | 5 | 1
23 | Prepare Presentation Slides | 5 | 5 | 1
Milestone: Final Presentation
Milestone: End of Transition Phase