|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task Name | Planned Start Date | Planned Finish Date | Actual Finish Date | Schedule Index |
| **Inception Phase** |
|  **Requirements Gathering** |
|  Understanding client's requirements | Mon 12/9/11 | Mon 19/9/11 | Mon 19/9/11 | 1.0  |
|  Finalize project scope | Mon 19/9/11 | Mon 26/9/11 | Mon 26/9/11 | 1.0  |
|  Research Drupal/CakePHP/Joomla | Tue 27/9/11 | Fri 21/10/11 | Fri 21/10/11 | 1.0 |
|  Research Mobile Platforms | Tue 27/9/11 | Fri 21/10/11 | Fri 21/10/11 | 1.0 |
| Specify functionalities for Portal & Mobile | Tue 27/9/11 | Fri 21/10/11 | Fri 21/10/11 | 1.0 |
|  Project Proposal Submission | Mon 24/10/11 | Mon 24/10/11 | Mon 24/10/11 | 1.0 |
| **Elaboration Phase** |
|  **Attendees Profile & UI - Web Platform (Iteration 1)** |
|  Design and develop UI for Web Portal | Tue 25/10/11 | Thu 27/10/11 | Thu 27/10/11 | 1.0 |
|  Create Diagrams (Use Case, Solutions Architecture, Deployment) | Tue 25/10/11 | Thu 27/10/11 | Thu 27/10/11 | 1.0 |
|  Design metrics (Bug, Schedule) | Tue 25/10/11 | Thu 27/10/11 | Thu 27/10/11 | 1.0 |
|  Develop test cases and test data | Fri 28/10/11 | Mon 31/10/11 | Mon 31/10/11 | 1.0 |
|  Develop user registration/login/logout function | Tue 1/11/11 | Wed 2/11/11 | Wed 2/11/11 | 1.0 |
|  Display attendees profile | Thu 3/11/11 | Fri 4/11/11 | Fri 4/11/11 | 1.0 |
|  Develop social networking function - friend system | Thu 3/11/11 | Tue 8/11/11 | Wed 9/11/11 | 1.1  |
|  Deployment | Wed 9/11/11 | Thu 10/11/11 | Thu 10/11/11 | 1.0 |
|  Test functions with test cases | Wed 9/11/11 | Thu 10/11/11 | Thu 10/11/11 | 1.0 |
|  Debugging | Wed 9/11/11 | Thu 10/11/11 | Thu 10/11/11 | 1.0 |
|  Buffer | Fri 11/11/11 | Fri 11/11/11 | Fri 11/11/11 | 1.0 |
|  **Conference Engagement I - Web Platform (Iteration 2)** |
|  Revise Diagrams | Mon 14/11/11 | Mon 14/11/11 | Mon 14/11/11 | 1.0 |
|  Develop test cases and test data | Mon 14/11/11 | Tue 15/11/11 | Tue 15/11/11 | 1.0 |
|  Display Conference Details | Wed 16/11/11 | Tue 22/11/11 | Thu 24/11/11 | 1.4  |
|  Develop live voting function | Wed 16/11/11 | Tue 22/11/11 | Tue 22/11/11 | 1.0 |
|  Develop Private Messaging System | Tue 29/11/11 | Tue 6/12/11 |   |   |
|  Deployment | Wed 7/12/11 | Fri 9/12/11 |   |   |
|  Test functions with test cases | Wed 7/12/11 | Fri 9/12/11 |   |   |
|  Debugging | Wed 7/12/11 | Fri 9/12/11 |   |   |
|  Buffer | Mon 12/12/11 | Wed 14/12/11 |   |   |
|  Milestone 1 |
| **Construction Phase** |
|  **Conference Engagement II - Web Platform (Iteration 3)** |
|  Revise Diagrams | Thu 15/12/11 | Thu 15/12/11 |   |   |
|  Develop test cases and test data | Thu 15/12/11 | Fri 16/12/11 |   |   |
|  Display sponsored children's details | Mon 19/12/11 | Fri 23/12/11 |   |   |
|  Develop live notes taking function | Mon 19/12/11 | Fri 23/12/11 |   |   |
|  Develop post conference feedback feature | Mon 26/12/11 | Tue 27/12/11 |   |   |
|  Deployment | Wed 28/12/11 | Thu 29/12/11 |   |   |
|  Test functions with test cases | Wed 28/12/11 | Thu 29/12/11 |   |   |
|  Debugging | Wed 28/12/11 | Thu 29/12/11 |   |   |
|  Buffer | Fri 30/12/11 | Fri 30/12/11 |   |   |
|  Milestone 2 |
|  **Attendees Engagement I - Web Platform (Iteration 4)** | **Mon 2/1/12** | **Fri 20/1/12** |  |   |
|  Revise Diagrams | Mon 2/1/12 | Mon 2/1/12 |   |   |
|  Develop test cases and test data | Tue 3/1/12 | Wed 4/1/12 |   |   |
|  Develop search function | Thu 5/1/12 | Wed 11/1/12 |   |   |
|  Develop forums feature | Thu 5/1/12 | Wed 11/1/12 |   |   |
|  Develop recommendation feature | Thu 12/1/12 | Tue 17/1/12 |   |   |
|  Deployment | Wed 18/1/12 | Thu 19/1/12 |   |   |
|  Test functions with test cases | Wed 18/1/12 | Thu 19/1/12 |   |   |
|  Debugging | Wed 18/1/12 | Thu 19/1/12 |   |   |
|  Buffer | Fri 20/1/12 | Fri 20/1/12 |   |   |
|  **Attendees Engagement II - Web Platform (Iteration 5)** |
|  Revise Diagrams | Mon 23/1/12 | Mon 23/1/12 |   |   |
|  Develop test cases and test data | Tue 24/1/12 | Wed 25/1/12 |   |   |
|  Develop web multilingual feature | Thu 26/1/12 | Tue 31/1/12 |   |   |
|  Develop Business Card System function | Wed 1/2/12 | Tue 7/2/12 |   |   |
|  Deployment | Wed 8/2/12 | Thu 9/2/12 |   |   |
|  Test functions with test cases | Wed 8/2/12 | Thu 9/2/12 |   |   |
|  Debugging | Wed 8/2/12 | Thu 9/2/12 |   |   |
|  Buffer | Fri 10/2/12 | Fri 10/2/12 |   |   |
|  Milestone 3 |
|  **Attendees Profile & UI - Mobile Platform (Iteration 6)** |
|  Design and develop UI for Mobile | Mon 13/2/12 | Wed 15/2/12 |   |   |
|  Revise Diagrams | Mon 13/2/12 | Mon 13/2/12 |   |   |
|  Develop test cases and test data | Tue 14/2/12 | Wed 15/2/12 |   |   |
|  Develop login function | Thu 16/2/12 | Fri 17/2/12 |   |   |
|  Display attendees profile | Thu 16/2/12 | Fri 17/2/12 |   |   |
|  Display Conference Details | Tue 21/2/12 | Thu 23/2/12 |   |   |
|  Deployment | Fri 24/2/12 | Mon 27/2/12 |   |   |
|  Test functions with test cases | Fri 24/2/12 | Mon 27/2/12 |   |   |
|  Debugging | Fri 24/2/12 | Mon 27/2/12 |   |   |
|  Buffer | Tue 28/2/12 | Tue 28/2/12 |   |   |
|  **Conference Engagement - Mobile Platform (Iteration 7)** |
|  Revise Diagrams | Wed 29/2/12 | Wed 29/2/12 |   |   |
|  Develop test cases and test data | Thu 1/3/12 | Fri 2/3/12 |   |   |
|  Display social announcements/news | Mon 5/3/12 | Tue 6/3/12 |   |   |
|  Display real-time conference feedback function | Mon 5/3/12 | Tue 6/3/12 |   |   |
|  Develop live voting function | Wed 7/3/12 | Fri 9/3/12 |   |   |
|  Deployment | Mon 12/3/12 | Tue 13/3/12 |   |   |
|  Test functions with test cases | Mon 12/3/12 | Tue 13/3/12 |   |   |
|  Debugging | Mon 12/3/12 | Tue 13/3/12 |   |   |
|  Buffer | Wed 14/3/12 | Fri 23/3/12 |   |   |
|  Milestone 4 | Fri 23/3/12 | Fri 23/3/12 |   |   |
| **Transition Phase** |
|  **Documentation** |
|  Design FYP Poster | Mon 26/3/12 | Fri 30/3/12 |   |   |
|  Finalize report | Fri 24/2/12 | Tue 10/4/12 |   |   |
|  Finalize user manual | Wed 11/4/12 | Thu 12/4/12 |   |   |
|  **Final Submission** |
|  Finalize slides and presentation for final presentation | Fri 13/4/12 | Thu 19/4/12 |   |   |
|  Handover deliverables to IMAPAC | Fri 13/4/12 | Thu 19/4/12 |   |   |