|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Task Name | Planned Start Date | Planned Finish Date | Actual Finish Date | Schedule Index |
| **Inception Phase** | | | | |
| **Requirements Gathering** | | | | |
| Understanding client's requirements | Mon 12/9/11 | Mon 19/9/11 | Mon 19/9/11 | 1.0 |
| Finalize project scope | Mon 19/9/11 | Mon 26/9/11 | Mon 26/9/11 | 1.0 |
| Research Drupal/CakePHP/Joomla | Tue 27/9/11 | Fri 21/10/11 | Fri 21/10/11 | 1.0 |
| Research Mobile Platforms | Tue 27/9/11 | Fri 21/10/11 | Fri 21/10/11 | 1.0 |
| Specify functionalities for Portal & Mobile | Tue 27/9/11 | Fri 21/10/11 | Fri 21/10/11 | 1.0 |
| Project Proposal Submission | Mon 24/10/11 | Mon 24/10/11 | Mon 24/10/11 | 1.0 |
| **Elaboration Phase** | | | | |
| **Attendees Profile & UI - Web Platform (Iteration 1)** | | | | |
| Design and develop UI for Web Portal | Tue 25/10/11 | Thu 27/10/11 | Thu 27/10/11 | 1.0 |
| Create Diagrams (Use Case, Solutions Architecture, Deployment) | Tue 25/10/11 | Thu 27/10/11 | Thu 27/10/11 | 1.0 |
| Design metrics (Bug, Schedule) | Tue 25/10/11 | Thu 27/10/11 | Thu 27/10/11 | 1.0 |
| Develop test cases and test data | Fri 28/10/11 | Mon 31/10/11 | Mon 31/10/11 | 1.0 |
| Develop user registration/login/logout function | Tue 1/11/11 | Wed 2/11/11 | Wed 2/11/11 | 1.0 |
| Display attendees profile | Thu 3/11/11 | Fri 4/11/11 | Fri 4/11/11 | 1.0 |
| Develop social networking function - friend system | Thu 3/11/11 | Tue 8/11/11 | Wed 9/11/11 | 1.1 |
| Deployment | Wed 9/11/11 | Thu 10/11/11 | Thu 10/11/11 | 1.0 |
| Test functions with test cases | Wed 9/11/11 | Thu 10/11/11 | Thu 10/11/11 | 1.0 |
| Debugging | Wed 9/11/11 | Thu 10/11/11 | Thu 10/11/11 | 1.0 |
| Buffer | Fri 11/11/11 | Fri 11/11/11 | Fri 11/11/11 | 1.0 |
| **Conference Engagement I - Web Platform (Iteration 2)** | | | | |
| Revise Diagrams | Mon 14/11/11 | Mon 14/11/11 | Mon 14/11/11 | 1.0 |
| Develop test cases and test data | Mon 14/11/11 | Tue 15/11/11 | Tue 15/11/11 | 1.0 |
| Display Conference Details | Wed 16/11/11 | Tue 22/11/11 | Thu 24/11/11 | 1.4 |
| Develop live voting function | Wed 16/11/11 | Tue 22/11/11 | Tue 22/11/11 | 1.0 |
| Develop Private Messaging System | Tue 29/11/11 | Tue 6/12/11 |  |  |
| Deployment | Wed 7/12/11 | Fri 9/12/11 |  |  |
| Test functions with test cases | Wed 7/12/11 | Fri 9/12/11 |  |  |
| Debugging | Wed 7/12/11 | Fri 9/12/11 |  |  |
| Buffer | Mon 12/12/11 | Wed 14/12/11 |  |  |
| Milestone 1 | | | | |
| **Construction Phase** | | | | |
| **Conference Engagement II - Web Platform (Iteration 3)** | | | | |
| Revise Diagrams | Thu 15/12/11 | Thu 15/12/11 |  |  |
| Develop test cases and test data | Thu 15/12/11 | Fri 16/12/11 |  |  |
| Display sponsored children's details | Mon 19/12/11 | Fri 23/12/11 |  |  |
| Develop live notes taking function | Mon 19/12/11 | Fri 23/12/11 |  |  |
| Develop post conference feedback feature | Mon 26/12/11 | Tue 27/12/11 |  |  |
| Deployment | Wed 28/12/11 | Thu 29/12/11 |  |  |
| Test functions with test cases | Wed 28/12/11 | Thu 29/12/11 |  |  |
| Debugging | Wed 28/12/11 | Thu 29/12/11 |  |  |
| Buffer | Fri 30/12/11 | Fri 30/12/11 |  |  |
| Milestone 2 | | | | |
| **Attendees Engagement I - Web Platform (Iteration 4)** | **Mon 2/1/12** | **Fri 20/1/12** |  |  |
| Revise Diagrams | Mon 2/1/12 | Mon 2/1/12 |  |  |
| Develop test cases and test data | Tue 3/1/12 | Wed 4/1/12 |  |  |
| Develop search function | Thu 5/1/12 | Wed 11/1/12 |  |  |
| Develop forums feature | Thu 5/1/12 | Wed 11/1/12 |  |  |
| Develop recommendation feature | Thu 12/1/12 | Tue 17/1/12 |  |  |
| Deployment | Wed 18/1/12 | Thu 19/1/12 |  |  |
| Test functions with test cases | Wed 18/1/12 | Thu 19/1/12 |  |  |
| Debugging | Wed 18/1/12 | Thu 19/1/12 |  |  |
| Buffer | Fri 20/1/12 | Fri 20/1/12 |  |  |
| **Attendees Engagement II - Web Platform (Iteration 5)** | | | | |
| Revise Diagrams | Mon 23/1/12 | Mon 23/1/12 |  |  |
| Develop test cases and test data | Tue 24/1/12 | Wed 25/1/12 |  |  |
| Develop web multilingual feature | Thu 26/1/12 | Tue 31/1/12 |  |  |
| Develop Business Card System function | Wed 1/2/12 | Tue 7/2/12 |  |  |
| Deployment | Wed 8/2/12 | Thu 9/2/12 |  |  |
| Test functions with test cases | Wed 8/2/12 | Thu 9/2/12 |  |  |
| Debugging | Wed 8/2/12 | Thu 9/2/12 |  |  |
| Buffer | Fri 10/2/12 | Fri 10/2/12 |  |  |
| Milestone 3 | | | | |
| **Attendees Profile & UI - Mobile Platform (Iteration 6)** | | | | |
| Design and develop UI for Mobile | Mon 13/2/12 | Wed 15/2/12 |  |  |
| Revise Diagrams | Mon 13/2/12 | Mon 13/2/12 |  |  |
| Develop test cases and test data | Tue 14/2/12 | Wed 15/2/12 |  |  |
| Develop login function | Thu 16/2/12 | Fri 17/2/12 |  |  |
| Display attendees profile | Thu 16/2/12 | Fri 17/2/12 |  |  |
| Display Conference Details | Tue 21/2/12 | Thu 23/2/12 |  |  |
| Deployment | Fri 24/2/12 | Mon 27/2/12 |  |  |
| Test functions with test cases | Fri 24/2/12 | Mon 27/2/12 |  |  |
| Debugging | Fri 24/2/12 | Mon 27/2/12 |  |  |
| Buffer | Tue 28/2/12 | Tue 28/2/12 |  |  |
| **Conference Engagement - Mobile Platform (Iteration 7)** | | | | |
| Revise Diagrams | Wed 29/2/12 | Wed 29/2/12 |  |  |
| Develop test cases and test data | Thu 1/3/12 | Fri 2/3/12 |  |  |
| Display social announcements/news | Mon 5/3/12 | Tue 6/3/12 |  |  |
| Display real-time conference feedback function | Mon 5/3/12 | Tue 6/3/12 |  |  |
| Develop live voting function | Wed 7/3/12 | Fri 9/3/12 |  |  |
| Deployment | Mon 12/3/12 | Tue 13/3/12 |  |  |
| Test functions with test cases | Mon 12/3/12 | Tue 13/3/12 |  |  |
| Debugging | Mon 12/3/12 | Tue 13/3/12 |  |  |
| Buffer | Wed 14/3/12 | Fri 23/3/12 |  |  |
| Milestone 4 | Fri 23/3/12 | Fri 23/3/12 |  |  |
| **Transition Phase** | | | | |
| **Documentation** | | | | |
| Design FYP Poster | Mon 26/3/12 | Fri 30/3/12 |  |  |
| Finalize report | Fri 24/2/12 | Tue 10/4/12 |  |  |
| Finalize user manual | Wed 11/4/12 | Thu 12/4/12 |  |  |
| **Final Submission** | | | | |
| Finalize slides and presentation for final presentation | Fri 13/4/12 | Thu 19/4/12 |  |  |
| Handover deliverables to IMAPAC | Fri 13/4/12 | Thu 19/4/12 |  |  |