## Legend
Legend
Design | HTML, CSS, Javascript
Develop | Yii - PHP
Deployment | AWS

## As of 13 July
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Comments
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 |  | 2012-06-09 | 2012-06-16
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 |  | 2012-06-09 | 2012-06-12 | All
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 |  | 2012-06-09 | 2012-06-12 | All
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 |  | 2012-06-10 | 2012-06-16 | All
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 |  | 2012-06-10 | 2012-06-16 | All
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 |  | 2012-06-11 | 2012-06-12 | Tsorng | Eileen
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 |  | 2012-06-17 | 2012-06-17 | All
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 |  | 2012-06-17 | 2012-06-18 | Michelle
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 |  | 2012-06-16 | 2012-06-16 | Nisa
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 |  | 2012-06-19 | 2012-06-19 | All
Milestone
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 |  | 2012-06-20 | 2012-06-20 | All
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 |  | 2012-06-20 | 2012-06-20 | All
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 |  | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | Postponed Sponsor meeting
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 |  | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | Change of date for team meet-up
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 |  | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 |  | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 |  | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07
| Function: Administration |  | 4 | 2012-07-08 | 2012-07-12
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 |  |  |  | Nisa
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11
|  | Design Profile_Projects page | 4 | 2012-07-08 | 2012-07-12
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 |  | 2012-08-06 | 2012-08-06
| Function: Project Proposal Approval |  | 19 | 2012-07-12 | 2012-07-31
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12
|  | Develop self-propose project function (incl NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28
| System Testing |  | 3 | 2012-07-28 | 2012-07-31
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 |  |  |  | All
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 |  |  |  | Eileen
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 |  |  |  | Michelle
Milestones
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 |  |  |  | All
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 |  |  |  | All
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21
| Function: Volunteer Profile Management |  | 10 | 2012-08-21 | 2012-08-31
|  | Develop sign up project function | 5 | 2012-08-21 | 2012-08-26
|  | Develop approve volunteer application function | 5 | 2012-08-21 | 2012-08-26
|  | Design Profile_About page | 1 | 2012-08-26 | 2012-08-27
|  | Develop profile management function | 4 | 2012-08-27 | 2012-08-31
|  | Unit Testing & Debugging | 2 | 2012-08-29 | 2012-08-31
| Function: Publishing |  | 8 | 2012-09-01 | 2012-09-09
|  | Design publishing media layout | 1 | 2012-09-01 | 2012-09-02
|  | Develop publish media function | 3 | 2012-09-01 | 2012-09-04
|  | Unit Testing & Debugging | 0 | 2012-09-04 | 2012-09-04
| System Testing |  | 0 | 2012-09-04 | 2012-09-04
| Deployment |  | 4 | 2012-09-05 | 2012-09-09
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10
| Function: Search (Part 1) |  | 10 | 2012-09-10 | 2012-09-20
|  | Design search function | 7 | 2012-09-10 | 2012-09-17
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| User Acceptance Test Preparation |  | 6 | 2012-09-17 | 2012-09-23
| System Testing |  | 0 | 2012-09-18 | 2012-09-18
| Deployment |  | 7 | 2012-09-19 | 2012-09-26
| Mid-Term Presentation Preparation |  | 7 | 2012-09-22 | 2012-09-29
Milestones
| User Acceptance Test |  | 2 | 2012-09-26 | 2012-09-28
| FYP Mid-term Presentation |  | 4 | 2012-10-01 | 2012-10-05
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 4 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (Part 2) |  | 16 | 2012-10-08 | 2012-10-24
|  | Develop search based on vicinity | 13 | 2012-10-08 | 2012-10-21
|  | Develop search based on specific location | 7 | 2012-10-08 | 2012-10-15
|  | Unit Testing & Debugging | 2 | 2012-10-22 | 2012-10-24
| Function: Social Network |  | 8 | 2012-10-25 | 2012-11-02
|  | Design social function | 4 | 2012-10-25 | 2012-10-29
|  | Develop Link to Facebook function | 7 | 2012-10-25 | 2012-11-01
|  | Develop Notification function | 7 | 2012-10-25 | 2012-11-01
|  | Develop comments function | 7 | 2012-10-25 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| System Testing |  | 0 | 2012-11-02 | 2012-11-02
| Deployment |  | 2 | 2012-11-03 | 2012-11-05
Function: Intelligence
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-29 | 2012-11-04
|  | Unit Testing & Debugging | 6 | 2012-10-29 | 2012-11-04
| System Testing |  | 0 | 2012-11-05 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Final Deployment |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of User Acceptance Test 2 |  | 5 | 2012-11-01 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Acceptance Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 9 Aug
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Comments
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All
Milestone
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | Postponed Sponsor meeting
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | Change of date for team meet-up
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 32 | 2012-07-07 | 2012-08-08
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle
| Function: Administration |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | Postponed due to unavailability and delayed due to unfamiliarity with Yii framework
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | Finished the original on 6 Aug, but change request for facebook login
|  | Design Home page | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa
| Function: Project Proposal Approval |  | 19 | 2012-07-12 | 2012-07-31 | 0
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng
|  | Develop self-propose project function (incl NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | Pending
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng
| System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 0
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 |  | 2012-08-10 |  | Eileen | All
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 |  | 2012-08-09 |  | Michelle | Nisa
Milestones
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 |  |  |  | All
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 |  |  |  | All
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21
| Function: Volunteer Profile Management |  | 10 | 2012-08-21 | 2012-08-31
|  | Develop sign up project function | 5 | 2012-08-21 | 2012-08-26
|  | Develop approve volunteer application function | 5 | 2012-08-21 | 2012-08-26
|  | Design Profile_About page | 1 | 2012-08-26 | 2012-08-27
|  | Develop profile management function | 4 | 2012-08-27 | 2012-08-31
|  | Unit Testing & Debugging | 2 | 2012-08-29 | 2012-08-31
| Function: Publishing |  | 8 | 2012-09-01 | 2012-09-09
|  | Design publishing media layout | 1 | 2012-09-01 | 2012-09-02
|  | Develop publish media function | 3 | 2012-09-01 | 2012-09-04
|  | Unit Testing & Debugging | 0 | 2012-09-04 | 2012-09-04
| System Testing |  | 0 | 2012-09-04 | 2012-09-04
| Deployment |  | 4 | 2012-09-05 | 2012-09-09
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10
| Function: Search (Part 1) |  | 10 | 2012-09-10 | 2012-09-20
|  | Design search function | 7 | 2012-09-10 | 2012-09-17
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| User Acceptance Test Preparation |  | 6 | 2012-09-17 | 2012-09-23
| System Testing |  | 0 | 2012-09-18 | 2012-09-18
| Deployment |  | 7 | 2012-09-19 | 2012-09-26
| Mid-Term Presentation Preparation |  | 7 | 2012-09-22 | 2012-09-29
Milestones
| User Acceptance Test |  | 2 | 2012-09-26 | 2012-09-28
| FYP Mid-term Presentation |  | 4 | 2012-10-01 | 2012-10-05
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 4 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (Part 2) |  | 16 | 2012-10-08 | 2012-10-24
|  | Develop search based on vicinity | 13 | 2012-10-08 | 2012-10-21
|  | Develop search based on specific location | 7 | 2012-10-08 | 2012-10-15
|  | Unit Testing & Debugging | 2 | 2012-10-22 | 2012-10-24
| Function: Social Network |  | 8 | 2012-10-25 | 2012-11-02
|  | Design social function | 4 | 2012-10-25 | 2012-10-29
|  | Develop Link to Facebook function | 7 | 2012-10-25 | 2012-11-01
|  | Develop Notification function | 7 | 2012-10-25 | 2012-11-01
|  | Develop comments function | 7 | 2012-10-25 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| System Testing |  | 0 | 2012-11-02 | 2012-11-02
| Deployment |  | 2 | 2012-11-03 | 2012-11-05
Function: Intelligence
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-29 | 2012-11-04
|  | Unit Testing & Debugging | 6 | 2012-10-29 | 2012-11-04
| System Testing |  | 0 | 2012-11-05 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Final Deployment |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of User Acceptance Test 2 |  | 5 | 2012-11-01 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Acceptance Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 13 Aug (hidden)
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1
| Milestone | [9 empty] | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1
1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 32 | 2012-07-07 | 2012-08-08 |  |  | 1.3333
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 | Closed
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143
| Milestones | [9 empty] | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21
| Function: Volunteer Profile Management & Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04
|  | Develop sign up project function | 5 | 2012-08-21 | 2012-08-26
|  | Design sign up project function | 5 | 2012-08-21 | 2012-08-26
|  | Design accept / reject volunteer function | 5 | 2012-08-21 | 2012-08-26
|  | Develop accept / reject volunteer function | 5 | 2012-08-21 | 2012-08-26
|  | Design volunteer profile management function page | 2 | 2012-08-26 | 2012-08-28
|  | Develop volunteer profile management function | 6 | 2012-08-27 | 2012-09-02
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04
|  | Design publishing media layout | 12 | 2012-08-21 | 2012-09-02
|  | Develop publish media function | 12 | 2012-08-21 | 2012-09-02
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04
| Integration & System Testing |  | 0 | 2012-09-04 | 2012-09-04
| Deployment |  | 4 | 2012-09-05 | 2012-09-09
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10
| Function: Search (Part 1) |  | 8 | 2012-09-10 | 2012-09-18
|  | Design search function | 7 | 2012-09-10 | 2012-09-17
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| User Acceptance Test Preparation |  | 6 | 2012-09-17 | 2012-09-23
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21
| Deployment |  | 3 | 2012-09-21 | 2012-09-24
| Mid-Term Presentation Preparation |  | 7 | 2012-09-22 | 2012-09-29
Milestones
| User Acceptance Test |  | 3 | 2012-09-25 | 2012-09-28
| FYP Mid-term Presentation |  | 4 | 2012-10-01 | 2012-10-05
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 4 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (Part 2) |  | 16 | 2012-10-08 | 2012-10-24
|  | Develop search based on vicinity | 13 | 2012-10-08 | 2012-10-21
|  | Develop search based on specific location | 7 | 2012-10-08 | 2012-10-15
|  | Unit Testing & Debugging | 2 | 2012-10-22 | 2012-10-24
| Function: Social Network |  | 16 | 2012-10-08 | 2012-10-24
|  | Design social function | 4 | 2012-10-08 | 2012-10-12
|  | Develop Link to Facebook function | 12 | 2012-10-12 | 2012-10-24
|  | Develop Notification function | 12 | 2012-10-12 | 2012-10-24
|  | Develop comments function | 7 | 2012-10-25 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| Integration & System Testing |  | 0 | 2012-10-25 | 2012-10-25
| Deployment |  | 10 | 2012-10-26 | 2012-11-05
| Function: Intelligence |  | 7 | 2012-10-29 | 2012-11-05
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-29 | 2012-11-04
|  | Unit Testing & Debugging | 6 | 2012-10-29 | 2012-11-04
| Integration & System Testing |  | 0 | 2012-11-05 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Final Deployment |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of User Acceptance Test 2 |  | 5 | 2012-11-01 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Acceptance Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 21 Aug
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1
| Milestone | [9 empty] | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1
1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 32 | 2012-07-07 | 2012-08-08 |  |  | 1.3333
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 | Pending
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143
| Milestones | [9 empty] | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 |  | 2012-08-21 | 2012-08-21 | All
| Function: Facebook Registration & Login |  | 14 | 2012-08-21 | 2012-09-04
|  | Develop Facebook Registration & Login | 12 | 2012-08-21 | 2012-09-02 |  | 2012-08-21 | 2012-09-01 | Aisya |  |  | Function dropped down
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 |  |  |  | Aisya
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04
|  | Develop sign up project function | 12 | 2012-08-21 | 2012-09-02 |  | 2012-08-21 |  | Eileen, Tsorng |  |  | May be behind schedule: Function put on hold on 29 Aug due to the additional task of changing UI
|  | Design sign up project function | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Eileen, Tsorng
|  | Design accept / reject volunteer function | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Eileen, Tsorng
|  | Develop accept / reject volunteer function | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Eileen, Tsorng
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 |  |  |  | Eileen, Tsorng
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04
|  | Design publishing media layout | 12 | 2012-08-21 | 2012-09-02 |  | 2012-08-21 |  | Michelle, Nisa
|  | Develop publish media function | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Michelle, Nisa
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 |  |  |  | Michelle, Nisa
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 |  |  |  | Eileen
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 |  |  |  | Eileen | Tsorng
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10
| Function: Search (Part 1) |  | 8 | 2012-09-10 | 2012-09-18
|  | Design search function | 7 | 2012-09-10 | 2012-09-17
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| Function: Volunteer Profile Management |  | 8 | 2012-09-10 | 2012-09-18
|  | Design volunteer profile management function page | 7 | 2012-09-10 | 2012-09-17
|  | Develop volunteer profile management function | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| User Acceptance Test Preparation |  | 5 | 2012-09-18 | 2012-09-23
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21
| Deployment |  | 3 | 2012-09-21 | 2012-09-24
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29
Milestones
| User Acceptance Test |  | 3 | 2012-09-25 | 2012-09-28
| FYP Mid-term Presentation |  | 4 | 2012-10-01 | 2012-10-05
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 4 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (Part 2) |  | 16 | 2012-10-08 | 2012-10-24
|  | Develop search based on vicinity | 13 | 2012-10-08 | 2012-10-21
|  | Develop search based on specific location | 7 | 2012-10-08 | 2012-10-15
|  | Unit Testing & Debugging | 2 | 2012-10-22 | 2012-10-24
| Function: Social Network |  | 16 | 2012-10-08 | 2012-10-24
|  | Design social function | 4 | 2012-10-08 | 2012-10-12
|  | Develop Link to Facebook function | 12 | 2012-10-12 | 2012-10-24
|  | Develop Notification function | 12 | 2012-10-12 | 2012-10-24
|  | Develop comments function | 7 | 2012-10-25 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| Integration & System Testing |  | 0 | 2012-10-25 | 2012-10-25
| Deployment |  | 10 | 2012-10-26 | 2012-11-05
| Function: Intelligence |  | 7 | 2012-10-29 | 2012-11-05
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-29 | 2012-11-04
|  | Unit Testing & Debugging | 6 | 2012-10-29 | 2012-11-04
| Integration & System Testing |  | 0 | 2012-11-05 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Final Deployment |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of User Acceptance Test 2 |  | 5 | 2012-11-01 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Acceptance Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 1 Sept (hidden)
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1
| Milestone | [9 empty] | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1
1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 32 | 2012-07-07 | 2012-08-08 |  |  | 1.3333
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 | Pending
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143
| Milestones | [9 empty] | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 |  | 2012-08-21 | 2012-08-21 | All
| Function: Register & Login |  | 6 | 2012-08-29 | 2012-09-04
|  | Edit registration accordingly to new UI (e.g include image upload) | 6 | 2012-09-01 | 2012-09-07 |  |  |  | Aisya
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04
|  | Change of UI for project management | 3 | 2012-09-02 | 2012-09-05 |  |  |  | Eileen, Tsorng
|  | Change of Workflow | 7 | 2012-09-02 | 2012-09-09 |  |  |  | Eileen, Tsorng
|  | Design & Develop Manage volunteer function | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Eileen, Tsorng
|  | Design & Develop Manage NGO function | 7 | 2012-09-09 | 2012-09-16 |  |  |  | Eileen, Tsorng
|  | Design & Develop Manage Sponsor function | 7 | 2012-09-09 | 2012-09-16 |  |  |  | Eileen, Tsorng
|  | Develop Manage Sponsor function | 0
|  | Develop Project Volunteer and Project Signup Box in Project Page | 2 | 2012-09-14 | 2012-09-16 |  |  |  | Eileen, Tsorng
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 |  |  |  | Eileen, Tsorng |  |  | Will be affected due to the change of scope
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04
|  | Design publish post layout | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Michelle, Nisa | Aisya
|  | Develop publish post function | 12 | 2012-08-21 | 2012-09-02 |  |  |  | Michelle, Nisa | Aisya
|  | Change of code logic due to new UI | 4 | 2012-09-11 | 2012-09-15 |  |  |  | Michelle
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 |  |  |  | Michelle, Nisa |  |  | Will be affected as publish post is needed
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 |  |  |  | Eileen
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 |  |  |  | Eileen | Tsorng
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10
| Function: Profile Management |  | 8 | 2012-09-10 | 2012-09-18
|  | Design profile management function page | 7 | 2012-09-10 | 2012-09-17
|  | Develop profile management function | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| User Acceptance Test Preparation |  | 5 | 2012-09-18 | 2012-09-23
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21
| Deployment |  | 3 | 2012-09-21 | 2012-09-24
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29
Milestones
| User Acceptance Test |  | 3 | 2012-09-25 | 2012-09-28
| FYP Mid-term Presentation |  | 4 | 2012-10-01 | 2012-10-05
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 4 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search |  | 18 | 2012-10-08 | 2012-10-26
|  | Design search function | 16 | 2012-10-08 | 2012-10-24
|  | Develop search | 16 | 2012-10-08 | 2012-10-24
|  | Unit Testing & Debugging | 1 | 2012-10-25 | 2012-10-26
| Function: Intelligence |  | 7 | 2012-10-08 | 2012-10-15
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Function: Project Management (partial) |  | 7 | 2012-10-08 | 2012-10-15
|  | Design sign up project function | 6 | 2012-10-08 | 2012-10-14
|  | Develop sign up project function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Integration & System Testing |  | 6 | 2012-10-26 | 2012-11-01
| Deployment |  | 3 | 2012-11-02 | 2012-11-05
| Integration & System Testing |  | 0 | 2012-11-05 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Final Deployment |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of User Acceptance Test 2 |  | 5 | 2012-11-01 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Acceptance Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 1 oct (hidden)
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1
| Milestone | [9 empty] | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1
1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 32 | 2012-07-07 | 2012-08-08 |  |  | 1.3333
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143
| Milestones | [9 empty] | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 |  | 2012-08-21 | 2012-08-21 | All
| Function: Register & Login |  | 6 | 2012-08-29 | 2012-09-04
|  | Edit registration accordingly to new UI (e.g include image upload) | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 | Aisya
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04 | 23 | 2012-09-02 | 2012-09-25
|  | Change of UI for project management | 3 | 2012-09-02 | 2012-09-05 | 1 | 2012-09-02 | 2012-09-03 | Eileen, Tsorng
|  | Change of Workflow | 7 | 2012-09-02 | 2012-09-09 | 6 | 2012-09-04 | 2012-09-10 | Eileen, Tsorng
|  | Design & Develop Manage volunteer function | 12 | 2012-08-21 | 2012-09-02 | 3 | 2012-09-11 | 2012-09-14 | Eileen, Tsorng
|  | Design & Develop Manage NGO function | 7 | 2012-09-09 | 2012-09-16 | 2 | 2012-09-15 | 2012-09-17 | Eileen, Tsorng
|  | Design & Develop Manage Sponsor function | 7 | 2012-09-09 | 2012-09-16 | 1 | 2012-09-18 | 2012-09-19 | Eileen, Tsorng
|  | Develop Manage Sponsor function | 0 |  |  | 0
|  | Develop Project Volunteer and Project Signup Box in Project Page | 2 | 2012-09-14 | 2012-09-16 | 1 | 2012-09-22 | 2012-09-23 | Eileen, Tsorng
|  | Unit Testing & Debugging | 2 | 2012-09-16 | 2012-09-18 | 1 | 2012-09-24 | 2012-09-25 | Eileen
| Function: Publishing Post |  | 14 | 2012-08-21 | 2012-09-04 | 37 | 2012-08-21 | 2012-09-27
|  | Design publish post layout | 12 | 2012-08-21 | 2012-09-02 | 19 | 2012-09-04 | 2012-09-23 | Michelle, Nisa | Aisya
|  | Develop publish post function | 12 | 2012-08-21 | 2012-09-02 | 19 | 2012-09-04 | 2012-09-23 | Michelle, Nisa | Aisya
|  | Change of code logic due to new UI | 4 | 2012-09-11 | 2012-09-15 | 2 | 2012-09-23 | 2012-09-25 | Michelle
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | [6 empty] | Need to push to next iteration
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | 2 | 2012-09-25 | 2012-09-27 | Michelle, Nisa |  |  | Will be affected as publish post is needed
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 | 2 | 2012-09-28 | 2012-09-30 | Eileen
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 | 2 | 2012-09-28 | 2012-09-30 | Eileen | Tsorng
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05
| User Acceptance Test Preparation |  | 5 | 2012-09-18 | 2012-09-23 | 2 | 2012-09-28 | 2012-09-30 | Aisya
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29 |  | 2012-09-30 |  | Michelle | Nisa
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10 | 0 | 2012-10-01 | 2012-10-01 | All
| Function: Profile Management |  | 8 | 2012-09-10 | 2012-09-18
|  | Design profile management function page | 7 | 2012-09-10 | 2012-09-17
|  | Develop profile management function | 7 | 2012-09-10 | 2012-09-17
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21
| Deployment |  | 3 | 2012-09-21 | 2012-09-24
Milestones
| User Acceptance Test |  | 0 | 2012-10-01 | 2012-10-01 |  |  |  | All
| FYP Mid-term Presentation |  | 0 | 2012-10-05 | 2012-10-05 |  |  |  | All
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 4 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search |  | 18 | 2012-10-08 | 2012-10-26
|  | Design search function | 16 | 2012-10-08 | 2012-10-24
|  | Develop search | 16 | 2012-10-08 | 2012-10-24
|  | Unit Testing & Debugging | 1 | 2012-10-25 | 2012-10-26
| Function: Intelligence |  | 7 | 2012-10-08 | 2012-10-15
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Function: Project Management (partial) |  | 7 | 2012-10-08 | 2012-10-15
|  | Design sign up project function | 6 | 2012-10-08 | 2012-10-14
|  | Develop sign up project function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Integration & System Testing |  | 6 | 2012-10-26 | 2012-11-01
| Deployment |  | 3 | 2012-11-02 | 2012-11-05
| Integration & System Testing |  | 0 | 2012-11-05 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Final Deployment |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of User Acceptance Test 2 |  | 5 | 2012-11-01 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Acceptance Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 10 Oct
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments | Schedule Metric
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1 |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1 |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1 |  | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1 |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1 |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1 |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1 |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1 |  | 1
| Milestone | [9 empty] | 1 |  | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting | 3
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up | 1
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 |  | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 33 | 2012-07-07 | 2012-08-09 |  |  | 1.375 |  | 1.375
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1 |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework | 6.25
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1 |  | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability | 2
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login | 2
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1 |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1 |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211 |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1 |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286 |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 |  | 0
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1 |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667 |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895 |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1 |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273 |  | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143 |  | 0.57143
| Milestones | [9 empty] | 1 |  | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1 |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1 |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09 | 40 | 2012-08-21 | 2012-09-30 |  |  | 2.1053 |  | 2.1053
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 | 0 | 2012-08-21 | 2012-08-21 | All |  |  |  | 1
| Function: Facebook Register & Login |  | 12 | 2012-08-21 | 2012-09-02 | - | 2012-08-21 | - | Aisya |  |  | Removed after re-scoping
|  | Develop Facebook Registration & Login | 2 | 2012-09-02 | 2012-09-04 | - | 2012-08-21 | - | Aisya
| Function: Register & Login |  | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 |  |  |  |  | 4.6667
|  | Edit registration accordingly to new UI (e.g include image upload) | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 | Aisya |  |  |  | 4.6667
|  | Unit Testing & Debugging | 0 | 2012-09-07 | 2012-09-07 | 0 | 2012-09-30 | 2012-09-30 | Aisya |  |  |  | 1
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04 | 23 | 2012-09-02 | 2012-09-25 |  |  |  | Extend of planned dates due to change of logic | 1.6429
|  | Design & Develop Manage volunteer function | 12 | 2012-08-21 | 2012-09-02 | 3 | 2012-09-11 | 2012-09-14 | Eileen, Tsorng |  |  |  | 0.25
|  | Develop sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Design sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Change of UI for project management | 3 | 2012-09-02 | 2012-09-05 | 1 | 2012-09-02 | 2012-09-03 | Eileen, Tsorng |  |  |  | 0.33333
|  | Change of Workflow for project approval | 7 | 2012-09-02 | 2012-09-09 | 6 | 2012-09-04 | 2012-09-10 | Eileen, Tsorng |  |  |  | 0.85714
|  | Design & Develop Manage NGO function | 7 | 2012-09-09 | 2012-09-16 | 2 | 2012-09-15 | 2012-09-17 | Eileen, Tsorng |  |  |  | 0.28571
|  | Design & Develop Manage Sponsor function | 7 | 2012-09-09 | 2012-09-16 | 1 | 2012-09-18 | 2012-09-19 | Eileen, Tsorng |  |  |  | 0.14286
|  | Develop Manage Sponsor function | 0 |  |  | 0 | [6 empty] | 1
|  | Develop Project Volunteer and Project Signup Box in Project Page | 2 | 2012-09-14 | 2012-09-16 | 1 | 2012-09-22 | 2012-09-23 | Eileen, Tsorng |  |  |  | 0.5
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 1 | 2012-09-24 | 2012-09-25 | Eileen |  |  |  | 0.5
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04 |  | 2012-09-04 | - |  |  |  | Extend of planned dates due to change of logic | 0
|  | Design publish post layout | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa | Aisya |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Develop publish post function | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Change of code logic due to new UI | 4 | 2012-09-11 | 2012-09-15 | - | 2012-09-23 | - | Michelle |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | - | 2012-09-25 | - | Michelle, Nisa |  |  | Postpone to another iteration due to incomplete of publish post
| Function: Volunteer Profile Management |  | 10 | 2012-08-21 | 2012-08-31 | [6 empty] | Postpone to next iteration | 0
|  | Develop profile management function | 10 | 2012-08-21 | 2012-08-31 | - | - | -
|  | Unit Testing & Debugging | 2 | 2012-08-29 | 2012-08-31 | - | - | -
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 | 2 | 2012-09-28 | 2012-09-30 | Eileen |  |  |  | 1
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 | 2 | 2012-09-28 | 2012-09-30 | Eileen | Tsorng |  |  | 0.66667
| User Test 1 Preparation (postponed) |  | 5 | 2012-09-18 | 2012-09-23 | - | 2012-09-28 | - | Aisya |  |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
| Mid-Term Presentation Preparation (postponed) |  | 5 | 2012-09-24 | 2012-09-29 | - | 2012-09-30 | - | Michelle | Nisa |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05 | 9 | 2012-10-01 | 2012-10-10 |  |  |  |  | 0.36
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10 | 0 | 2012-10-01 | 2012-10-01 | All |  |  |  | 1
| Function: Profile Management (partial) |  | 8 | 2012-09-10 | 2012-09-18 | 5 | 2012-10-02 | 2012-10-07 |  |  |  |  | 0.625
|  | Design Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 1 | 2012-10-02 | 2012-10-03 | Eileen |  |  |  | 0.14286
|  | Develop Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 2 | 2012-10-03 | 2012-10-05 | Eileen |  |  |  | 0.28571
|  | Design Volunteer Profile management function page | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-02 | - | Tsorng |  |  | On hold due to incompletion of certain functionalities
|  | Develop Volunteer Profile management function | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-03 | - | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | 0 | 2012-10-07 | 2012-10-07 | Eileen, Tsorng |  |  |  | 1
| Function: Publishing (Article) |  | 8 | 2012-09-10 | 2012-09-18 | 6 | 2012-10-02 | 2012-10-08 |  |  |  |  | 0.75
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | 0 | 2012-10-08 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0
| Function: Project Management |  | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 |  |  |  |  | 0.16667
|  | Design sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Develop sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 0 | 2012-10-07 | 2012-10-07 | Eileen |  |  |  | 0
| Function: Search |  | 10 | 2012-09-10 | 2012-09-20 | [6 empty] | Adjusted to next iteration due to re-scope | 0
|  | Design search function | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | - | - | - |  |  |  |  | 1
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21 | 0 | 2012-10-08 | 2012-10-08 | Eileen, Tsorng |  |  |  | 0
| Deployment |  | 3 | 2012-09-21 | 2012-09-24 | 1 | 2012-10-08 | 2012-10-09 | Eileen |  |  |  | 0.33333
| User Test 1 Preparation |  | 5 | 2012-09-18 | 2012-09-23 | 0 | 2012-10-08 | 2012-10-08 | Aisya | All |  | Resumed task | 0
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29 | 1 | 2012-10-08 | 2012-10-09 | Michelle | All |  | Resumed task | 0.2
| Milestones | [11 empty] | 1
| User Test 1 |  | 0 | 2012-10-01 | 2012-10-01 | 0 | 2012-10-09 | 2012-10-09 | All |  |  |  | 1
| FYP Mid-term Presentation |  | 0 | 2012-10-05 | 2012-10-05 | 0 | 2012-10-10 | 2012-10-10 | All |  |  |  | 1
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 5 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search |  | 18 | 2012-10-08 | 2012-10-26
|  | Design search function | 16 | 2012-10-08 | 2012-10-24
|  | Develop search | 16 | 2012-10-08 | 2012-10-24
|  | Unit Testing & Debugging | 1 | 2012-10-25 | 2012-10-26
| Function: Intelligence |  | 7 | 2012-10-08 | 2012-10-15
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Function: Publishing (Post) |  | 17 | 2012-10-15 | 2012-11-01
|  | Design publish post layout (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Develop publish post function (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| Function: Profile Management |  | 20 | 2012-10-15 | 2012-11-04
|  | Volunteer Profile: Edit volunteer experience | 7 | 2012-10-15 | 2012-10-22
|  | Volunteer Profile: Link to volunteer's article | 7 | 2012-10-15 | 2012-10-22
|  | Volunteer Profile: Link to volunteer's post | 2 | 2012-11-02 | 2012-11-04
|  | Unit Testing & Debugging | 0 | 2012-11-04 | 2012-11-04
| Integration & System Testing |  | 3 | 2012-11-01 | 2012-11-04
| Deployment |  | 1 | 2012-11-04 | 2012-11-05
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Preparation of User Test 2 |  | 0 | 2012-11-06 | 2012-11-06
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Test 2 |  | 2 | 2012-11-07 | 2012-11-09
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 9 | 2012-11-26 | 2012-12-05
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 13 Nov
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments | Schedule Metric
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1 |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1 |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1 |  | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1 |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1 |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1 |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1 |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1 |  | 1
| Milestone | [9 empty] | 1 |  | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting | 3
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up | 1
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 |  | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 33 | 2012-07-07 | 2012-08-09 |  |  | 1.375 |  | 1.375
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1 |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework | 6.25
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1 |  | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability | 2
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login | 2
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1 |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1 |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211 |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1 |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286 |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 |  | 0
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1 |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667 |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895 |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1 |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273 |  | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143 |  | 0.57143
| Milestones | [9 empty] | 1 |  | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1 |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1 |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09 | 40 | 2012-08-21 | 2012-09-30 |  |  | 2.1053 |  | 2.1053
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 | 0 | 2012-08-21 | 2012-08-21 | All |  |  |  | 1
| Function: Facebook Register & Login |  | 12 | 2012-08-21 | 2012-09-02 | - | 2012-08-21 | - | Aisya |  |  | Removed after re-scoping
|  | Develop Facebook Registration & Login | 2 | 2012-09-02 | 2012-09-04 | - | 2012-08-21 | - | Aisya
| Function: Register & Login |  | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 |  |  |  |  | 4.6667
|  | Edit registration accordingly to new UI (e.g include image upload) | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 | Aisya |  |  |  | 4.6667
|  | Unit Testing & Debugging | 0 | 2012-09-07 | 2012-09-07 | 0 | 2012-09-30 | 2012-09-30 | Aisya |  |  |  | 1
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04 | 23 | 2012-09-02 | 2012-09-25 |  |  |  | Extend of planned dates due to change of logic | 1.6429
|  | Design & Develop Manage volunteer function | 12 | 2012-08-21 | 2012-09-02 | 3 | 2012-09-11 | 2012-09-14 | Eileen, Tsorng |  |  |  | 0.25
|  | Develop sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Design sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Change of UI for project management | 3 | 2012-09-02 | 2012-09-05 | 1 | 2012-09-02 | 2012-09-03 | Eileen, Tsorng |  |  |  | 0.33333
|  | Change of Workflow for project approval | 7 | 2012-09-02 | 2012-09-09 | 6 | 2012-09-04 | 2012-09-10 | Eileen, Tsorng |  |  |  | 0.85714
|  | Design & Develop Manage NGO function | 7 | 2012-09-09 | 2012-09-16 | 2 | 2012-09-15 | 2012-09-17 | Eileen, Tsorng |  |  |  | 0.28571
|  | Design & Develop Manage Sponsor function | 7 | 2012-09-09 | 2012-09-16 | 1 | 2012-09-18 | 2012-09-19 | Eileen, Tsorng |  |  |  | 0.14286
|  | Develop Manage Sponsor function | 0 |  |  | 0 | [6 empty] | 1
|  | Develop Project Volunteer and Project Signup Box in Project Page | 2 | 2012-09-14 | 2012-09-16 | 1 | 2012-09-22 | 2012-09-23 | Eileen, Tsorng |  |  |  | 0.5
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 1 | 2012-09-24 | 2012-09-25 | Eileen |  |  |  | 0.5
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04 |  | 2012-09-04 | - |  |  |  | Extend of planned dates due to change of logic | 0
|  | Design publish post layout | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa | Aisya |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Develop publish post function | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Change of code logic due to new UI | 4 | 2012-09-11 | 2012-09-15 | - | 2012-09-23 | - | Michelle |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | - | 2012-09-25 | - | Michelle, Nisa |  |  | Postpone to another iteration due to incomplete of publish post
| Function: Volunteer Profile Management |  | 10 | 2012-08-21 | 2012-08-31 | [6 empty] | Postpone to next iteration | 0
|  | Develop profile management function | 10 | 2012-08-21 | 2012-08-31 | - | - | -
|  | Unit Testing & Debugging | 2 | 2012-08-29 | 2012-08-31 | - | - | -
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 | 2 | 2012-09-28 | 2012-09-30 | Eileen |  |  |  | 1
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 | 2 | 2012-09-28 | 2012-09-30 | Eileen | Tsorng |  |  | 0.66667
| User Test 1 Preparation (postponed) |  | 5 | 2012-09-18 | 2012-09-23 | - | 2012-09-28 | - | Aisya |  |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
| Mid-Term Presentation Preparation (postponed) |  | 5 | 2012-09-24 | 2012-09-29 | - | 2012-09-30 | - | Michelle | Nisa |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05 | 9 | 2012-10-01 | 2012-10-10 |  |  |  |  | 0.36
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10 | 0 | 2012-10-01 | 2012-10-01 | All |  |  |  | 1
| Function: Profile Management (partial) |  | 8 | 2012-09-10 | 2012-09-18 | 5 | 2012-10-02 | 2012-10-07 |  |  |  |  | 0.625
|  | Design Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 1 | 2012-10-02 | 2012-10-03 | Eileen |  |  |  | 0.14286
|  | Develop Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 2 | 2012-10-03 | 2012-10-05 | Eileen |  |  |  | 0.28571
|  | Design Volunteer Profile management function page | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-02 | - | Tsorng |  |  | On hold due to incompletion of certain functionalities
|  | Develop Volunteer Profile management function | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-03 | - | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | 0 | 2012-10-07 | 2012-10-07 | Eileen, Tsorng |  |  |  | 1
| Function: Publishing (Article) |  | 8 | 2012-09-10 | 2012-09-18 | 6 | 2012-10-02 | 2012-10-08 |  |  |  |  | 0.75
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | 0 | 2012-10-08 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0
| Function: Project Management |  | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 |  |  |  |  | 0.16667
|  | Design sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Develop sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 0 | 2012-10-07 | 2012-10-07 | Eileen |  |  |  | 0
| Function: Search |  | 10 | 2012-09-10 | 2012-09-20 | [6 empty] | Adjusted to next iteration due to re-scope | 0
|  | Design search function | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | - | - | - |  |  |  |  | 1
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21 | 0 | 2012-10-08 | 2012-10-08 | Eileen, Tsorng |  |  |  | 0
| Deployment |  | 3 | 2012-09-21 | 2012-09-24 | 1 | 2012-10-08 | 2012-10-09 | Eileen |  |  |  | 0.33333
| User Test 1 Preparation |  | 5 | 2012-09-18 | 2012-09-23 | 0 | 2012-10-08 | 2012-10-08 | Aisya | All |  | Resumed task | 0
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29 | 1 | 2012-10-08 | 2012-10-09 | Michelle | All |  | Resumed task | 0.2
| Milestones | [11 empty] | 1
| User Test 1 |  | 0 | 2012-10-01 | 2012-10-01 | 0 | 2012-10-09 | 2012-10-09 | All |  |  |  | 1
| FYP Mid-term Presentation |  | 0 | 2012-10-05 | 2012-10-05 | 0 | 2012-10-10 | 2012-10-10 | All |  |  |  | 1
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05
| Review of Iteration 5 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (incomplete) |  | 18 | 2012-10-08 | 2012-10-26 |  | 2012-11-01 | 2012-11-07 |  |  |  | Adjusted to next iteration, unsuccessful attempt from 1 nov - 7 Nov
|  | Design search function | 16 | 2012-10-08 | 2012-10-24 |  | 2012-11-01 | 2012-11-07 | Nisa
|  | Develop search | 16 | 2012-10-08 | 2012-10-24 |  | 2012-11-01 | 2012-11-07 | Nisa
|  | Unit Testing & Debugging | 1 | 2012-10-25 | 2012-10-26
| Function: Intelligence |  | 7 | 2012-10-08 | 2012-10-15 | [6 empty] | Removed from scope
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Function: Publishing (Post) |  | 17 | 2012-10-15 | 2012-11-01 | [6 empty] | Removed from scope
|  | Design publish post layout (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Develop publish post function (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| Function: Profile Management |  | 20 | 2012-10-15 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28
|  | Volunteer Profile: Edit volunteer experience | 7 | 2012-10-15 | 2012-10-22 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Volunteer Profile: Link to volunteer's article | 7 | 2012-10-15 | 2012-10-22 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Volunteer Profile: Link to volunteer's post | 2 | 2012-11-02 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-11-04 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
| Debugging after UT 1 |  | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07
|  | Register & Login | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Aisya
|  | Project Management | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Eileen, Tsorng
|  | Profile Management | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Eileen, Tsorng
|  | Publishing (Article) | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Michelle | Aisya, Nisa
| Integration & System Testing |  | 3 | 2012-11-01 | 2012-11-04 | 1 | 2012-11-08 | 2012-11-09 | Eileen, Tsorng
| Deployment |  | 1 | 2012-11-04 | 2012-11-05 | 0 | 2012-11-09 | 2012-11-09 | Eileen
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07
| Preparation of User Test 2 |  | 0 | 2012-11-06 | 2012-11-06 |  | 2012-11-09 | 2012-11-09 | Aisya, Michelle
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11 |  | 2012-11-09 | 2012-11-11 | Nisa
| Preparation of FYP Video |  | 1 | 2012-11-10 | 2012-11-11 |  | 2012-11-11 | 2012-11-11 | Aisya, Michelle
| Function: Search (resume) |  | 0
|  | Design search function | 12 | 2012-11-17 | 2012-11-29 |  |  |  | Eileen, Tsorng
|  | Develop search | 12 | 2012-11-17 | 2012-11-29 |  |  |  | Eileen, Tsorng
|  | Unit Testing & Debugging | 12 | 2012-11-17 | 2012-11-29 |  |  |  | Eileen, Tsorng
| Debugging after UT 2 |  | 0
|  | Register & Login | 7 | 2012-11-17 | 2012-11-24 |  |  |  | Aisya
|  | Project Management | 7 | 2012-11-17 | 2012-11-24 |  |  |  | Eileen, Tsorng
|  | Profile Management | 7 | 2012-11-17 | 2012-11-24 |  |  |  | Eileen, Tsorng
|  | Publishing (Article) | 7 | 2012-11-17 | 2012-11-24 |  |  |  | Michelle | Aisya
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23
Milestones
| User Test 2 |  | 1 | 2012-11-10 | 2012-11-11 | 3 | 2012-11-10 | 2012-11-13
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12 | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 0 | 2012-12-03 | 2012-12-03
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## As of 28 Nov 12
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments | Schedule Metric
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1 |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1 |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1 |  | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1 |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1 |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1 |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1 |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1 |  | 1
| Milestone | [9 empty] | 1 |  | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting | 3
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up | 1
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 |  | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 33 | 2012-07-07 | 2012-08-09 |  |  | 1.375 |  | 1.375
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1 |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework | 6.25
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1 |  | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability | 2
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login | 2
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1 |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1 |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211 |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1 |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286 |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 |  | 0
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1 |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667 |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895 |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1 |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273 |  | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143 |  | 0.57143
| Milestones | [9 empty] | 1 |  | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1 |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1 |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09 | 40 | 2012-08-21 | 2012-09-30 |  |  | 2.1053 |  | 2.1053
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 | 0 | 2012-08-21 | 2012-08-21 | All |  |  |  | 1
| Function: Facebook Register & Login |  | 12 | 2012-08-21 | 2012-09-02 | - | 2012-08-21 | - | Aisya |  |  | Removed after re-scoping
|  | Develop Facebook Registration & Login | 2 | 2012-09-02 | 2012-09-04 | - | 2012-08-21 | - | Aisya
| Function: Register & Login |  | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 |  |  |  |  | 4.6667
|  | Edit registration accordingly to new UI (e.g include image upload) | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 | Aisya |  |  |  | 4.6667
|  | Unit Testing & Debugging | 0 | 2012-09-07 | 2012-09-07 | 0 | 2012-09-30 | 2012-09-30 | Aisya |  |  |  | 1
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04 | 23 | 2012-09-02 | 2012-09-25 |  |  |  | Extend of planned dates due to change of logic | 1.6429
|  | Design & Develop Manage volunteer function | 12 | 2012-08-21 | 2012-09-02 | 3 | 2012-09-11 | 2012-09-14 | Eileen, Tsorng |  |  |  | 0.25
|  | Develop sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Design sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Change of UI for project management | 3 | 2012-09-02 | 2012-09-05 | 1 | 2012-09-02 | 2012-09-03 | Eileen, Tsorng |  |  |  | 0.33333
|  | Change of Workflow for project approval | 7 | 2012-09-02 | 2012-09-09 | 6 | 2012-09-04 | 2012-09-10 | Eileen, Tsorng |  |  |  | 0.85714
|  | Design & Develop Manage NGO function | 7 | 2012-09-09 | 2012-09-16 | 2 | 2012-09-15 | 2012-09-17 | Eileen, Tsorng |  |  |  | 0.28571
|  | Design & Develop Manage Sponsor function | 7 | 2012-09-09 | 2012-09-16 | 1 | 2012-09-18 | 2012-09-19 | Eileen, Tsorng |  |  |  | 0.14286
|  | Develop Manage Sponsor function | 0 |  |  | 0 | [6 empty] | 1
|  | Develop Project Volunteer and Project Signup Box in Project Page | 2 | 2012-09-14 | 2012-09-16 | 1 | 2012-09-22 | 2012-09-23 | Eileen, Tsorng |  |  |  | 0.5
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 1 | 2012-09-24 | 2012-09-25 | Eileen |  |  |  | 0.5
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04 |  | 2012-09-04 | - |  |  |  | Extend of planned dates due to change of logic | 0
|  | Design publish post layout | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa | Aisya |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Develop publish post function | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Change of code logic due to new UI | 4 | 2012-09-11 | 2012-09-15 | - | 2012-09-23 | - | Michelle |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | - | 2012-09-25 | - | Michelle, Nisa |  |  | Postpone to another iteration due to incomplete of publish post
| Function: Volunteer Profile Management |  | 10 | 2012-08-21 | 2012-08-31 | [6 empty] | Postpone to next iteration | 0
|  | Develop profile management function | 10 | 2012-08-21 | 2012-08-31 | - | - | -
|  | Unit Testing & Debugging | 2 | 2012-08-29 | 2012-08-31 | - | - | -
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 | 2 | 2012-09-28 | 2012-09-30 | Eileen |  |  |  | 1
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 | 2 | 2012-09-28 | 2012-09-30 | Eileen | Tsorng |  |  | 0.66667
| User Test 1 Preparation (postponed) |  | 5 | 2012-09-18 | 2012-09-23 | - | 2012-09-28 | - | Aisya |  |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
| Mid-Term Presentation Preparation (postponed) |  | 5 | 2012-09-24 | 2012-09-29 | - | 2012-09-30 | - | Michelle | Nisa |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05 | 9 | 2012-10-01 | 2012-10-10 |  |  |  |  | 0.36
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10 | 0 | 2012-10-01 | 2012-10-01 | All |  |  |  | 1
| Function: Profile Management (partial) |  | 8 | 2012-09-10 | 2012-09-18 | 5 | 2012-10-02 | 2012-10-07 |  |  |  |  | 0.625
|  | Design Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 1 | 2012-10-02 | 2012-10-03 | Eileen |  |  |  | 0.14286
|  | Develop Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 2 | 2012-10-03 | 2012-10-05 | Eileen |  |  |  | 0.28571
|  | Design Volunteer Profile management function page | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-02 | - | Tsorng |  |  | On hold due to incompletion of certain functionalities
|  | Develop Volunteer Profile management function | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-03 | - | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | 0 | 2012-10-07 | 2012-10-07 | Eileen, Tsorng |  |  |  | 1
| Function: Publishing (Article) |  | 8 | 2012-09-10 | 2012-09-18 | 6 | 2012-10-02 | 2012-10-08 |  |  |  |  | 0.75
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | 0 | 2012-10-08 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0
| Function: Project Management |  | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 |  |  |  |  | 0.16667
|  | Design sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Develop sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 0 | 2012-10-07 | 2012-10-07 | Eileen |  |  |  | 0
| Function: Search |  | 10 | 2012-09-10 | 2012-09-20 | [6 empty] | Adjusted to next iteration due to re-scope | 0
|  | Design search function | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | - | - | - |  |  |  |  | 1
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21 | 0 | 2012-10-08 | 2012-10-08 | Eileen, Tsorng |  |  |  | 0
| Deployment |  | 3 | 2012-09-21 | 2012-09-24 | 1 | 2012-10-08 | 2012-10-09 | Eileen |  |  |  | 0.33333
| User Test 1 Preparation |  | 5 | 2012-09-18 | 2012-09-23 | 0 | 2012-10-08 | 2012-10-08 | Aisya | All |  | Resumed task | 0
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29 | 1 | 2012-10-08 | 2012-10-09 | Michelle | All |  | Resumed task | 0.2
| Milestones | [11 empty] | 1
| User Test 1 |  | 0 | 2012-10-01 | 2012-10-01 | 0 | 2012-10-09 | 2012-10-09 | All |  |  |  | 1
| FYP Mid-term Presentation |  | 0 | 2012-10-05 | 2012-10-05 | 0 | 2012-10-10 | 2012-10-10 | All |  |  |  | 1
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05 | 19 | 2012-10-21 | 2012-11-09 |  |  |  |  | 0.63333
| Review of Iteration 5 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (incomplete) |  | 18 | 2012-10-08 | 2012-10-26 |  | 2012-11-01 | 2012-11-07 |  |  |  | Adjusted to next iteration, unsuccessful attempt from 1 nov - 7 Nov
|  | Design search function | 16 | 2012-10-08 | 2012-10-24 |  | 2012-11-01 | 2012-11-07 | Nisa
|  | Develop search | 16 | 2012-10-08 | 2012-10-24 |  | 2012-11-01 | 2012-11-07 | Nisa
|  | Unit Testing & Debugging | 1 | 2012-10-25 | 2012-10-26
| Function: Intelligence |  | 7 | 2012-10-08 | 2012-10-15 | [6 empty] | Removed from scope
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Function: Publishing (Post) |  | 17 | 2012-10-15 | 2012-11-01 | [6 empty] | Removed from scope
|  | Design publish post layout (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Develop publish post function (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| Function: Profile Management |  | 20 | 2012-10-15 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28
|  | Volunteer Profile: Edit volunteer experience | 7 | 2012-10-15 | 2012-10-22 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Volunteer Profile: Link to volunteer's article | 7 | 2012-10-15 | 2012-10-22 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Volunteer Profile: Link to volunteer's post | 2 | 2012-11-02 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-11-04 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
| Debugging after UT 1 |  | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07
|  | Register & Login | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Aisya
|  | Project Management | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Eileen, Tsorng
|  | Profile Management | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Eileen, Tsorng
|  | Publishing (Article) | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Michelle | Aisya, Nisa
| Integration & System Testing |  | 3 | 2012-11-01 | 2012-11-04 | 1 | 2012-11-08 | 2012-11-09 | Eileen, Tsorng
| Deployment |  | 1 | 2012-11-04 | 2012-11-05 | 0 | 2012-11-09 | 2012-11-09 | Eileen
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07 | 28 | 2012-11-09 | 2012-12-07
| Preparation of User Test 2 |  | 0 | 2012-11-06 | 2012-11-06 | 0 | 2012-11-09 | 2012-11-09 | Aisya, Michelle
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11 | 2 | 2012-11-09 | 2012-11-11 | Nisa
| Preparation of FYP Video |  | 1 | 2012-11-10 | 2012-11-11 | 0 | 2012-11-11 | 2012-11-11 | Aisya, Michelle
| Function: Search (resume) |  | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27
|  | Design search function | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27 | Eileen, Tsorng
|  | Develop search | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27 | Eileen, Tsorng
|  | Unit Testing & Debugging | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27 | Eileen, Tsorng
| Final Debugging |  | 7 | 2012-11-17 | 2012-11-24 | 16 | 2012-11-10 | 2012-11-26
|  | Register & Login | 7 | 2012-11-17 | 2012-11-24 | 16 | 2012-11-10 | 2012-11-26 | Aisya
|  | Publishing (Article) | 7 | 2012-11-17 | 2012-11-24 | 16 | 2012-11-10 | 2012-11-26 | Michelle,Nisa,Aisya
|  | Displaying Homepage | 7 | 2012-11-17 | 2012-11-24 | 3 | 2012-11-23 | 2012-11-26 | Aisya
| Integration & System Testing |  | 0 | 2012-11-27 | 2012-11-27 | 0 |  |  | Eileen
| Deployment |  | 1 | 2012-11-28 | 2012-11-29 | 0 |  |  | Eileen
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23 | 2 | 2012-11-26 | 2012-11-28 | Michelle | All
Milestones
| User Test 2 |  | 1 | 2012-11-10 | 2012-11-11 | 7 | 2012-11-10 | 2012-11-17
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12 | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 0 | 2012-12-03 | 2012-12-03
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07

## 30 Nov 12
Task Name |  |  | Planned Duration | Planned Start | Planned Finish | Actual Duration | Actual Start | Actual Finish | Member-in charge | Resources Name | Schedule Metric | Comments | Schedule Metric
Iteration 0 |  |  | 11 | 2012-06-09 | 2012-06-20 | 11 | 2012-06-09 | 2012-06-20 |  |  | 1 |  | 1
| Project Specification Stage |  | 7 | 2012-06-09 | 2012-06-16 | 7 | 2012-06-09 | 2012-06-16 |  |  | 1 |  | 1
|  | Project Requirement Gathering | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Define Project Scope | 3 | 2012-06-09 | 2012-06-12 | 3 | 2012-06-09 | 2012-06-12 | All |  | 1 |  | 1
|  | Research on PHP framework | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Research on email & localization | 6 | 2012-06-10 | 2012-06-16 | 6 | 2012-06-10 | 2012-06-16 | All |  | 1 |  | 1
|  | Develop Workflow Diagram | 1 | 2012-06-11 | 2012-06-12 | 1 | 2012-06-11 | 2012-06-12 | Tsorng | Eileen | 1 |  | 1
| Project Management Planning |  | 3 | 2012-06-16 | 2012-06-19 | 3 | 2012-06-16 | 2012-06-19 |  |  | 1 |  | 1
|  | Project Roles & Responsibilities | 0 | 2012-06-17 | 2012-06-17 | 0 | 2012-06-17 | 2012-06-17 | All |  | 1 |  | 1
|  | Project Schedule | 1 | 2012-06-17 | 2012-06-18 | 1 | 2012-06-17 | 2012-06-18 | Michelle |  | 1 |  | 1
|  | Project Risks | 0 | 2012-06-16 | 2012-06-16 | 0 | 2012-06-16 | 2012-06-16 | Nisa |  | 1 |  | 1
| Develop Wiki Page Layout |  | 0 | 2012-06-19 | 2012-06-19 | 0 | 2012-06-19 | 2012-06-19 | All |  | 1 |  | 1
| Milestone | [9 empty] | 1 |  | 1
|  | FYP Proposal Submission | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 1 |  |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
| Review of Iteration 0 |  | 0 | 2012-06-20 | 2012-06-20 | 0 | 2012-06-20 | 2012-06-20 | All |  | 1 |  | 1
| Diagramming & Structuring Stage |  | 16 | 2012-06-20 | 2012-07-06 | 16 | 2012-06-20 | 2012-07-06 |  |  | 1 |  | 1
|  | Develop UI Design | 2 | 2012-06-20 | 2012-06-22 | 6 | 2012-06-20 | 2012-06-26 | Tsorng | Aisya, Eileen, Michelle | 3 | Postponed Sponsor meeting | 3
|  | Develop Use Case Diagram | 0 | 2012-06-26 | 2012-06-26 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 | Change of date for team meet-up | 1
|  | Revamp UI Design (after Sponsor meeting 2) | 9 | 2012-06-27 | 2012-07-06 | 9 | 2012-06-27 | 2012-07-06 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
|  | Develop System Architecture Diagram & Deployment Diagram | 0 | 2012-06-28 | 2012-06-28 | 0 | 2012-06-28 | 2012-06-28 | Nisa | Aisya, Michelle | 1 |  | 1
|  | Develop Application Architecture Diagram & Logical Diagram | 0 | 2012-07-01 | 2012-07-01 | 0 | 2012-07-01 | 2012-07-01 | Nisa | Aisya, Michelle | 1 |  | 1
[11 empty] | 1 |  | 1
Iteration 2 |  |  | 24 | 2012-07-07 | 2012-07-31 | 33 | 2012-07-07 | 2012-08-09 |  |  | 1.375 |  | 1.375
| Review of Iteration 1 |  | 0 | 2012-07-07 | 2012-07-07 | 0 | 2012-07-07 | 2012-07-07 | All |  | 1 |  | 1
|  | Revamp of UI Design (after Sponsor meeting 3) | 2 | 2012-07-07 | 2012-07-09 | 2 | 2012-07-07 | 2012-07-09 | Tsorng | Aisya, Eileen, Michelle | 1 |  | 1
| Function:Register & Login |  | 4 | 2012-07-08 | 2012-07-12 | 25 | 2012-07-14 | 2012-08-08 |  |  | 6.25 | Delayed due to unfamiliarity with Yii framework | 6.25
|  | Develop database architecture | 2 | 2012-07-08 | 2012-07-10 | 2 | 2012-08-06 | 2012-08-08 | Nisa | All | 1 |  | 1
|  | Design Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Postponed due to unavailability | 2
|  | Develop Registration & Login Function | 3 | 2012-07-08 | 2012-07-11 | 6 | 2012-07-31 | 2012-08-06 | Aisya, Michelle, Nisa |  | 2 | Finished the original on 6 Aug, but change request for facebook login | 2
|  | Develop master UI skeleton | 4 | 2012-07-08 | 2012-07-12 | 4 | 2012-07-14 | 2012-07-18 | Tsorng, Eileen |  | 1 |  | 1
|  | Unit Testing & Debugging | 0 | 2012-07-12 | 2012-07-12 | 2 | 2012-08-06 | 2012-08-08 | Aisya, Michelle, Nisa |  | 1 |  | 1
| Function: Project Proposal Approval & Project Management (partial) |  | 19 | 2012-07-12 | 2012-07-31 | 16 | 2012-07-24 | 2012-08-09 |  |  | 0.84211 |  | 0.84211
|  | Design view proposed project status page | 0 | 2012-07-12 | 2012-07-12 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 1 |  | 1
|  | Develop self-propose project function (incl approval from NGO & Sponsor) | 14 | 2012-07-12 | 2012-07-26 | 9 | 2012-07-24 | 2012-08-02 | Eileen, Tsorng |  | 0.64286 |  | 0.64286
|  | Develop Email Javascript plugin | 14 | 2012-07-12 | 2012-07-26 | 0 |  |  | Eileen, Tsorng |  | 0 |  | 0
|  | Unit Testing & Debugging | 1 | 2012-07-27 | 2012-07-28 | 1 | 2012-08-03 | 2012-08-04 | Eileen, Tsorng |  | 1 |  | 1
| Integration & System Testing |  | 3 | 2012-07-28 | 2012-07-31 | 2 | 2012-08-07 | 2012-08-09 | Eileen |  | 0.66667 |  | 0.66667
Iteration 3 |  |  | 19 | 2012-08-01 | 2012-08-20 | 11 | 2012-08-09 | 2012-08-20 |  |  | 0.57895 |  | 0.57895
| Review of Iteration 2 |  | 0 | 2012-08-01 | 2012-08-01 | 0 | 2012-08-09 | 2012-08-09 | All |  | 1 |  | 1
| Deployment |  | 11 | 2012-08-01 | 2012-08-12 | 3 | 2012-08-10 | 2012-08-13 | Eileen | Tsorng | 0.27273 |  | 0.27273
| Preparation of Acceptance Presentation |  | 7 | 2012-08-01 | 2012-08-08 | 4 | 2012-08-09 | 2012-08-13 | Michelle | Nisa | 0.57143 |  | 0.57143
| Milestones | [9 empty] | 1 |  | 1
| FYP Acceptance Presentation |  | 0 | 2012-08-14 | 2012-08-14 | 0 | 2012-08-14 | 2012-08-14 | All |  | 1 |  | 1
| FYP Registration |  | 0 | 2012-08-20 | 2012-08-20 | 0 | 2012-08-20 | 2012-08-20 | All |  | 1 |  | 1
Iteration 4 |  |  | 19 | 2012-08-21 | 2012-09-09 | 40 | 2012-08-21 | 2012-09-30 |  |  | 2.1053 |  | 2.1053
| Review of Iteration 3 |  | 0 | 2012-08-21 | 2012-08-21 | 0 | 2012-08-21 | 2012-08-21 | All |  |  |  | 1
| Function: Facebook Register & Login |  | 12 | 2012-08-21 | 2012-09-02 | - | 2012-08-21 | - | Aisya |  |  | Removed after re-scoping
|  | Develop Facebook Registration & Login | 2 | 2012-09-02 | 2012-09-04 | - | 2012-08-21 | - | Aisya
| Function: Register & Login |  | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 |  |  |  |  | 4.6667
|  | Edit registration accordingly to new UI (e.g include image upload) | 6 | 2012-09-01 | 2012-09-07 | 28 | 2012-09-02 | 2012-09-30 | Aisya |  |  |  | 4.6667
|  | Unit Testing & Debugging | 0 | 2012-09-07 | 2012-09-07 | 0 | 2012-09-30 | 2012-09-30 | Aisya |  |  |  | 1
| Function: Project Management (partial) |  | 14 | 2012-08-21 | 2012-09-04 | 23 | 2012-09-02 | 2012-09-25 |  |  |  | Extend of planned dates due to change of logic | 1.6429
|  | Design & Develop Manage volunteer function | 12 | 2012-08-21 | 2012-09-02 | 3 | 2012-09-11 | 2012-09-14 | Eileen, Tsorng |  |  |  | 0.25
|  | Develop sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Design sign up project function | 12 | 2012-08-21 | 2012-09-02 | - | - | - | Eileen, Tsorng |  |  | Function put on hold on 29 Aug due to the additional task of changing UI
|  | Change of UI for project management | 3 | 2012-09-02 | 2012-09-05 | 1 | 2012-09-02 | 2012-09-03 | Eileen, Tsorng |  |  |  | 0.33333
|  | Change of Workflow for project approval | 7 | 2012-09-02 | 2012-09-09 | 6 | 2012-09-04 | 2012-09-10 | Eileen, Tsorng |  |  |  | 0.85714
|  | Design & Develop Manage NGO function | 7 | 2012-09-09 | 2012-09-16 | 2 | 2012-09-15 | 2012-09-17 | Eileen, Tsorng |  |  |  | 0.28571
|  | Design & Develop Manage Sponsor function | 7 | 2012-09-09 | 2012-09-16 | 1 | 2012-09-18 | 2012-09-19 | Eileen, Tsorng |  |  |  | 0.14286
|  | Develop Manage Sponsor function | 0 |  |  | 0 | [6 empty] | 1
|  | Develop Project Volunteer and Project Signup Box in Project Page | 2 | 2012-09-14 | 2012-09-16 | 1 | 2012-09-22 | 2012-09-23 | Eileen, Tsorng |  |  |  | 0.5
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 1 | 2012-09-24 | 2012-09-25 | Eileen |  |  |  | 0.5
| Function: Publishing |  | 14 | 2012-08-21 | 2012-09-04 |  | 2012-09-04 | - |  |  |  | Extend of planned dates due to change of logic | 0
|  | Design publish post layout | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa | Aisya |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Develop publish post function | 12 | 2012-08-21 | 2012-09-02 | - | 2012-09-04 | - | Michelle, Nisa |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Change of code logic due to new UI | 4 | 2012-09-11 | 2012-09-15 | - | 2012-09-23 | - | Michelle |  |  | On hold due to incompletion (tried from 1 Oct - 5 Oct)
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | - | - | - |  |  |  | Postpone to next iteration due to incomplete of publish post
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | - | 2012-09-25 | - | Michelle, Nisa |  |  | Postpone to another iteration due to incomplete of publish post
| Function: Volunteer Profile Management |  | 10 | 2012-08-21 | 2012-08-31 | [6 empty] | Postpone to next iteration | 0
|  | Develop profile management function | 10 | 2012-08-21 | 2012-08-31 | - | - | -
|  | Unit Testing & Debugging | 2 | 2012-08-29 | 2012-08-31 | - | - | -
| Integration & System Testing |  | 2 | 2012-09-04 | 2012-09-06 | 2 | 2012-09-28 | 2012-09-30 | Eileen |  |  |  | 1
| Deployment |  | 3 | 2012-09-06 | 2012-09-09 | 2 | 2012-09-28 | 2012-09-30 | Eileen | Tsorng |  |  | 0.66667
| User Test 1 Preparation (postponed) |  | 5 | 2012-09-18 | 2012-09-23 | - | 2012-09-28 | - | Aisya |  |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
| Mid-Term Presentation Preparation (postponed) |  | 5 | 2012-09-24 | 2012-09-29 | - | 2012-09-30 | - | Michelle | Nisa |  | on Hold between 1 Oct 12 - 8 Oct 12 because of postpone of mid-term presentation
Iteration 5 |  |  | 25 | 2012-09-10 | 2012-10-05 | 9 | 2012-10-01 | 2012-10-10 |  |  |  |  | 0.36
| Review of Iteration 4 |  | 0 | 2012-09-10 | 2012-09-10 | 0 | 2012-10-01 | 2012-10-01 | All |  |  |  | 1
| Function: Profile Management (partial) |  | 8 | 2012-09-10 | 2012-09-18 | 5 | 2012-10-02 | 2012-10-07 |  |  |  |  | 0.625
|  | Design Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 1 | 2012-10-02 | 2012-10-03 | Eileen |  |  |  | 0.14286
|  | Develop Project Profile management function page | 7 | 2012-09-10 | 2012-09-17 | 2 | 2012-10-03 | 2012-10-05 | Eileen |  |  |  | 0.28571
|  | Design Volunteer Profile management function page | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-02 | - | Tsorng |  |  | On hold due to incompletion of certain functionalities
|  | Develop Volunteer Profile management function | 7 | 2012-09-10 | 2012-09-17 | - | 2012-10-03 | - | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | 0 | 2012-10-07 | 2012-10-07 | Eileen, Tsorng |  |  |  | 1
| Function: Publishing (Article) |  | 8 | 2012-09-10 | 2012-09-18 | 6 | 2012-10-02 | 2012-10-08 |  |  |  |  | 0.75
|  | Design publish article layout | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Develop publish article function | 7 | 2012-09-10 | 2012-09-17 | 6 | 2012-10-02 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0.85714
|  | Unit Testing & Debugging | 1 | 2012-09-17 | 2012-09-18 | 0 | 2012-10-08 | 2012-10-08 | Nisa, Aisya,Michelle |  |  |  | 0
| Function: Project Management |  | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 |  |  |  |  | 0.16667
|  | Design sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Develop sign up function | 12 | 2012-08-21 | 2012-09-02 | 2 | 2012-10-05 | 2012-10-07 | Eileen |  |  |  | 0.16667
|  | Unit Testing & Debugging | 2 | 2012-09-02 | 2012-09-04 | 0 | 2012-10-07 | 2012-10-07 | Eileen |  |  |  | 0
| Function: Search |  | 10 | 2012-09-10 | 2012-09-20 | [6 empty] | Adjusted to next iteration due to re-scope | 0
|  | Design search function | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Develop search based on project name | 7 | 2012-09-10 | 2012-09-17 | - | - | -
|  | Unit Testing & Debugging | 0 | 2012-09-18 | 2012-09-18 | - | - | - |  |  |  |  | 1
| Integration & System Testing |  | 3 | 2012-09-18 | 2012-09-21 | 0 | 2012-10-08 | 2012-10-08 | Eileen, Tsorng |  |  |  | 0
| Deployment |  | 3 | 2012-09-21 | 2012-09-24 | 1 | 2012-10-08 | 2012-10-09 | Eileen |  |  |  | 0.33333
| User Test 1 Preparation |  | 5 | 2012-09-18 | 2012-09-23 | 0 | 2012-10-08 | 2012-10-08 | Aisya | All |  | Resumed task | 0
| Mid-Term Presentation Preparation |  | 5 | 2012-09-24 | 2012-09-29 | 1 | 2012-10-08 | 2012-10-09 | Michelle | All |  | Resumed task | 0.2
| Milestones | [11 empty] | 1
| User Test 1 |  | 0 | 2012-10-01 | 2012-10-01 | 0 | 2012-10-09 | 2012-10-09 | All |  |  |  | 1
| FYP Mid-term Presentation |  | 0 | 2012-10-05 | 2012-10-05 | 0 | 2012-10-10 | 2012-10-10 | All |  |  |  | 1
Iteration 6 |  |  | 30 | 2012-10-06 | 2012-11-05 | 19 | 2012-10-21 | 2012-11-09 |  |  |  |  | 0.63333
| Review of Iteration 5 |  | 1 | 2012-10-06 | 2012-10-07
| Function: Search (incomplete) |  | 18 | 2012-10-08 | 2012-10-26 |  | 2012-11-01 | 2012-11-07 |  |  |  | Adjusted to next iteration, unsuccessful attempt from 1 nov - 7 Nov
|  | Design search function | 16 | 2012-10-08 | 2012-10-24 |  | 2012-11-01 | 2012-11-07 | Nisa
|  | Develop search | 16 | 2012-10-08 | 2012-10-24 |  | 2012-11-01 | 2012-11-07 | Nisa
|  | Unit Testing & Debugging | 1 | 2012-10-25 | 2012-10-26
| Function: Intelligence |  | 7 | 2012-10-08 | 2012-10-15 | [6 empty] | Removed from scope
|  | Develop Past User Selection Intelligence Function | 6 | 2012-10-08 | 2012-10-14
|  | Unit Testing & Debugging | 1 | 2012-10-14 | 2012-10-15
| Function: Publishing (Post) |  | 17 | 2012-10-15 | 2012-11-01 | [6 empty] | Removed from scope
|  | Design publish post layout (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Develop publish post function (resume) | 17 | 2012-10-15 | 2012-11-01
|  | Unit Testing & Debugging | 1 | 2012-11-01 | 2012-11-02
| Function: Profile Management |  | 20 | 2012-10-15 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28
|  | Volunteer Profile: Edit volunteer experience | 7 | 2012-10-15 | 2012-10-22 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Volunteer Profile: Link to volunteer's article | 7 | 2012-10-15 | 2012-10-22 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Volunteer Profile: Link to volunteer's post | 2 | 2012-11-02 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
|  | Unit Testing & Debugging | 0 | 2012-11-04 | 2012-11-04 | 7 | 2012-10-21 | 2012-10-28 | Tsorng
| Debugging after UT 1 |  | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07
|  | Register & Login | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Aisya
|  | Project Management | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Eileen, Tsorng
|  | Profile Management | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Eileen, Tsorng
|  | Publishing (Article) | 23 | 2012-10-15 | 2012-11-07 | 17 | 2012-10-21 | 2012-11-07 | Michelle | Aisya, Nisa
| Integration & System Testing |  | 3 | 2012-11-01 | 2012-11-04 | 1 | 2012-11-08 | 2012-11-09 | Eileen, Tsorng
| Deployment |  | 1 | 2012-11-04 | 2012-11-05 | 0 | 2012-11-09 | 2012-11-09 | Eileen
Iteration 7 |  |  | 31 | 2012-11-06 | 2012-12-07 | 28 | 2012-11-09 | 2012-12-07
| Preparation of User Test 2 |  | 0 | 2012-11-06 | 2012-11-06 | 0 | 2012-11-09 | 2012-11-09 | Aisya, Michelle
| Preparation of FYP Poster |  | 1 | 2012-11-10 | 2012-11-11 | 2 | 2012-11-09 | 2012-11-11 | Nisa
| Preparation of FYP Video |  | 1 | 2012-11-10 | 2012-11-11 | 0 | 2012-11-11 | 2012-11-11 | Aisya, Michelle
| Function: Search (resume) |  | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27
|  | Design search function | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27 | Eileen, Tsorng
|  | Develop search | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27 | Eileen, Tsorng
|  | Unit Testing & Debugging | 12 | 2012-11-17 | 2012-11-29 | 10 | 2012-11-17 | 2012-11-27 | Eileen, Tsorng
| Final Debugging |  | 7 | 2012-11-17 | 2012-11-24 | 16 | 2012-11-10 | 2012-11-26
|  | Register & Login | 7 | 2012-11-17 | 2012-11-24 | 16 | 2012-11-10 | 2012-11-26 | Aisya
|  | Publishing (Article) | 7 | 2012-11-17 | 2012-11-24 | 16 | 2012-11-10 | 2012-11-26 | Michelle,Nisa,Aisya
|  | Displaying Homepage | 7 | 2012-11-17 | 2012-11-24 | 3 | 2012-11-23 | 2012-11-26 | Aisya
| Integration & System Testing |  | 0 | 2012-11-27 | 2012-11-27 | 3 | 2012-11-27 | 2012-11-30 | Eileen
| Deployment |  | 1 | 2012-11-28 | 2012-11-29 | 0 | 2012-11-30 | 2012-11-30 | Eileen
| Preparation of Final Presentation |  | 10 | 2012-11-13 | 2012-11-23 | 2 | 2012-11-26 | 2012-11-28 | Michelle | All
Milestones
| User Test 2 |  | 1 | 2012-11-10 | 2012-11-11 | 9 | 2012-11-10 | 2012-11-19
| FYP Poster Submission |  | 0 | 2012-11-12 | 2012-11-12 | 0 | 2012-11-12 | 2012-11-12
| FYP Final Presentation |  | 0 | 2012-12-03 | 2012-12-03 | 0 | 2012-12-03 | 2012-12-03
| FYP Poster Day |  | 0 | 2012-12-07 | 2012-12-07 | 0 | 2012-12-07 | 2012-12-07