## Sheet1
Project Schedule
Iteration | Task | Planned Duration (Days) | Planned Start | Planned Finish | Planned Man Hours | Actual Duration (Days) | Actual Start | Actual Finish | Actual Man Hours | Schedule Metrics | Man Hours Metric | Resources
Inception Phase
1 | Business Modelling | 20 days | 7th Oct 2012 | 26th Oct 2012 | 70.5 | 20 | 7th Oct 2012 | 26th Oct 2012 | 72 | Completed
Define Project Scope
| Finalize on Team Roles & Responsibilities | 2 | 7th Oct 2012 | 8th Oct 2012 | 1.5 | 2 | 7th Oct 2012 | 8th Oct 2012 | 2 | 0 | 0.5 | All
| Work on Project Proposal | 10 | 7th Oct 2012 | 16th Oct 2012 | 12 | 10 | 7th Oct 2012 | 16th Oct 2012 | 12 | 0 | 0 | All
| Create Project Schedule | 10 | 7th Oct 2012 | 16th Oct 2012 | 5 | 10 | 7th Oct 2012 | 16th Oct 2012 | 5 | 0 | 0 | Jian Wei
| Create Team Logo | 6 | 7th Oct 2012 | 12th Oct 2012 | 2 | 6 | 7th Oct 2012 | 12th Oct 2012 | 2 | 0 | 0 | Edward
| Create & update Team's Wiki Skeleton | 10 | 7th Oct 2012 | 16th Oct 2012 | 2 | 10 | 7th Oct 2012 | 16th Oct 2012 | 2 | 0 | 0 | Edward, Jian Wei
| Do Storyboard for Project Acceptance | 10 | 7th Oct 2012 | 16th Oct 2012 | 4 | 10 | 7th Oct 2012 | 16th Oct 2012 | 4 | 0 | 0 | Brian, Jessie
Diagrams
| Use-case diagram | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0 | Jessie
| Domain diagram | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0 | Jessie
| Class diagrams | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0 | Jessie
| System diagram | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0 | Jessie
| System sequence diagram | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0 | Jessie
| Workflow diagram | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0 | Brian
| Schedule Metrics | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0.5 | Jian Wei
| Bugs Metrics | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1.5 | 0 | 0.5 | Jian Wei
Define Risk
| Resource Risk | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Technical Risk | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Project Continuity Risk | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 4 | 16th Oct 2012 | 19th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Gather website information for domains | 4 | 16th Oct 2012 | 19th Oct 2012 | 4 | 4 | 16th Oct 2012 | 19th Oct 2012 | 4 | 0 | 0 | Kuang Quan, Wei Hao
| Wiki Update | 1 | 19th Oct 2012 | 19th Oct 2012 | 1 | 1 | 19th Oct 2012 | 19th Oct 2012 | 1 | 0 | 0 | Jian Wei
Identify Architecture
| Objective-C | 8 | 19th Oct 2012 | 26th Oct 2012 | 4 | 8 | 19th Oct 2012 | 26th Oct 2012 | 4 | 0 | 0 | Edward, Jessie
| Facebook API | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Brian
| Google Maps API | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Edward
| Server Architecture | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Wei Hao
| Ipad/Mobile User Interface Design | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Wei Hao
| Mongo Database | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Brian
| Database Indexing | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Brian
| Define data to be parsed from XML | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Brian
| Apple Design Guidelines | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Edward
| X-Codes | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Jessie
| UI Design | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 8 | 19th Oct 2012 | 26th Oct 2012 | 2 | 0 | 0 | Edward, Jessie
| Wiki Update | 4 | 23th Oct 2012 | 26th Oct 2012 | 1 | 4 | 23th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jian Wei
Milestone 1: 26th Oct 2012: Submission of Project Proposal
Elaboration Phase
2 | Requirements Gathering | 1 day | 26th Oct 2012 | 26th Oct 2012 | 12.5 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | Completed
Track Progresss Summary
| Progress Review | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Wiki Update | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Refine Use-case diagram | 1 | 26th Oct 2012 | 26th Oct 2012 | 1.5 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | -0.5 | Jessie, KQ
| Refine Domain diagram | 1 | 26th Oct 2012 | 26th Oct 2012 | 1.5 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | -0.5 | Jessie, KQ
| Refine Class diagrams | 1 | 26th Oct 2012 | 26th Oct 2012 | 1.5 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | -0.5 | Jessie, KQ
| Refine System diagram | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jessie
| Refine System sequence diagram | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jessie
| Refine Workflow diagram | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jessie
Update Metrics
| Update Schedule Metrics | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Update Bugs Metrics | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jian Wei
| Update Technical Risk | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 1 | 26th Oct 2012 | 26th Oct 2012 | 1 | 0 | 0 | Jian Wei
3 | Analysis & Design | 11 days | 26th Oct 2012 | 5th Nov 2012 | 64 | 11 days | 26th Oct 2012 | 5th Nov 2012 | 65 | Completed
Understand Requirements
| Research on handling different Ipads' screen sizes | 3 | 26th Oct 2012 | 29th Oct 2012 | 2 | 3 | 26th Oct 2012 | 29th Oct 2012 | 2 | 0 | 0 | Edward
| Research on utilizing 11 available touches on the iPads | 3 | 26th Oct 2012 | 29th Oct 2012 | 2 | 3 | 26th Oct 2012 | 29th Oct 2012 | 2 | 0 | 0 | Jessie
| Research on how to use specific iPad with UISplitview interface element | 3 | 26th Oct 2012 | 29th Oct 2012 | 2 | 3 | 26th Oct 2012 | 29th Oct 2012 | 2 | 0 | 0 | Edward
Constructing Components
| Propose XSD schema for Dining | 4 | 26th Oct 2012 | 29th Oct 2012 | 4 | 4 | 26th Oct 2012 | 29th Oct 2012 | 4 | 0 | 0 | Brian, KQ
| Rearrage dining data in proper format using DOM | 4 | 26th Oct 2012 | 29th Oct 2012 | 4 | 4 | 26th Oct 2012 | 29th Oct 2012 | 6 | 0 | 2 | Brian, Wei Hao
| Write out stand alone java codes to parse data from XML format using DOM | 4 | 28th Oct 2012 | 29th Oct 2012 | 3 | 4 | 28th Oct 2012 | 29th Oct 2012 | 4 | 0 | 1 | Brian
Database Design
| Setting up MySQL Database | 4 | 26th Oct 2012 | 29th Oct 2012 | 3 | 4 | 26th Oct 2012 | 29th Oct 2012 | 3 | 0 | 0 | Brian
| Plugin Values | 4 | 26th Oct 2012 | 29th Oct 2012 | 4 | 4 | 26th Oct 2012 | 29th Oct 2012 | 4 | 0 | 0 | Brian
| Opening Ports | 4 | 26th Oct 2012 | 29th Oct 2012 | 2 | 4 | 26th Oct 2012 | 29th Oct 2012 | 3 | 0 | 1 | Brian
| Work on indexing the data | 4 | 26th Oct 2012 | 29th Oct 2012 | 2 | 4 | 26th Oct 2012 | 29th Oct 2012 | 3 | 0 | 1 | Brian
User interface Design
| Provide Dining search services using java restful webservice | 4 | 26th Oct 2012 | 29th Oct 2012 | 5 | 4 | 26th Oct 2012 | 29th Oct 2012 | 4 | 0 | -1 | Wei Hao
| Improve UI Design | 4 | 26th Oct 2012 | 29th Oct 2012 | 5 | 4 | 26th Oct 2012 | 29th Oct 2012 | 5 | 0 | 0 | Edward
| Implement design on bread crumbs | 4 | 26th Oct 2012 | 29th Oct 2012 | 5 | 4 | 26th Oct 2012 | 29th Oct 2012 | 5 | 0 | 0 | Edward
| Login/Logout | 4 | 26th Oct 2012 | 29th Oct 2012 | 5 | 4 | 26th Oct 2012 | 29th Oct 2012 | 3 | 0 | -2 | Edward
Integration
| Testing and Integrating | 4 | 29th Oct 2012 | 1st Nov 2012 | 4 | 4 | 29th Oct 2012 | 1st Nov 2012 | 3 | 0 | -1 | Kuang Quan
Preparation for Acceptance
| Prepare storyboard & rehearse presentation slides | 3 | 1st Nov 2012 | 3th Nov 2012 | 12 | 3 | 1st Nov 2012 | 3th Nov 2012 | 12 | 0 | 0 | Everyone
| Buffer | 2 | 4th Nov 2012 | 5th Nov 2012
Milestone 2: 5th Nov 2012: Acceptance Presentation
Construction Phase
4 | Implementation & Testing for Categories: Nearby | 32 days | 5th Nov 2012 | 16th Dec 2012 | 121 | 32 days | 5th Nov 2012 | 16th Dec 2012 | 120 | Completed
Track Progresss Summary
| Progress Review | 3 | 5th Nov 2012 | 7th Nov 2012 | 5 | 3 | 5th Nov 2012 | 7th Nov 2012 | 5 | 0 | 0 | Jian Wei
| Wiki Update | 5 | 5th Nov 2012 | 9th Nov 2012 | 5 | 5 | 5th Nov 2012 | 9th Nov 2012 | 5 | 0 | 0 | Jian Wei
| Discussion with supervisor / advisors on acceptance feedback | 5 | 12th Nov 2012 | 16th Nov 2012 | 4 | 5 | 12th Nov 2012 | 16th Nov 2012 | 3 | 0 | -1 | Everyone
Requirements Gathering
| Storyboard with sponsor (Meeting) | 1 | 19th Nov 2012 | 19th Nov 2012 | 2 | 1 | 19th Nov 2012 | 19th Nov 2012 | 2 | 0 | 0 | Everyone
Study Week + Exam Period (19thNov12-10thDec12)
Test Discipline
| Develop Test Cases | 4 | 10th Dec2012 | 13rd Dec 2012 | 4 | 4 | 10th Dec2012 | 13rd Dec 2012 | 4 | 0 | 0 | Kuang Quan
| Develop Test Plan | 4 | 10th Dec2012 | 13rd Dec 2012 | 4 | 4 | 10th Dec2012 | 13rd Dec 2012 | 4 | 0 | 0 | Kuang Quan
Building Database
| 1st phase - Data Normalization | 4 | 10th Dec2012 | 13rd Dec 2012 | 15 | 6 | 10th Dec2012 | 15th Dec 2012 | 15 | 2 | 0 | Brian
| 2nd phase - Data validation | 4 | 10th Dec2012 | 13rd Dec 2012 | 15 | 6 | 10th Dec2012 | 15th Dec 2012 | 15 | 2 | 0 | Brian
Implementing Components
| Home screen completed | 4 | 10th Dec2012 | 13rd Dec 2012 | 10 | 4 | 10th Dec2012 | 13rd Dec 2012 | 10 | 0 | 0 | Edward
| Provide "dining" search services using java restful webservice | 4 | 10th Dec2012 | 13rd Dec 2012 | 8 | 4 | 10th Dec2012 | 13rd Dec 2012 | 8 | 0 | 0 | Wei Hao / Jessie
| Provide "places of interest" search services using java restful webservice | 4 | 10th Dec2012 | 13rd Dec 2012 | 8 | 4 | 10th Dec2012 | 13rd Dec 2012 | 8 | 0 | 0 | Wei Hao / Jessie
| Provide "retail" search services using java restful webservice | 4 | 10th Dec2012 | 13rd Dec 2012 | 8 | 4 | 10th Dec2012 | 13rd Dec 2012 | 8 | 0 | 0 | Wei Hao / Jessie
| Installing Java, Apache Tomcat on Ubuntu | 3 | 10th Dec2012 | 12nd Dec 2012 | 8 | 3 | 10th Dec2012 | 12nd Dec 2012 | 8 | 0 | 0 | Wei Hao
| MongoDB, LAMP, RockMongo installed on test server | 1 | 12th Dec 2012 | 12th Dec 2012 | 8 | 1 | 12th Dec 2012 | 12th Dec 2012 | 8 | 0 | 0 | Wei Hao
Deployment
| Deploy to iPad for testing | 1 | 13rd Dec 2012 | 13rd Dec 2012 | 5 | 1 | 13rd Dec 2012 | 13rd Dec 2012 | 5 | 0 | 0 | Wei Hao
Testing & Debugging
| Testing | 2 | 13rd Dec 2012 | 14th Dec 2012 | 6 | 2 | 13rd Dec 2012 | 14th Dec 2012 | 6 | 0 | 0 | Kuang Quan ,Wei Hao
| Debugging | 2 | 13rd Dec 2012 | 14th Dec 2012 | 6 | 2 | 13rd Dec 2012 | 14th Dec 2012 | 6 | 0 | 0 | Kuang Quan ,Wei Hao
| Buffer | 2 | 15th Dec 2012 | 16th Dec 2012
5 | Implementation & Testing for Categories: Foodie | 7 days | 17th Dec 2012 | 23rd Dec 2012 | 82 | 7 days | 17th Dec 2012 | 23rd Dec 2012 | 86 | Completed
Track Progresss Summary
| Progress Review | 2 | 17th Dec 2012 | 18th Dec 2012 | 2 | 2 | 17th Dec 2012 | 18th Dec 2012 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 17th Dec 2012 | 18th Dec 2012 | 2 | 2 | 17th Dec 2012 | 18th Dec 2012 | 2 | 0 | 0 | Jian Wei
Test Discipline
| Develop Test Cases | 4 | 17th Dec 2012 | 20th Dec 2012 | 2 | 4 | 17th Dec 2012 | 20th Dec 2012 | 2 | 0 | 0 | Kuang Quan
| Develop Test Plan | 4 | 17th Dec 2012 | 20th Dec 2012 | 2 | 4 | 17th Dec 2012 | 20th Dec 2012 | 2 | 0 | 0 | Kuang Quan
Building Database
| 1st phase - Normalization | 4 | 17th Dec 2012 | 20th Dec 2012 | 5 | 4 | 17th Dec 2012 | 20th Dec 2012 | 6 | 0 | 1 | Brian
| 2nd phase - Data validation | 4 | 17th Dec 2012 | 20th Dec 2012 | 5 | 4 | 17th Dec 2012 | 20th Dec 2012 | 5 | 0 | 0 | Brian
Implementing Components
| Basic Search functionality on iPad completed (for restaurants) | 4 | 17th Dec 2012 | 20th Dec 2012 | 10 | 4 | 17th Dec 2012 | 20th Dec 2012 | 10 | 0 | 0 | Edward
| Provide "dining" search services using java restful webservice | 4 | 17th Dec 2012 | 20th Dec 2012 | 4 | 4 | 17th Dec 2012 | 20th Dec 2012 | 5 | 0 | 1 | Wei Hao / Jessie
| Provide "places of interest" search services using java restful webservice | 4 | 17th Dec 2012 | 20th Dec 2012 | 4 | 4 | 17th Dec 2012 | 20th Dec 2012 | 5 | 0 | 1 | Wei Hao / Jessie
| Provide "retail" search services using java restful webservice | 4 | 17th Dec 2012 | 20th Dec 2012 | 4 | 4 | 17th Dec 2012 | 20th Dec 2012 | 5 | 0 | 1 | Wei Hao / Jessie
| Code webservice for the retrival of resturant data from database | 2 | 17th Dec 2012 | 18th Dec 2012 | 7 | 2 | 17th Dec 2012 | 18th Dec 2012 | 7 | 0 | 0 | Wei Hao
| Updates pushed to production server | 1 | 18th Dec 2012 | 18th Dec 2012 | 10 | 1 | 18th Dec 2012 | 18th Dec 2012 | 10 | 0 | 0 | Wei Hao
Deployment
| Deploy to iPad for testing | 1 | 20th Dec 2012 | 20th Dec 2012 | 5 | 1 | 20th Dec 2012 | 20th Dec 2012 | 5 | 0 | 0 | Edward
Requirements Gathering
| Storyboard with sponsor | 1 | 21st Dec 2012 | 21st Dec 2012 | 12 | 1 | 21st Dec 2012 | 21st Dec 2012 | 12 | 0 | 0 | Everyone
Testing & Debugging
| Testing | 2 | 20th Dec 2012 | 21st Dec 2012 | 4 | 2 | 20th Dec 2012 | 21st Dec 2012 | 4 | 0 | 0 | Kuang Quan ,Wei Hao
| Debugging | 2 | 20th Dec 2012 | 21st Dec 2012 | 4 | 2 | 20th Dec 2012 | 21st Dec 2012 | 4 | 0 | 0 | Kuang Quan ,Wei Hao
| Buffer | 2 | 22nd Dec 2012 | 23rd Dec 2012
6 | Facebook, Google Integration & Google Map (Part 1) | 8 Days | 24th Dec 2012 | 30th Dec 2012 | 43 | 8 Days | 24th Dec 2012 | 30th Dec 2012 | 43.75 | Completed
Track Progresss Summary
| Progress Review | 2 | 24th Dec 2012 | 26th Dec 2012 | 2 | 2 | 24th Dec 2012 | 26th Dec 2012 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 24th Dec 2012 | 26th Dec 2012 | 2 | 2 | 24th Dec 2012 | 26th Dec 2012 | 2 | 0 | 0 | Jian Wei
Test Discipline
| Develop Test Cases | 4 | 24th Dec 2012 | 28th Dec 2012 | 2 | 4 | 24th Dec 2012 | 28th Dec 2012 | 2 | 0 | 0 | Kuang Quan
| Develop Test Plan | 4 | 24th Dec 2012 | 28th Dec 2012 | 2 | 4 | 24th Dec 2012 | 28th Dec 2012 | 2 | 0 | 0 | Kuang Quan
Building Database
| 1st phase - Normalization | 4 | 24th Dec 2012 | 28th Dec 2012 | 5 | 4 | 24th Dec 2012 | 28th Dec 2012 | 5 | 0 | 0 | Brian
| 2nd phase - Data validation | 4 | 24th Dec 2012 | 28th Dec 2012 | 5 | 4 | 24th Dec 2012 | 28th Dec 2012 | 5 | 0 | 0 | Brian
Implementing Components
| Installing LUCENE SOLR on Tomcat | 2 | 24th Dec 2012 | 28th Dec 2012 | 5 | 2 | 24th Dec 2012 | 28th Dec 2012 | 5 | 0 | 0 | Wei Hao / Jessie
| Modify appearance of navigation bar and add cusom tab bar to views | 2 | 27th Dec 2012 | 28th Dec 2012 | 9 | 2 | 27th Dec 2012 | 28th Dec 2012 | 9.75 | 0 | 0.75 | Edward
| Installing Solr-Mongo connector on test server | 2 | 28th Dec 2012 | 29th Dec 2012 | 5 | 2 | 28th Dec 2012 | 29th Dec 2012 | 5 | 0 | 0 | Wei Hao
| Updates pushed to production server | 1 | 29th Dec 2012 | 29th Dec 2012 | 6 | 1 | 29th Dec 2012 | 29th Dec 2012 | 6 | 0 | 0 | Wei Hao
| Buffer | 1 | 30th Dec 2012 | 30th Dec 2012
7 | Facebook, Google Integration & Google Map (Part 2) | 7 days | 31st Dec 2013 | 6th Jan 2013 | 65.5 | 7 days | 31st Dec 2013 | 6th Jan 2013 | 64.35 | Completed
Track Progresss Summary
| Progress Review | 2 | 31st Dec 2012 | 1st Jan 2013 | 2 | 2 | 31st Dec 2012 | 1st Jan 2013 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 31st Dec 2012 | 1st Jan 2013 | 2 | 2 | 31st Dec 2012 | 1st Jan 2013 | 2 | 0 | 0 | Jian Wei
Test Discipline
| Develop Test Cases | 4 | 31st Dec 2012 | 4th Jan 2013 | 2 | 4 | 31st Dec 2012 | 4th Jan 2013 | 2 | 0 | 0 | Kuang Quan
| Develop Test Plan | 4 | 31st Dec 2012 | 4th Jan 2013 | 2 | 4 | 31st Dec 2012 | 4th Jan 2013 | 2 | 0 | 0 | Kuang Quan
Building Database
| 1st phase - Normalization | 4 | 31st Dec 2012 | 4th Jan 2013 | 5 | 4 | 31st Dec 2012 | 4th Jan 2013 | 5 | 0 | 0 | Brian
| 2nd phase - Data validation | 4 | 31st Dec 2012 | 4th Jan 2013 | 5 | 4 | 31st Dec 2012 | 4th Jan 2013 | 5 | 0 | 0 | Brian
Implementing Components
| ElasticSearch installed on test server | 1 | 4th Jan 2013 | 4th Jan 2013 | 7 | 1 | 4th Jan 2013 | 4th Jan 2013 | 7 | 0 | 0 | Wei Hao
| Installing MONGO-LUCENE connector on Ubantu | 1 | 4th Jan 2013 | 5th Jan 2013 | 7 | 1 | 4th Jan 2013 | 5th Jan 2013 | 6.3 | 0 | -0.7 | Edward
| ElasticSearch-Mongo connector installed on test server | 2 | 5th Jan 2013 | 6th Jan 2013 | 5 | 2 | 5th Jan 2013 | 6th Jan 2013 | 5 | 0 | 0 | Wei Hao
| Location detail page layout completed | 1 | 4th Jan 2013 | 5th Jan 2013 | 7 | 1 | 4th Jan 2013 | 5th Jan 2013 | 6.3 | 0 | -0.7 | Edward
| Installing MONGO-LUCENE connector on Ubantu | 1 | 5th Jan 2013 | 5th Jan 2013 | 6 | 1 | 5th Jan 2013 | 5th Jan 2013 | 6.5 | 0 | 0.5 | Wei Hao
| Improve search logic and inteerface workflow | 1 | 6th Jan 2013 | 6th Jan 2013 | 1.5 | 1 | 6th Jan 2013 | 6th Jan 2013 | 1.25 | 0 | -0.25 | Edward
| Updates pushed to production server | 1 | 6th Jan 2013 | 6th Jan 2013 | 9 | 1 | 6th Jan 2013 | 6th Jan 2013 | 9 | 0 | 0 | Wei Hao
Deployment
| Deploy to iPad for testing | 1 | 4th Jan 2013 | 4th Jan 2013 | 5 | 1 | 4th Jan 2013 | 4th Jan 2013 | 5 | 0 | 0 | Edward
| Buffer | 1 | 6th Jan 2013 | 6th Jan 2013
Milestone 3: 7th Jan 2013: Registration of FYP
8 | Facebook, Google Integration & Google Map (Part 3) | 8 days | 7th Jan 2013 | 13th Jan 2013 | 75.5 | 8 days | 7th Jan 2013 | 13th Jan 2013 | 74.83 | Completed
Track Progresss Summary
| Progress Review | 2 | 7th Jan 2013 | 8th Jan 2013 | 2 | 2 | 7th Jan 2013 | 8th Jan 2013 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 7th Jan 2013 | 8th Jan 2013 | 2 | 2 | 7th Jan 2013 | 8th Jan 2013 | 2 | 0 | 0 | Jian Wei
Test Discipline
| Develop Test Cases | 4 | 7th Jan 2013 | 10th Jan 2013 | 2 | 4 | 7th Jan 2013 | 10th Jan 2013 | 2 | 0 | 0 | Kuang Quan
| Develop Test Plan | 4 | 7th Jan 2013 | 10th Jan 2013 | 2 | 4 | 7th Jan 2013 | 10th Jan 2013 | 2 | 0 | 0 | Kuang Quan
Building Database
| 1st phase - Normalization | 4 | 7th Jan 2013 | 10th Jan 2013 | 6 | 4 | 7th Jan 2013 | 10th Jan 2013 | 6 | 0 | 0 | Brian
| 2nd phase - Data validation | 4 | 7th Jan 2013 | 10th Jan 2013 | 6 | 4 | 7th Jan 2013 | 10th Jan 2013 | 6 | 0 | 0 | Brian
Implementing Components
| Change filter buttons and complete search filters | 1 | 7th Jan 2013 | 7th Jan 2013 | 1.5 | 1 | 7th Jan 2013 | 7th Jan 2013 | 1.33 | 0 | -0.17 | Edward
| Favourites list completed | 2 | 7th Jan 2013 | 9th Jan 2013 | 9 | 2 | 7th Jan 2013 | 9th Jan 2013 | 8.25 | 0 | -0.75 | Edward
| API for geolocation search completed | 1 | 7th Jan 2013 | 7th Jan 2013 | 7 | 1 | 7th Jan 2013 | 7th Jan 2013 | 7 | 0 | 0 | Wei Hao
| Improve rebuilding of databases via API | 1 | 9th Jan 2013 | 9th Jan 2013 | 10 | 1 | 9th Jan 2013 | 9th Jan 2013 | 10 | 0 | 0 | Wei Hao
| Retrieval of GPS coordinate of device completed | 4 | 10th Jan 2013 | 13th Jan 2013 | 9 | 4 | 10th Jan 2013 | 13th Jan 2013 | 9.25 | 0 | 0.25 | Edward
| Integrate full restaurant datasets into database | 1 | 10th Jan 2013 | 10th Jan 2013 | 6 | 1 | 10th Jan 2013 | 10th Jan 2013 | 6 | 0 | 0 | Wei Hao
Deployment
| Deploy to iPad for testing | 1 | 10th Jan 2013 | 10th Jan 2013 | 5 | 1 | 10th Jan 2013 | 10th Jan 2013 | 5 | 0 | 0 | Wei Hao
Testing & Debugging
| Testing | 2 | 10th Jan 2013 | 11th Jan 2013 | 4 | 2 | 10th Jan 2013 | 11th Jan 2013 | 4 | 0 | 0 | Kuang Quan ,Wei Hao
| Debugging | 2 | 10th Jan 2013 | 11th Jan 2013 | 4 | 2 | 10th Jan 2013 | 11th Jan 2013 | 4 | 0 | 0 | Kuang Quan ,Wei Hao
| Buffer | 2 | 12th Jan 2013 | 13th Jan 2013
9 | Implementation & Testing for Categories: Arty Farty, Local Culture, Family, Adventure | 38 days | 14st Jan 2013 | 20th Feb 2013 | 262 | 38 days | 14st Jan 2013 | 20th Feb 2013 | 265 | Completed
Track Progresss Summary
| Progress Review | 2 | 14th Jan 2013 | 15th Jan 2013 | 2 | 2 | 14th Jan 2013 | 15th Jan 2013 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 14th Jan 2013 | 15th Jan 2013 | 2 | 2 | 14th Jan 2013 | 15th Jan 2013 | 2 | 0 | 0 | Jian Wei
Test Discipline
| Develop Test Cases | 4 | 14th Jan 2013 | 17th Jan 2013 | 2 | 4 | 14th Jan 2013 | 17th Jan 2013 | 2 | 0 | 0 | Kuang Quan
| Develop Test Plan | 4 | 14th Jan 2013 | 17th Jan 2013 | 2 | 4 | 14th Jan 2013 | 17th Jan 2013 | 2 | 0 | 0 | Kuang Quan
Building Database
| 1st phase - Normalization | 4 | 14th Jan 2013 | 17th Jan 2013 | 6 | 4 | 14th Jan 2013 | 17th Jan 2013 | 6.5 | 0 | 0.5 | Brian
| 2nd phase - Data validation | 4 | 14th Jan 2013 | 17th Jan 2013 | 6 | 4 | 14th Jan 2013 | 17th Jan 2013 | 6.5 | 0 | 0.5 | Brian
Implementing Components
| Google Plus share function completed | 2 | 14th Jan 2013 | 15th Jan 2013 | 6 | 2 | 14th Jan 2013 | 15th Jan 2013 | 6 | 0 | 0 | Edward
| Push updates to server | 1 | 14th Jan 2013 | 14th Jan 2013 | 6 | 1 | 14th Jan 2013 | 14th Jan 2013 | 6 | 0 | 0 | Wei Hao
| Bug Squashing | 1 | 15th Jan 2013 | 15th Jan 2013 | 4 | 1 | 15th Jan 2013 | 15th Jan 2013 | 4 | 0 | 0 | Wei Hao
| Retrieval and display of location details completed | 4 | 16th Jan 2013 | 18th Jan 2013 | 11 | 4 | 16th Jan 2013 | 19th Jan 2013 | 11.5 | 0 | 0.5 | Edward
| Simple Ranking Algorithm | 1 | 17th Jan 2013 | 17th Jan 2013 | 6 | 1 | 17th Jan 2013 | 17th Jan 2013 | 6 | 0 | 0 | Wei Hao
| Map function completed | 4 | 24th Jan 2013 | 27th Jan 2013 | 10 | 4 | 24th Jan 2013 | 27th Jan 2013 | 10 | 0 | 0 | Edward
| Facebook share function completed | 3 | 24th Jan 2013 | 26th Jan 2013 | 8 | 3 | 24th Jan 2013 | 26th Jan 2013 | 8 | 0 | 0 | Edward
| Add Reviews into data set | 1 | 25th Jan 2013 | 25th Jan 2013 | 4 | 1 | 25th Jan 2013 | 25th Jan 2013 | 4 | 0 | 0 | Wei Hao
| Convert utility classes to static | 1 | 26th Jan 2013 | 26th Jan 2013 | 4 | 1 | 26th Jan 2013 | 26th Jan 2013 | 4 | 0 | 0 | Wei Hao
| Add & Remove location from favourite list | 2 | 27th Jan 2013 | 28th Jan 2013 | 7 | 2 | 27th Jan 2013 | 28th Jan 2013 | 7.5 | 0 | 0.5 | Edward
| Autorebuild index | 1 | 28th Jan 2013 | 28th Jan 2013 | 4 | 1 | 28th Jan 2013 | 28th Jan 2013 | 4 | 0 | 0 | Wei Hao
Building Database
| Update Reading of Restaurant Review Data | 3 | 25th Jan 2013 | 27th Jan 2013 | 5 | 3 | 25th Jan 2013 | 27th Jan 2013 | 5 | 0 | 0 | Brian
| Intergrate new Resturant data into database | 1 | 30th Jan 2013 | 30th Jan 2013 | 8 | 1 | 30th Jan 2013 | 30th Jan 2013 | 8 | 0 | 0 | Brian
| Retrieval Latitude from Google | 2 | 30th Jan 2013 | 31th Jan 2013 | 5 | 2 | 30th Jan 2013 | 31th Jan 2013 | 5 | 0 | 0 | Brian
Deployment
| Deploy to iPad for testing | 1 | 30th Jan 2013 | 30th Jan 2013 | 5 | 1 | 30th Jan 2013 | 30th Jan 2013 | 5 | 0 | 0 | Wei Hao
Testing & Debugging
| Testing | 2 | 30th Jan 2013 | 31th Jan 2013 | 4 | 2 | 30th Jan 2013 | 31th Jan 2013 | 4 | 0 | 0 | Kuang Quan ,Wei Hao
| Debugging | 2 | 30th Jan 2013 | 31th Jan 2013 | 4 | 2 | 30th Jan 2013 | 31th Jan 2013 | 4 | 0 | 0 | Kuang Quan ,Wei Hao
Unit Testing 1
| Prepare UT questions | 1 | 31th Jan 2013 | 31th Jan 2013 | 2 | 1 | 31th Jan 2013 | 31th Jan 2013 | 2 | 0 | 0 | Kuang Quan
| UT (10.30am - 5pm) | 3 | 5th Feb 2013 | 5th Feb 2013
| Work on feedback | 3 | 6th Feb 2013 | 8th Feb 2013 | 20 | 3 | 6th Feb 2013 | 8th Feb 2013 | 20 | 0 | 0 | Brian, Wei Hao
| Adding of fuzzy search | 1 | 6th Feb 2013 | 6th Feb 2013 | 5 | 1 | 6th Feb 2013 | 6th Feb 2013 | 5 | 0 | 0 | Wei Hao
| Adding of key words from text file | 1 | 7th Feb 2013 | 7th Feb 2013 | 6 | 1 | 7th Feb 2013 | 7th Feb 2013 | 6 | 0 | 0 | Wei Hao
| Settings page completed | 2 | 8th Feb 2013 | 9th Feb 2013 | 5 | 2 | 8th Feb 2013 | 9th Feb 2013 | 5 | 0 | 0 | Edward
| Adding of Ranking Algorithm | 1 | 9th Feb 2013 | 9th Feb 2013 | 6 | 1 | 9th Feb 2013 | 9th Feb 2013 | 5 | 0 | -1 | Wei Hao
| Retails & Recreation inserted into database | 7 | 8th Feb 2013 | 15th Feb 2013 | 18 | 7 | 8th Feb 2013 | 15th Feb 2013 | 20 | 0 | 2 | Brian
| Editing of data via admin console | 1 | 11th Feb 2013 | 11th Feb 2013 | 5 | 1 | 11th Feb 2013 | 11th Feb 2013 | 5 | 0 | 0 | Wei Hao
| Adding of full datasets from all domains | 1 | 13th Feb 2013 | 13th Feb 2013 | 4 | 1 | 13th Feb 2013 | 13th Feb 2013 | 4 | 0 | 0 | Wei Hao
| Custom loading indicator & display more info for reviews | 4 | 11th Feb 2013 | 14th Feb 2013 | 10 | 4 | 11th Feb 2013 | 14th Feb 2013 | 10 | 0 | 0 | Edward
Testing
| Testing | 2 | 11th Feb 2013 | 12th Feb 2013 | 4 | 2 | 11th Feb 2013 | 12th Feb 2013 | 4 | 0 | 0 | Kuang Quan
| Debugging | 2 | 11th Feb 2013 | 12th Feb 2013 | 4 | 2 | 11th Feb 2013 | 12th Feb 2013 | 4 | 0 | 0 | Wei Hao
Prepare for Midterm Review
| Prepare slides | 5 | 12th Feb 2013 | 16th Feb 2013 | 24 | 5 | 12th Feb 2013 | 16th Feb 2013 | 24 | 0 | 0 | Everyone
| Update Wiki | 4 | 13th Feb 2013 | 16th Feb 2013 | 4 | 4 | 13th Feb 2013 | 16th Feb 2013 | 4 | 0 | 0 | Jian Wei
| Rehearsal | 4 | 16th Feb 2013 | 19th Feb 2013 | 24 | 4 | 16th Feb 2013 | 19th Feb 2013 | 24 | 0 | 0 | Everyone
| Buffer | 5 | 16th Feb 2013 | 20th Feb 2013
Milestone 4: 20th Feb 2013: Midterm Review
Transition Phase
10 | Production | 59 days | 19th Feb 2013 | 18th Apr 2013 | 169 | 59 days | 19th Feb 2013 | 18th Apr 2013 | 169 | Completed
Track Progresss Summary
| Progress Review | 2 | 19th Feb 2013 | 20th Feb 2013 | 2 | 2 | 19th Feb 2013 | 20th Feb 2013 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 19th Feb 2013 | 20th Feb 2013 | 2 | 2 | 19th Feb 2013 | 20th Feb 2013 | 2 | 0 | 0 | Jian Wei
| Discuss feedback from midterm | 3 | 19th Feb 2013 | 21st Feb 2013 | 18 | 3 | 19th Feb 2013 | 21st Feb 2013 | 18 | 0 | 0 | Everyone
Requirements Gathering
| Sponsor Meeting on feedbacks | 1 | 22nd Feb 2013 | 22nd Feb 2013 | 6 | 1 | 22nd Feb 2013 | 22nd Feb 2013 | 6 | 0 | 0 | Everyone
Implementing Components
| Work onMidTerm feedback | 5 | 25th Feb 2013 | 1st March 2013 | 20 | 5 | 25th Feb 2013 | 1st March 2013 | 20 | 0 | 0 | Brian, Wei Hao, Edward
Testing & Debugging
| Testing | 2 | 1st Mar 2013 | 2nd Mar 2013 | 4 | 2 | 1st Mar 2013 | 2nd Mar 2013 | 4 | 0 | 0 | Kuang Quan
| Debugging | 2 | 1st Mar 2013 | 2nd Mar 2013 | 4 | 2 | 1st Mar 2013 | 2nd Mar 2013 | 4 | 0 | 0 | Wei Hao
Preparation for UT2
| Preparing survey questions | 3 | 6th Mar 2013 | 8th Mar 2013 | 6 | 3 | 6th Mar 2013 | 8th Mar 2013 | 6 | 0 | 0 | Jessie, Kuang Quan
| Gathering users | 3 | 6th Mar 2013 | 8th Mar 2013 | 6 | 3 | 6th Mar 2013 | 8th Mar 2013 | 6 | 0 | 0 | Everyone
Preparation of Poster
| Design Poster | 2 | 6th Mar 2013 | 8th Mar 2013 | 4 | 2 | 6th Mar 2013 | 8th Mar 2013 | 4 | 0 | 0 | Jessie
UAT 1
| UAT with Sponsor | 5 | 8th Mar 2013 | 12th Mar 2013
| Work on Sponsor's feedbacks | 9 | 12th Mar 2013 | 20th Mar 2013 | 20 | 9 | 12th Mar 2013 | 20th Mar 2013 | 20 | 0 | 0 | Edward, Brian, Wei Hao
Unit Testing 2
| Conducting of UT2 | 1 | 20th Mar 2013 | 20th Mar 2013 | 8 | 1 | 20th Mar 2013 | 20th Mar 2013 | 8 | 0 | 0 | Everyone
| Work on UT2 feedbacks | 13 | 20th Mar 2013 | 1st Apr 2013 | 20 | 13 | 20th Mar 2013 | 1st Apr 2013 | 20 | 0 | 0 | Edward, Brian, Wei Hao
Track Progresss Summary
| Progress Review | 2 | 1st Apr 2013 | 2nd Apr 2013 | 2 | 2 | 1st Apr 2013 | 2nd Apr 2013 | 2 | 0 | 0 | Jian Wei
| Wiki Update | 2 | 1st Apr 2013 | 2nd Apr 2013 | 2 | 2 | 1st Apr 2013 | 2nd Apr 2013 | 2 | 0 | 0 | Jian Wei | 42
Final Review of feedbacks and testing
| Finalize Testing | 5 | 1st Apr 2013 | 5th Apr 2013 | 10 | 5 | 1st Apr 2013 | 5th Apr 2013 | 10 | 0 | 0 | Kuang Quan
Testing & Debugging
| Testing of all Integrated Functions | 5 | 1st Apr 2013 | 5th Apr 2013 | 10 | 5 | 1st Apr 2013 | 5th Apr 2013 | 10 | 0 | 0 | Edward, Brian, Wei Hao
Preparation for Final Presentation
| Prepare Final Presentation materials | 8 | 5th Apr 2013 | 12th Apr 2013 | 24 | 8 | 5th Apr 2013 | 12th Apr 2013 | 24 | 0 | 0 | Everyone
| Supervisor Rehearsal | 1 | 12th Apr 2013 | 12th Apr 2013 | 1 | 1 | 12th Apr 2013 | 12th Apr 2013 | 1 | 0 | 0 | Everyone
| Buffer | 6 | 13th Apr 2013 | 18th Apr 2013
Milestone 5: 18th April 2013: Final presentation
Milestone 6: 26th April 2013: Poster Day