## Sample Test Case
Functionality | Description | Test Inputs | Test procedure | Expected Results | Actual Results | Current Pass/Fail | Signed and Tested By | Previous - Sprint 2
Log in - Correct username + correct password | Ensure that the user of the system is authenticated before they can proceed to use the application | Username:"amy.ng.2009" Password: "qwerty128" | Click the "Log in" button on the login page after entering username and password as specified in 'Test Inputs' | The user should be successfully authenticated and directed to the student's home page. | The successfully authenticated user is directed to the student's home page. | Pass | Rafid Rafid | Pass

## TRF Routing wo UI
Functionality | Description | Test Inputs | Test procedure | Expected Results | Actual Results | Current Pass/Fail | Signed and Tested By | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
This set of test cases is for internal testing purposes only | The approval workflow is based off the following db data
Individual TRF Routing | Approval Workflow: Supervisor > HR Applicant: Staff | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 500 overseas: 'n' User Table For userID S5350714Z, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) 3. TRF should be routed to HR (S8761181G) 4. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) 3. TRF routes to HR (S8761181G) 4. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR Applicant: Staff | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 1002 overseas: 'n' User Table For userID S5350714Z, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) 3. TRF should be routed to HR (S8761181G) 4. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) 3. TRF routes to HR (S8761181G) 4. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > HOD Applicant: Staff | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 3002 overseas: 'n' User Table For userID S5350714Z, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button 5. Click 'select' hyperlink for userID_To 'S2388106C' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) 3. TRF should be routed to HR (S8761181G) 4. TRF should be routed to HOD (S2388106C) 5. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) 3. TRF routes to HR (S8761181G) 4. TRF routes to HOD (S2388106C) 5. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > HOD > CEO Applicant: Staff | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 5001 overseas: 'n' User Table For userID S5350714Z, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button 5. Click 'select' hyperlink for userID_To 'S2388106C' and click the Submit button 6. Click 'select' hyperlink for userID_To 'S0646033Z' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) and a bond record should be created 3. TRF should be routed to HR (S8761181G) 4. TRF should be routed to HOD (S2388106C) 5. TRF should be routed to CEO (S0646033Z) 6. TRF and bond's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) and a bond record is created 3. TRF routes to HR (S8761181G) 4. TRF routes to HOD (S2388106C) 5. TRF routes to CEO (S0646033Z) 6. TRF's and bond's status change to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HOD > CEO Applicant: Staff on probation | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 500 overseas: 'n' User Table For userID S5350714Z, start_Date: 0.2 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S2388106C' and click the Submit button 5. Click 'select' hyperlink for userID_To 'S0646033Z' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) 3. TRF should be routed to HOD (S2388106C) 4. TRF should be routed to CEO (S0646033Z) 5. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) 3. TRF routes to HR (S8761181G) 4. TRF routes to HOD (S2388106C) 5. TRF routes to CEO (S0646033Z) 6. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > CEO Applicant: Staff applying for overseas course | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 1002 overseas: 'y' User Table For userID S5350714Z, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button 5. Click 'select' hyperlink for userID_To 'S0646033Z' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) 3. TRF should be routed to HR (S8761181G) 4. TRF should be routed to CEO (S0646033Z) 5. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) 3. TRF routes to HR (S8761181G) 4. TRF routes to HOD (S2388106C) 5. TRF routes to CEO (S0646033Z) 6. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > HOD > CEO Applicant: Staff on probation applying for overseas course | TRF Table userID: 'S5350714Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 5002 overseas: 'y' User Table For userID S5350714Z, start_Date: 0.2 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S9613780Z' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button 5. Click 'select' hyperlink for userID_To 'S2388106C' and click the Submit button 6. Click 'select' hyperlink for userID_To 'S0646033Z' and click the Submit button | 1. TRF routing page should appear 2. TRF form should be routed to Supervisor (S9613780Z) and a bond record should be created 3. TRF should be routed to HR (S8761181G) 4. TRF should be routed to HOD (S2388106C) 5. TRF should be routed to CEO (S0646033Z) 6. TRF and bond's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to Supervisor (S9613780Z) and a bond record is created 3. TRF routes to HR (S8761181G) 4. TRF routes to HOD (S2388106C) 5. TRF routes to CEO (S0646033Z) 6. TRF's and bond's status change to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > HOD Applicant: Supervisor | TRF Table userID: 'S9613780Z' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 500 overseas: 'n' User Table For userID S9613780Z, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S8761181G' and click the Submit button 4. Click 'select' hyperlink for userID_To 'S2388106C' and click the Submit button | 1. TRF routing page should appear 2. TRF should be routed to HR (S8761181G) 3. TRF should be routed to HOD (S2388106C) 4. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to HR (S8761181G) 3. TRF routes to HOD (S2388106C) 4. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > HOD Applicant: HR | TRF Table userID: 'S7442654I' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 500 overseas: 'n' User Table For userID S7442654I, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S2388106C' and click the Submit button | 1. TRF routing page should appear 2. TRF should be routed to HOD (S2388106C) 3. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to HOD (S2388106C) 4. TRF's status changes to 'approved' | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint
| Approval Workflow: Supervisor > HR > HOD Applicant: HOD | TRF Table userID: 'S2388106C' status: 'pending' wf_status: 0 wf_sub_id: NULL Course Table price: 500 overseas: 'n' User Table For userID S2388106C, start_Date: 10 | 1. Run 'testIndividualRouting.aspx' 2. Click 'select' hyperlink of the TRF Table and click the Submit button 3. Click 'select' hyperlink for userID_To 'S0646033Z' and click the Submit button | 1. TRF routing page should appear 2. TRF should be routed to CEO (S0646033Z) 3. TRF's status should be changed to 'approved' | 1. TRF routing page appears 2. TRF routes to CEO (S0646033Z) For dev: wf_sub_id changes to 1 instead of 15 | Not applicable anymore for this sprint | Rafid Rafid | Pass | Pass | Not applicable anymore for this sprint | Not applicable anymore for this sprint

## Individual Training Nomination
Functionality | User(s) Involved | Description | Test Inputs | Test procedure | Expected Results | Actual Results | Current Pass/Fail | Signed and Tested By | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
[START] TRF ROUTING
Custom Workflow Routing | Applicant: Staff | To ensure that the routing of the custom workflow is correct | - | 1. Check and note who are the approvers in the custom approval workflow 2. Login as staff 3. Navigate to TRF application 4. Fill up TRF and submit form successfully 5. Login to next immediate approver's account and approve the TRF 6. Repeat Step 5 until all approvers have approved the TRF | All the approvers in the custom approval workflow should have received and approved the TRF by the end of the approval process | All the approvers in the custom approval workflow were able to receive and approve the TRF by the end of the approval process | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
|  | To ensure that users outside of the custom workflow do not receive the TRF | - | 1. Check and note who are the approvers in the custom approval workflow 2. Login as staff 3. Navigate to TRF application 4. Fill up TRF and submit form successfully 5. Login to another account that's NOT involved in the custom workflow 6. Check if the account received the TRF 7. Repeat Steps 5 and 6 untill all accounts have been checked | All the user accounts that are not involved in the custom approval workflow should not receive the TRF | All the user accounts that are not involved in the custom approval workflow did not receive the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Supervisor Routing Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Receiver: Supervisor | To ensure that routing of the TRF to the Supervisor is successful | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to Supervisor's account | Supervisor should receive the TRF | Supervisor receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HOD Routing (1) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor Receiver: HOD | To ensure that routing of the TRF to the HOD is successful | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to Supervisor's account, approve TRF and logout 6. Login to HOD's account | HOD should receive the TRF | HOD receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HOD Routing (2) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Supervisor Receiver: HOD | To ensure that routing of the TRF to the HOD is successful | - | 1. Login to Supervisor's account 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from Supervisor's account 5. Login to HOD's account | HOD should receive the TRF | HOD receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HOD Routing (3) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Receiver: HOD | To ensure that the TRF is not routed to the HOD if Supervisor has not approved the TRF | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to HOD's account | HOD should not receive the TRF | HOD does not receive the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR Routing (1) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approvers: Supervisor, HOD Receiver: HR | To ensure that routing of the TRF to HR is successful | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to Supervisor's and HOD's account, approve TRF and logout 6. Login to HR's account | HR should receive the TRF | HR receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR Routing (2) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Supervisor Approver: HOD Receiver: HR | To ensure that routing of the TRF to HR is successful | - | 1. Login to Supervisor's account 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from Supervisor's account 5. Login to HOD's account, approve TRF and logout 6. Login to HR's account | HR should receive the TRF | HR receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR Routing (3) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: HOD Receiver: HR | To ensure that routing of the TRF to HR is successful | - | 1. Login to HOD's account 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from HOD's account 5. Login to HR's account | HR should receive the TRF | HR receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR Routing (4) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Receiver: HR | To ensure that the TRF is not routed to HR if the Supervisor and HOD have not approved the TRF | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to HR's account | HR should not receive the TRF | HR does not receive the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR HOD Routing (1) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approvers: Supervisor, HOD, HR Receiver: HR HOD | To ensure that routing of the TRF to HR HOD is successful | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to Supervisor's, HOD's and HR's account, approve TRF and logout 6. Login to HR HOD's account | HR HOD should receive the TRF | HR HOD receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR HOD Routing (2) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Supervisor Approvers: HOD, HR Receiver: HR HOD | To ensure that routing of the TRF to HR HOD is successful | - | 1. Login to Supervisor's account 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from Supervisor's account 5. Login to HOD's and HR's account, approve TRF and logout 6. Login to HR HOD's account | HR HOD should receive the TRF | HR HOD receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR HOD Routing (3) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: HOD Approver: HR Receiver: HR HOD | To ensure that routing of the TRF to HR HOD is successful | - | 1. Login to HOD's account 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from HOD's account 5. Login to HOD's and HR's account, approve TRF and logout 6. Login to HR HOD's account | HR HOD should receive the TRF | HR HOD receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR HOD Routing (4) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: HR Receiver: HR HOD | To ensure that routing of the TRF to HR HOD is successful | - | 1. Login to HR's account 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from HR's account 5. Login to HR HOD's account | HR HOD should receive the TRF | HR HOD receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
HR HOD Routing (5) Given Workflow: Supervisor > HOD > HR > HR HOD > | Applicant: Staff Receiver: HR HOD | To ensure that the TRF is not routed to the HR HOD if the Supervisor, HOD and HR have not approved the TRF | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs < $10k 4. Logout from staff account 5. Login to HR HOD's account | HR HOD should not receive the TRF | HR HOD does not receive the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
CEO Routing (1) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: Staff Approvers: Supervisor, HOD, HR, HR HOD Receiver: CEO | To ensure that routing of the TRF to the CEO is successful | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs >= $10k 4. Logout from staff account 5. Login to Supervisor's, HOD's, HR's and HR HOD's account, approve TRF and logout 6. Login to CEO's account | CEO should receive the TRF | CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
CEO Routing (2) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: Supervisor Approvers: HOD, HR, HR HOD Receiver: CEO | To ensure that routing of the TRF to the CEO is successful | - | 1. Login to Supervisor's account 2. Navigate to TRF application 3. Apply for a course which costs >= $10k 4. Logout from Supervisor's account 5. Login to HOD's, HR's and HR HOD's account, approve TRF and logout 6. Login to CEO's account | CEO should receive the TRF | CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
CEO Routing (3) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: HOD Approver: HR, HR HOD Receiver: CEO | To ensure that routing of the TRF to the CEO is successful | - | 1. Login to HOD's account 2. Navigate to TRF application 3. Apply for a course which costs >= $10k 4. Logout from HOD's account 5. Login to HR's and HR HOD's account, approve TRF and logout 6. Login to CEO's account | CEO should receive the TRF | CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
CEO Routing (4) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: HR Approver: HR HOD Receiver: CEO | To ensure that routing of the TRF to the CEO is successful | - | 1. Login to HR's account 2. Navigate to TRF application 3. Apply for a course which costs >= $10k 4. Logout from HR's account 5. Login to HR HOD's account, approve TRF and logout 6. Login to CEO's account | CEO should receive the TRF | CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
CEO Routing (5) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: HR HOD Receiver: CEO | To ensure that routing of the TRF to the CEO is successful | - | 1. Login to HR HOD's account 2. Navigate to TRF application 3. Apply for a course which costs >= $10k 4. Logout from HR HOD's account 5. Login to CEO's account | CEO should receive the TRF | CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
CEO Routing (6) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: Staff Receiver: CEO | To ensure that the TRF is not routed to the CEO if the Supervisor, HOD, HR and HR HOD have not approved the TRF | - | 1. Login as staff 2. Navigate to TRF application 3. Apply for a course which costs >= $10k 4. Logout from staff account 5. Login to CEO's account | CEO should not receive the TRF | CEO does not receive the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Submit TRF (with no missing fields) | Staff Supervisor HOD HR HR HOD | To ensure that users are able to submit TRFs successfully if all required fields are filled up | - | 1. Login to a staff, supervisor, HOD, HR, or HR HOD account 2. Navigate to TRF application 3. Fill up all required fields correctly in the TRF 4. Click the 'submit' button | A success message should appear, indicating that the TRF was submitted successfully | A success message appears, indicating that the TRF was submitted successfully | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Submit TRF (with missing fields) | Staff Supervisor HOD HR HR HOD | To ensure that users are not allowed to submit TRFs if there are missing required fields | - | 1. Login to a staff, supervisor, HOD, HR, or HR HOD account 2. Navigate to TRF application 3. Leave a missing required field blank 4. Click the 'submit' button | The system should display an error message, indicating the missing fields that need to be filled up | The system displays an error message, indicating the missing fields that need to be filled up | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Bond Limit (Supervisor) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Receiver: Supervisor | To ensure that the system will alert Supervisor if staff is applying for an external course that will exceed bond limit | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that costs >= $5000 but < $10k and submit TRF 4. Login to Supervisor's account | 1. Supervisor should receive the TRF 2. When Supervisor views the TRF, a message should appear to indicate the exceeding of bond limit | 1. Supervisor receives the TRF 2. When Supervisor views the TRF, a message appears to indicate the exceeding of bond limit | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Bond Limit (HOD) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor Receiver: HOD | To ensure that the system will alert HOD if staff is applying for an external course that will exceed bond limit | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that costs >= $5000 but < $10k and submit TRF 4. Login to Supervisor's account and approve the TRF 5. Login to HOD's account | 1. HOD should receive the TRF 2. When HOD views the TRF, a message should appear to indicate the exceeding of bond limit | 1. HOD receives the TRF 2. When HOD views the TRF, a message appears to indicate the exceeding of bond limit | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Bond Limit (HR) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor, HOD Receiver: HR | To ensure that the system will alert HR if staff is applying for an external course that will exceed bond limit | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that costs >= $5000 but < $10k and submit TRF 4. Login to Supervisor's and HOD's account and approve the TRF 5. Login to HR's account | 1. HR should receive the TRF 2. When HR views the TRF, a message should appear to indicate the exceeding of bond limit | 1. HR receives the TRF 2. When HR views the TRF, a message appears to indicate the exceeding of bond limit | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Bond Limit (HR HOD) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor, HOD, HR Receiver: HR HOD | To ensure that the system will alert HR HOD if staff is applying for an external course that will exceed bond limit | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that costs >= $5000 but < $10k and submit TRF 4. Login to Supervisor's, HOD's and HR's account and approve the TRF 5. Login to HR HOD's account | 1. HR HOD should receive the TRF 2. When HR HOD views the TRF, a message should appear to indicate the exceeding of bond limit | 1. HR HOD receives the TRF 2. When HR HOD views the TRF, a message appears to indicate the exceeding of bond limit | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Bond Limit (CEO) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: Staff Approver: Supervisor, HOD, HR, HR HOD Receiver: CEO | To ensure that the system will alert CEO if staff is applying for an external course that will exceed bond limit | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that costs >= $10k and submit TRF 4. Login to Supervisor's, HOD's, HR's and HR HOD's account and approve the TRF 5. Login to CEO's account | 1. CEO should receive the TRF 2. When CEO views the TRF, a message should appear to indicate the exceeding of bond limit | 1. CEO receives the TRF 2. When CEO views the TRF, a message appears to indicate the exceeding of bond limit | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Budget (Supervisor) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Receiver: Supervisor | To ensure that the system will alert Supervisor if staff is applying for an external course that will exceed budget | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that will exceed the department's budget 4. Login to Supervisor's account | 1. Supervisor should receive the TRF 2. When Supervisor views the TRF, a message should appear to indicate the exceeding of budget | 1. Supervisor receives the TRF 2. When Supervisor views the TRF, a message appears to indicate the exceeding of budget | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Budget (HOD) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor Receiver: HOD | To ensure that the system will alert HOD if staff is applying for an external course that will exceed budget | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that will exceed the department's budget 4. Login to Supervisor's account and approve the TRF 5. Login to HOD's account | 1. HOD should receive the TRF 2. When HOD views the TRF, a message should appear to indicate the exceeding of budget | 1. HOD receives the TRF 2. When HOD views the TRF, a message appears to indicate the exceeding of budget | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Budget (HR) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor, HOD Receiver: HR | To ensure that the system will alert HR if staff is applying for an external course that will exceed budget | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that will exceed the department's budget 4. Login to Supervisor's and HOD's account and approve the TRF 5. Login to HR's account | 1. HR should receive the TRF 2. When HR views the TRF, a message should appear to indicate the exceeding of budget | 1. HR receives the TRF 2. When HR views the TRF, a message appears to indicate the exceeding of budget | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Budget (HR HOD) Given Workflow: Supervisor > HOD > HR > HR HOD | Applicant: Staff Approver: Supervisor, HOD, HR Receiver: HR HOD | To ensure that the system will alert HR HOD if staff is applying for an external course that will exceed budget | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that will exceed the department's budget 4. Login to Supervisor's, HOD's and HR's account and approve the TRF 5. Login to HR HOD's account | 1. HR HOD should receive the TRF 2. When HR HOD views the TRF, a message should appear to indicate the exceeding of budget | 1. HR HOD receives the TRF 2. When HR HOD views the TRF, a message appears to indicate the exceeding of budget | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Flag for Exceeding Budget (CEO) Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Applicant: Staff Approver: Supervisor, HOD, HR, HR HOD Receiver: CEO | To ensure that the system will alert CEO if staff is applying for an external course that will exceed budget | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for a course that will exceed the department's budget 4. Login to Supervisor's, HOD's, HR's and HR HOD's account and approve the TRF 5. Login to CEO's account | 1. CEO should receive the TRF 2. When CEO views the TRF, a message should appear to indicate the exceeding of budget | 1. CEO receives the TRF 2. When CEO views the TRF, a message appears to indicate the exceeding of budget | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Staff on Probation Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Staff | To ensure that the system will route to the CEO if applicant is on probation | - | 1. Login to a 'staff on probation' account 2. Navigate to TRF application 3. Apply for a course which costs < $10k and fill in all required fields 4. Submit TRF 5. Log out of staff account 6. Login to Supervisor, HOD, HR and HR HOD accounts and approve the TRF 7. Login to CEO's account | The CEO should receive the TRF | The CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Overseas Courses Given Workflow: Supervisor > HOD > HR > HR HOD > CEO | Staff | To ensure that the system will route to the CEO if applicant applies for an overseas course | - | 1. Login to a staff account 2. Navigate to TRF application 3. Apply for an overseas course and fill in all required fields 4. Submit TRF 5. Log out of staff account 6. Login to Supervisor, HOD, HR and HR HOD accounts and approve the TRF 7. Login to CEO's account | The CEO should receive the TRF | The CEO receives the TRF | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
[END] TRF ROUTING
Apply for Course (no missing required fields) | All users except CEO | To ensure that an individual staff can apply for an external course using the TRF | - | 1. Login to any staff account 2. Navigate to TRF application 3. Fill in all fields 4. Click the submit button | A success message should appear to indicate that the application was submitted sucessfully | A success message appears to indicate that the application was submitted sucessfully | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Apply for Course (with missing required fields) | All users except CEO | To ensure that an individual staff cannot apply for a course when there are missing required fields | - | 1. Login to any staff account 2. Navigate to TRF application 3. Leave 'Course Title' and Section C blank 4. Click the submit button | An error message should show when the user clicks the submit button | An error message shows when the user clicks the submit button | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Clear Individual TRF Fields | All users except CEO | To ensure that the TRF can be cleared | - | 1. Login to any staff account 2. Navigate to TRF application 3. Fill in all fields 4. Scroll all the way down and click the 'Clear' button | The TRF should be reloaded with all the fields empty | The TRF is reloaded with all the fields empty | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Section C: Target Completion Date | All users except CEO | To ensure that users are not allowed to enter a target completion date that is before the course completion date | Course Title: Brush Teeth Target Completion Date (mm/dd/yyyy): 07/02/2017 | 1. Login to any staff account 2. Navigate to TRF application 3. Select 'Brush Teeth' for 'Course Title' 4. Scroll all the way down and check the 'To prepare for new job role/task' 5. Enter '07/02/2017' for 'Target Completion Date' 6. Submit the TRF | An error message should be displayed, stating that the entered target completion date is invalid | An error message displays, stating that the entered target completion date is invalid | Fail (Due to incorrect implementation of validation) | Rafid Rafid | NA | Fail | Fail (Due to page refresh bug when TRF is submitted) | Fail (Due to incorrect implementation of validation)
Approve TRF | Applicant: Staff Approver: Supervisor | To ensure that supervisors are able to approve TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to a supervisor account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Approve' button | The user should be brought to a page which will inform the user of the successful approval | The user is brought to a page which will inform the user of the successful approval | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: HOD | To ensure that HODs are able to approve TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to a HOD account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Approve' button | The user should be brought to a page which will inform the user of the successful approval | The user is brought to a page which will inform the user of the successful approval | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: HR | To ensure that HRs are able to approve TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to a HOD account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 7. Fill in all required fields correctly 8. Scroll all the way to the bottom of the page and click the 'Approve' button | The user should be brought to a page which will inform the user of the successful approval | The user is brought to a page which will inform the user of the successful approval | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: HR HOD | To ensure that HR HODs are able to approve TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to HR HOD's account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Approve' button | The user should be brought to a page which will inform the user of the successful approval | The user is brought to a page which will inform the user of the successful approval | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: CEO | To ensure that CEO able to approve TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to CEO's account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Approve' button | The user should be brought to a page which will inform the user of the successful approval | The user is brought to a page which will inform the user of the successful approval | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
Reject TRF | Applicant: Staff Approver: Supervisor | To ensure that supervisors are able to reject TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to a supervisor account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Reject' button | The user should be brought to a page which will inform the user of the successful rejection | The user is brought to a page which will inform the user of the successful rejection | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: HOD | To ensure that HODs are able to reject TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to a HOD account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Reject' button | The user should be brought to a page which will inform the user of the successful rejection | The user is brought to a page which will inform the user of the successful rejection | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: HR | To ensure that HRs are able to reject TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to a HR account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Reject' button | The user should be brought to a page which will inform the user of the successful rejection | The user is brought to a page which will inform the user of the successful rejection | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: HR HOD | To ensure that HR HOD is able to reject TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to HR HOD's account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Reject' button | The user should be brought to a page which will inform the user of the successful rejection | The user is brought to a page which will inform the user of the successful rejection | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass
| Applicant: Staff Approver: CEO | To ensure that CEO is able to reject TRFs | - | 1. Login to normal staff account 2. Successfully submit TRF application 3. Logout and then login to CEO's account 4. Click on the bell icon on the top navigation bar 5. Click on the pending TRF message 6. Scroll all the way to the bottom of the page and click the 'Reject' button | The user should be brought to a page which will inform the user of the successful rejection | The user is brought to a page which will inform the user of the successful rejection | Pass | Rafid Rafid | NA | Pass | Fail (Due to page refresh bug when TRF is submitted) | Pass

## e-Learning Portal
Functionality | User(s) Involved | Description | Test Inputs | Test procedure | Expected Results | Actual Results | Current Pass/Fail | Signed and Tested By | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
Login (with correct username AND password) | All users | To ensure that users are able to log into the system when they enter the correct username AND password | Username: 'admin' Password: 'admin' | 1. Go to the login page 2. Enter test inputs | 1. Textboxes' colours should return back to normal if they were previously red 2. User will be redirected to the dashboard page | 1. Textboxes' colours return back to normal if they were previously red 2. User is redirected to the dashboard page | Pass | Rafid Rafid | Pass | Pass | Pass | Pass
Login (with incorrect username AND correct password) | All users | To ensure that users are not able to log into the system when they enter the wrong username OR password | Username: 'admin' Password: 'admin' | 1. Go to the login page 2. Enter test inputs | 1. Username and password textboxes should turn red 2. An error message should appear, saying that the username and password was entered wrongly | 1. Username and password textboxes turn red 2. An error message appears, saying that the username and password was entered wrongly | Pass | Rafid Rafid | Pass | Pass | Pass | Pass
Login (with correct username AND incorrect password) | All users | To ensure that users are not able to log into the system when they enter the wrong username OR password | Username: 'admin' Password: 'hello' | 1. Go to the login page 2. Enter test inputs | 1. Password textbox should turn red 2. An error message should appear, saying that the password was entered wrongly | 1. Password textbox turns red 2. An error message appears, saying that the password was entered wrongly | Pass | Rafid Rafid | Pass | Pass | Pass | Pass
Login (with blank username AND blank password) | All users | To ensure that users are not able to log into the system when they provide no username and no password | Username: "" Password: "" | 1. Go to the login page 2. Enter test inputs | 1. Password and username textboxes should turn red 2. Error messages "Please Enter Your Username" and "Please Enter Your Password" should appear | 1. Password and username textboxes turn red 2. Error messages "Please Enter Your Username" and "Please Enter Your Password" appear | Pass | Rafid Rafid | Pass | Pass | Pass | Pass
Logout | All users | To ensure that users are able to log out of the system | - | Click on the 'Logout' button, located on the top right corner of the portal | 1. User's session will end 2. User will be redirected to the login page | 1. User's session ends 2. User will be redirected to the login page | Pass | Rafid Rafid | Pass | Pass | Pass | Pass
Create Course (no missing required fields) | Course Creator | To ensure that users are able to create courses when there are no missing required fields | Module Category: Compulsory Name of Module: A compulsory course Description of Module: This is a compulsory course Learning Hours: 3 Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click the ellipses button on the top right > 'Create New Modules' 4. Enter test inputs | User should be able to create the course | User is able to create the course | Pass | Rafid Rafid | NA | NA | NA | Pass
Create Course (with missing required fields) | Course Creator | To ensure that users are not able to create courses when there are missing required fields | Module Category: Compulsory Name of Module: [blank] Description of Module: This is a compulsory course Learning Hours: 3 Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click the ellipses button on the top right > 'Create New Modules' 4. Enter test inputs 5. Click the 'Submit' button | 1. Error message(s) should show to indicate the missing fields that need to be fillled 2. User should not be able to create the course | 1. Error message(s) are shown to indicate the missing fields that need to be filled 2. User is not able to create the course | Pass | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Create Course (start date later than end date) | Course Creator | To ensure that users are not able to create the course when the entered start date is later than the end date | Module Category: Compulsory Name of Module: A compulsory course 2 Description of Module: This is a compulsory course Learning Hours: 3 Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click the ellipses button on the top right > 'Create New Modules' 4. Enter test inputs 5. Click the 'Submit' button | 1. Error message(s) should show to indicate that the start date is later than the end date 2. User should not be able to create the course | 1. Error message(s) are shown to indicate the missing fields that need to be filled 2. User is not able to create the course | Pass | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Create Course (existing course) | Course Creator | To ensure that users are not able to create the course when the course already exists in the system | Module Category: Compulsory Name of Module: [same name as an existing course] Description of Module: This is a compulsory course Learning Hours: 3 Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click the ellipses button on the top right > 'Create New Modules' 4. Enter test inputs 5. Repeat Step 2-4 again | 1. Error message(s) should show to indicate that the course already exists 2. User should not be able to create the course | 1. Error message(s) does not show to indicate that the course already exists 2. User is able to create the course | Fail | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Create Course (special characters, letters and decimal point for hours awarded ) | Course Creator | To ensure that users are not able to create the course when special characters, letters and numbers with decimal points are entered for hours awarded | Module Category: Compulsory Name of Module: A compulsory course 3 Description of Module: This is a compulsory course Learning Hours: 1.999 [OR] abc [OR] $%^ Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click the ellipses button on the top right > 'Create New Modules' 4. Enter test inputs | 1. Error message(s) should show to indicate that only integers are allowed to be entered for hours awarded 2. User should not be able to create the course | 1. Error message(s) are shown to indicate that only integers are allowed to be entered for hours awarded 2. User is not able to create the course | Pass | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Create Course (end date is earlier than current date) | Course Creator | To ensure that users are not able to create the course when the entered end date is earlier than the current date | Module Category: Compulsory Name of Module: A compulsory course 4 Description of Module: This is a compulsory course Learning Hours: 3 Target Audience: Staff Date to Display: [today's date] to [one day before current date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click the ellipses button on the top right > 'Create New Modules' 4. Enter test inputs | 1. Error message(s) should show to indicate that the entered end date is earlier than the current date 2. User should not be able to create the course | 1. Error message(s) are not shown to indicate that the entered end date is earlier than the current date 2. User is able to create the course | Fail | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Edit Course (no missing required fields) | Course Creator | To ensure that users are able to edit a course's fields when there are no missing required fields | Module Category: Compulsory Name of Module: Wash face edited Description of Module: Wash face description edited Learning Hours: 2 Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' link for 'Wash face' course 4. Enter test inputs | The course should be updated according to the user's changes | The course is updated according to the user's changes | Fail | Rafid Rafid | NA | NA | NA | Pass
Edit Course (with missing required fields) | Course Creator | To ensure that users are not able to edit a course when there are missing required fields | Module Category: Compulsory Name of Module: [blank] Description of Module: Wash face description edited Learning Hours: 2 Target Audience: Staff Date to Display: [today's date] to [one year from today's date] Module Pre-requisite: [choose any course] OR [blank] | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' link for 'Wash face' course 4. Enter test inputs | 1. Error message(s) should be shown to indicate to the user the missing required fields 2. The course should not be updated | 1. Error message(s) are shown to indicate to the user the missing required fields 2. The course is not updated | Fail (validation is yet to be implemented) | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Deactivate Course | Course Creator | To ensure that users are able to deactivate a course | - | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' link for 'Wash face' course 4. Click on the ellipses icon button, located on the extreme right of course's title 5. Click on the 'Edit Module' button 6. Scroll down and click the 'Deactivate Module' button 7. Click the 'Deactivate' button in the confirmation page | 1. A success message should be shown to the user 2. The deactivated course should be removed from the list of courses | 1. A success message is not shown to the user 2. The deactivated course is not removed from the list of courses | Fail (function is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Activate Course | Course Creator | To ensure that users are able to deactivate a course | - | 1. Login as course creator 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' link for 'Wash face' course 4. Click on the ellipses icon button, located on the extreme right of course's title 5. Click on the 'Edit Module' button 6. Scroll down and click the 'Activate Module' button 7. Click the 'Activate' button in the confirmation page | 1. A success message should be shown to the user 2. The activated course should be displayed in the list of courses | 1. A success message is not shown to the user 2. The activated course appears in the list of courses | Fail (function is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Search Course | Staff | To ensure that users are able to search for courses and the list of relevant courses are displayed to the user | Search: Wash | 1. On navigation bar, click 'Module' > 'Compulsory Training' 2. In search bar, enter test inputs | The system should show the list of courses that matches with the user's searched words | The system shows the list of courses that matches with the user's searched words | Pass | Rafid Rafid | NA | NA | NA | Pass
View List of Compulsory Courses | Staff | To ensure that users are able to view compulsory courses | - | On navigation bar, click 'Module' > 'Compulsory Training' | User should be able to view the list of compulsory courses | User is able to view the list of compulsory courses | Pass | Rafid Rafid | NA | NA | NA | Pass
View List of Leadership Skills Courses | Staff | To ensure that users are able to view leadership skills courses | - | On navigation bar, click 'Module' > 'Leadership Skills Training' | User should be able to view the list of leadership courses | User is able to view the list of leadership courses | Pass | Rafid Rafid | NA | NA | NA | Pass
View List of Professional Courses | Staff | To ensure that users are able to view professional courses | - | On navigation bar, click 'Module' > 'Professional Training' | User should be able to view the list of professional courses | User is able to view the list of professional courses | Pass | Rafid Rafid | NA | NA | NA | Pass
View Course Details | Staff | To ensure that users are able to view the selected course's details | - | 1. On navigation bar, click 'Module' > 'Compulsory Training ' or 'Professional Training' or 'Leadership Skills Training' 2. Click 'View Info' to view a course's details | User should be able to view the course's details | User is able to view the course's details | Pass | Rafid Rafid | NA | NA | NA | Pass
Upload Course Materials (no missing required fields) | Course Creator | To ensure that users are able to upload course materials when there are no missing fields | Enter Upload Title: Course A Enter Upload Description: Course A Description Choose File: [any file] | 1. Login as course creator 2. On navigation bar, click 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click 'Learning Materials' tab 5. Click the ellispses button on the top right > 'Upload Learning Materials' 6. Enter test inputs 7. Click 'Upload' button | User should be able to upload course materials | User is able to upload course materials | Pass | Rafid Rafid | NA | NA | NA | Pass
Upload Course Materials (with missing required fields) | Course Creator | To ensure that users are not able to upload course materials when there are missing required fields | Enter Upload Title: [blank] Enter Upload Description: Course A Description Choose File: [any file] | 1. Login as course creator 2. On navigation bar, click 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click 'Learning Materials' tab 5. Click the ellispses button on the top right > 'Upload Learning Materials' 6. Enter test inputs 7. Click 'Upload' button | 1. Error message(s) should be shown to indicate the missing fields that need to be filled 2. User should not be able to upload course materials | 1. Error message(s) are shown to indicate the missing fields that need to be filled 2. User is not able to upload course materials | Fail (validation is yet to be implemented) | Rafid Rafid | NA | NA | NA | Fail (Validations have not been implemented yet)
Download Course Materials | Enrolled Staff | To ensure that users are able to download course materials | - | 1. Login as staff 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click 'Learning Materials' tab 5. Click the ellispses button on the top right > 'Upload Learning Materials' 6. Upload learning material successfully 7. Click on the learning material's file name to download | User should be able to download course materials | User is able to download course materials | Pass | Rafid Rafid | NA | NA | NA | Fail (Due to a download bug that caused the download to fail)
Delete Course Materials | Course Creator | To ensure that users are able to delete uploaded course materials | - | 1. Login as staff 2. On navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click 'Learning Materials' tab 5. Click on the red trash can button of any uploaded course material 6. Click the 'Delete' button in the confirmation page | 1. A success message should appear to indicate successful deletion of the course material 2. The course material should not be shown in the list of course materials | 1. Success message doesn't appear to indicate successful deletion of the course material 2. The course material still shows in the list of course materials | Fail (function is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Create testimonial (no missing required fields) | HR | To ensure that users are able to create/write testimonials when there are no missing required fields | Title: Saved a life Body: This course helped me to save a life! Name: Patrick | 1. Login as HR 2. In the navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click the pen icon button in grey, located on the right of 'Testimonial' 5. Enter test inputs and click the 'Submit' button | 1. A success message should be displayed to the user 2. The testimonial should be shown in the list of testimonials | 1. A success message is displayed to the user 2. The testimonial is shown in the list of testimonials | Fail (function is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Create testimonial (with missing required fields) | HR | To ensure that users are not able to create/write testimonials when there are missing required fields | Title: [blank] Body: [blank] Name: Patrick | 1. Login as HR 2. In the navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click the pen icon button in grey, located on the right of 'Testimonial' 5. Enter test inputs and click the 'Submit' button | An error message should be displayed to the user | An error message is displayed to the user | Fail (function is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Edit testimonial (no missing required fields) | HR | To ensure that users are able to edit testimonials when there are no missing required fields | [to be completed when UI for edit testimonial is up] | [to be completed when UI for edit testimonial is up] | 1. A success message should be displayed to the user 2. The testimonial be updated in the list of testimonials | 1. A success message is displayed to the user 2. The testimonial is updated in the list of testimonials | Fail (function and UI are yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Edit testimonial (with missing required fields) | HR | To ensure that users are not able to edit testimonials when there are missing required fields | [to be completed when UI for testimonial is up] | [to be completed when UI for testimonial is up] | An error message should be displayed to the user | An error message is displayed to the user | Fail (function and UI are yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Delete testimonial | HR | To ensure that users are able to delete testimonials | - | 1. Login as HR 2. In the navigation bar, click 'Module' > 'Compulsory Training' 3. Click 'View Info' for any of the courses 4. Click the trash icon button in red, located on the right side of each testimonial 5. Click the 'Delete' button in the confirmation page | 1. A success message should be displayed to the user 2. The testimonial should be removed from the list of testimonials | 1. A success message is displayed to the user 2. The testimonial is removed from the list of testimonials | Fail (function is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA

## AI Bot
Functionality | User(s) Involved | Description | Test Inputs | Test procedure | Expected Results | Actual Results | Current Pass/Fail | Signed and Tested By | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "If I am on probation, will I be eligible to go for training course?" | 1. Open up Emma chat bot 2. Enter test inputs | "Yes, you are eligible to go for training subject to the approval from CEO." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How do I go about requesting for training?" | 1. Open up Emma chat bot 2. Enter test inputs | "You are required to apply for the course through the electronic training request form which can be found in the intranet: http://ouramkh/forms_download/hr/Training%20Request%20Form.pdf The request will be routed to your supervisor and Head of Departments (HOD) for approval, subsequently to HR department to verify the eligibility and requirements prior to course approval. You will receive an email notification through the portal of your course status after all approvals and verifications are approved." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What is the difference between the Training Request Form and the Sponsorship form?" | 1. Open up Emma chat bot 2. Enter test inputs | "The Training Request Form (TRF) is catered for short ad-hoc courses ( e.g. a few days to a few weeks etc.). A sponsership form is catered for staff pursuing further education leading to formal qualifications to help them progress further in their career with us. (Bachelor of Science, Advance Diploma or Certificate), it normally lasts from a few months to years , either full-time or part- time. " | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What is the requirements of a MSP (Minimum Service Period) or Bond with AMK-THKH? " | 1. Open up Emma chat bot 2. Enter test inputs | "You can refer to the tab on training policies and requirements on the e-portal" | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What kind of courses can I apply for?" | 1. Open up Emma chat bot 2. Enter test inputs | "Please refer to the the list of common courses applied for during Annual Learning Needs Analysis Exercise on the e-portal." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "I have trouble applying the course online, who can I contact for help?" | 1. Open up Emma chat bot 2. Enter test inputs | "Please contact HR – Learning and Development at 6450-6272 or 6450-6122" | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How do I check the status of application for my course?" | 1. Open up Emma chat bot 2. Enter test inputs | "You can check the status of your application through individual training report in the e-portal." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Do HR take the cost fees inclusive of GST?" | 1. Open up Emma chat bot 2. Enter test inputs | "Yes, we take into consideration all costs related to the course." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Do I need to apply for the course if it is compulsory for attend in the course of my employment?" | 1. Open up Emma chat bot 2. Enter test inputs | "No. You do not need to request for training for compulsory courses. The list of compulsory courses can be found in the intranet : xxx " | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Who can I contact if I am unable to turn up for course on the day?" | 1. Open up Emma chat bot 2. Enter test inputs | "Please contact HR – Learning and Development at 6450-6272 or 6450-6122." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Do I need to submit the certificate attained after I complete the course to HR?" | 1. Open up Emma chat bot 2. Enter test inputs | "Yes, you need to submit the certificate to HR once you receive it from the training vendor." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "If I fail to complete the course due to personal reasons, do I need to pay the course fees on my own?" | 1. Open up Emma chat bot 2. Enter test inputs | "This will be handled on a case by case basis. Please contact HR – Learning and Development at 6450-6272 or 6450-6122 to find out more." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How in advance should I request for my courses?" | 1. Open up Emma chat bot 2. Enter test inputs | "You should request to attend courses 2 weeks before the course registration date so that there will be sufficient time for seek approval, verify and register with external providers." | "You can check the status of your application through individual training report in the e-portal." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How much learning budget am I entitled to each year?" | 1. Open up Emma chat bot 2. Enter test inputs | "Annual learning budget is allocated to each department by HR. Learning budget for each individual is fairly distributed to each staff learning needs by the HODs or supervisor." | "I am unable to process this request yet. Maybe in the near future perhaps." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How is learning budget planned for me each year?" | 1. Open up Emma chat bot 2. Enter test inputs | "There will be an annual Learning Needs Analysis Exercise conducted by your supervisor . You will discuss your learning needs with your supervisor and plan out the budget accordingly." | "Sorry, I do not understand what you are saying" | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What are the criteria to apply for formal sponsorship?" | 1. Open up Emma chat bot 2. Enter test inputs | "You must be a confirmed staff of AMK-THKH, minimally 1 year into your service with AMK-THKH, Singaporean or PR with a performance rating of at least B." | The Training Request Form (TRF) is catered for short-term courses (eg. courses that last for few days to few weeks) while a Sponsorship form is catered for staff pursuing further education in order to progress further with their carreer with us. Courses of this nature usually lasts for few months to few years. | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What are the formal courses I can apply for?" | 1. Open up Emma chat bot 2. Enter test inputs | "Please refer to AIC funding guide at xxx website" | "Please refer to the the list of common courses applied for during Annual Learning Needs Analysis Exercise on the e-portal." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How would I know if the sponsorship I applied for is successful?" | 1. Open up Emma chat bot 2. Enter test inputs | "You are required to go for a panel interview with AMK-THKH. HR will notify you of the application status." | "The Training Request Form (TRF) is catered for short-term courses (eg. courses that last for few days to few weeks) while a Sponsorship form is catered for staff pursuing further education in order to progress further with their carreer with us. Courses of this nature usually lasts for few months to few years." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How do I apply for formal sponsorship?" | 1. Open up Emma chat bot 2. Enter test inputs | "Communicate your needs through the annual Learning Needs Analysis (LNA) exercise to your supervisor. Subsequently fill up the sponsership form prior to a scheduled panel interview." | "The Training Request Form (TRF) is catered for short-term courses (eg. courses that last for few days to few weeks) while a Sponsorship form is catered for staff pursuing further education in order to progress further with their carreer with us. Courses of this nature usually lasts for few months to few years." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What is the bond requirements like with AMK-THKH after my sponsership?" | 1. Open up Emma chat bot 2. Enter test inputs | "For less than S$2000 – no bond, S$2000- S$10,000 – 1 year, S$10,000 – S$25,000 2 years, S$25,000 –S$50,000 3 years, S$50,000 – S$100,000 4 years S$100,000 and above – 5 years" | "Please refer to the tab on training policies and requirements on the e-portal." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Who do I liaise with for formal education matters?" | 1. Open up Emma chat bot 2. Enter test inputs | "Please contact HR – Learning and Development at 6450-6272 or 6450-6122." | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Is there any study leave for formal education?" | 1. Open up Emma chat bot 2. Enter test inputs | "3 working days of study leave" | "I am unable to process this request yet. Maybe in the near future perhaps." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "If my course is overseas, is there any time allowance granted for me to travel?" | 1. Open up Emma chat bot 2. Enter test inputs | "Depends on the travelling hours, please refer to training policy guide" | "Please contact HR – Learning and Development at 6450-6272 or 6450-6122 for assistance." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Where can I find the list of courses I can apply for?" | 1. Open up Emma chat bot 2. Enter test inputs | "Refer to latest version of AIC funding guidelines at xxx website." | "Please refer to the the list of common courses applied for during Annual Learning Needs Analysis Exercise on the e-portal." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "When do I apply for sponsorship of formal education?" | 1. Open up Emma chat bot 2. Enter test inputs | "You can choose to apply for sponsership of formal education at the annual LNA exercise." | "The Training Request Form (TRF) is catered for short-term courses (eg. courses that last for few days to few weeks) while a Sponsorship form is catered for staff pursuing further education in order to progress further with their carreer with us. Courses of this nature usually lasts for few months to few years." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "What are the allowances that I am entitled to if my sponsership is successful?" | 1. Open up Emma chat bot 2. Enter test inputs | "Refer to latest version of AIC funding guidelines at xxx website." | "Sorry, I do not understand what you are saying" | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Am I entitled to all leave types if I go on a full-time sponsership course?" | 1. Open up Emma chat bot 2. Enter test inputs | "Your leave will be pro-rated prior to your full-time sponsership course." | "Please contact HR – Learning and Development at 6450-6272 or 6450-6122 for assistance." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Am I entitled to all leave types if I go on a part-time sponsership course?" | 1. Open up Emma chat bot 2. Enter test inputs | "Your leave entitlement will not be affected." | "Please contact HR – Learning and Development at 6450-6272 or 6450-6122 for assistance." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Do I need to submit any reports after completing my formal education to AMK-THKH?" | 1. Open up Emma chat bot 2. Enter test inputs | "Yes, you are required to submit each completed semester’s transcript and the final certificate to HR." | "Sorry, I do not understand what you are saying" | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "How do I get my reimbursement for any expenses incurred during the course of my studies?" | 1. Open up Emma chat bot 2. Enter test inputs | "Submit all claims to HR- L&D department for reimbursements." | "You can check the status of your application through individual training report in the e-portal." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Who sits in the panel of interviewers before approving my sponsership application?" | 1. Open up Emma chat bot 2. Enter test inputs | "Various Head of Departments (HOD) from different departments " | "You can check the status of your application through individual training report in the e-portal." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "When does my bond commence after I have completed my sponsership? " | 1. Open up Emma chat bot 2. Enter test inputs | "Your bond will commence once you return to work with AMK-THKH" | "Sorry, I do not understand what you are saying" | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Is it compulsory to attend the new staff orientation?" | 1. Open up Emma chat bot 2. Enter test inputs | "Yes, it is compulsory to attend both 1st day orientation as well as the Corporate Orientation that is conducted every 3 months. " | "No. You do not need to request for training for compulsory courses." | Fail | Rafid Rafid | NA | NA | NA | NA
AI Bot | Any Staff | To ensure that the AI Bot works as intended | "Will orientation attendance contribute to my training hours? " | 1. Open up Emma chat bot 2. Enter test inputs | "Yes, both 1st day and corporate orientation will contribute to my training hours." | "Registered staffs are eligible to apply for courses." | Fail | Rafid Rafid | NA | NA | NA | NA
Submit Feedback to AI Bot | Any Staff | To ensure that the AI Bot will allow user to give feedback | Query: "I want to give feedback" What is your name?: "Jane" What department are you from?: "HR" What's your feedback?: "The e-Learning portal is great!" | 1. Open up Emma chat bot 2. Enter test inputs | 1. The AI chat bot should ask the user for their name, department and feedback 2. The AI chat bot should reply by saying ''Thanks for the feedback" 3. The AI chat bot should store the feedback in the database | Same as expected results | Pass | Rafid Rafid | NA | NA | NA | NA

## AI Bot Configuration
Functionality | User(s) Involved | Description | Test Inputs | Test procedure | Expected Results | Actual Results | Current Pass/Fail | Signed and Tested By | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5
View List of Existing Answers | HR | To ensure that users are able to view list of existing answers | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile | The list of existing answers should be displayed to the user | The list of existing answers is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Add Answer (no missing required fields) | HR | To ensure that users are able to add answers when there are no missing required fields | Choose a Category*: About Me Enter Keyword: [blank] Answer*: I am Emma I am your friend | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile 4. Click on the '+ New' button, located beside 'Manage Emma's Answers' 5. Enter test inputs and click the 'Submit' button 6. Click the 'Submit' button in the confirmation page | 1. A success message should be displayed to the user 2. The new answer should be added into the list of existing answers | 1. A success message is displayed to the user 2. The new answer is added into the list of existing answers | Pass | Rafid Rafid | NA | NA | NA | NA
Add Answer (with missing required fields) | HR | To ensure that users are not able to add answers when there are missing required fields | Choose a Category*: About Me Enter Keyword: [blank] Answer*: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile 4. Click on the '+ New' button, located beside 'Manage Emma's Answers' 5. Enter test inputs and click the 'Submit' button 6. Click the 'Submit' button in the confirmation page | An error message should be displayed to the user, indicating which field(s) are incorrect | An error message is displayed to the user, indicating which field(s) are incorrect | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Answer (no missing required fields) | HR | To ensure that users are able to edit answers when there are no missing required fields | Choose a Category*: About Me Enter Keyword: [blank] Answer*: I can edit this answer! | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Update' button 6. Click the 'Overwrite' button in the confirmation page | 1. A success message should be displayed to the user 2. The updated answer should be reflected in the list of existing answers | 1. A success message is displayed to the user 2. The updated answer is reflected in the list of existing answers | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Answer (with missing required fields) | HR | To ensure that users are not able to edit answers when there are missing required fields | Choose a Category*: About Me Enter Keyword: [blank] Answer*: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Update' button 6. Click the 'Overwrite' button in the confirmation page | An error message should be displayed to the user, indicating which field(s) are incorrect | An error message is displayed to the user, indicating which field(s) are incorrect | Pass | Rafid Rafid | NA | NA | NA | NA
Delete Answer | HR | To ensure that users are able to delete answers | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile 4. Click on any one of the pen icon button in blue 5. Click the red 'Delete' button 6. Click the 'Delete' button in the confirmation page | 1. User should be redirected to the list of answers page 2. The deleted answer should not be showing in the list of answers | 1. User is redirected to the list of answers page 2. The deleted answer is not shown in the list of answers | Pass | Rafid Rafid | NA | NA | NA | NA
Search Answer | HR | To ensure that users are able to search for answers | Search: Hello OR [any other word(s)] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Answers' tile 4. Enter test inputs in the search bar | A list of answers which matches the user's search words should be displayed to the user | A list of answers which matches the user's search words is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
View List of Existing Categories | HR | To ensure that users are able to view the list of existing categories | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile | The list of existing categories should be displayed to the user | The list of existing categories is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Create Category (no missing required fields) | HR | To ensure that users are able to create categories when there are no missing required fields | Name of Category: A New Category | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile 4. Click the '+ New' button, located beside 'Manage Categories' 5. Enter test inputs and click the 'Submit' button 6. Click the 'Submit' button in the confirmation page | 1. A success message should be displayed to the user 2. The new category should be added into the list of existing categories | 1. A success message is displayed to the user 2. The new category is added into the list of existing categories | Pass | Rafid Rafid | NA | NA | NA | NA
Create Category (with missing required fields) | HR | To ensure that users are not able to create categories when there are missing required fields | Name of Category: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile 4. Click the '+ New' button, located beside 'Manage Categories' 5. Enter test inputs and click the 'Submit' button 6. Click the 'Submit' button in the confirmation page | An error message should be displayed to the user, indicating which field(s) are incorrect | An error message is displayed to the user, indicating which field(s) are incorrect | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Category (no missing required fields) | HR | To ensure that users are able to edit categories when there are no missing required fields | Name of Category: An Edited Category | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Update' button 6. Click the 'Overwrite' button in the confirmation page | 1. A success message should be displayed to the user 2. The updated category should be reflected in the list of existing categories | 1. A success message is displayed to the user 2. The updated category is reflected in the list of existing categories | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Category (with missing required fields) | HR | To ensure that users are not able to edit categories when there are missing required fields | Name of Category: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Update' button 6. Click the 'Overwrite' button in the confirmation page | An error message should be displayed to the user, indicating which field(s) are incorrect | An error message is displayed to the user, indicating which field(s) are incorrect | Pass | Rafid Rafid | NA | NA | NA | NA
Delete Category | HR | To ensure that users are able to delete categories | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile 4. Click on any one of the pen icon button in blue 5. Click the 'Delete' button 6. Click the 'Delete' button again in the confirmation page | A success message should be displayed to the user | A success message is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Search Category | HR | To ensure that users are able to search for categories | Search: About OR [any other word(s)] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Categories' tile 4. Enter test inputs in the search bar | A list of categories which matches the user's search words should be displayed to the user | A list of categories which matches the user's search words is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
View List of Existing Initialization Messages | HR | To ensure that users are able to view the list of existing initialization messages | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Initialization Message' tile | The list of existing initialization messages should be displayed to the user | The list of existing initialization messages is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Add Initialization Message (no missing required fields) | HR | To ensure that users are able to add initialization messages when there are no missing required fields | Initialization Message: A New Initialization Message | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Initialization Message' tile 4. Scroll down, enter test inputs and click the 'Add' button | 1. A success message should be displayed to the user 2. The new initialization message should be added into the list of existing initialization messages | 1. A success message is displayed to the user 2. The new initialization message is added into the list of existing initialization messages | Pass | Rafid Rafid | NA | NA | NA | NA
Add Initialization Message (with missing required fields) | HR | To ensure that users are not able to add initialization messages when there are missing required fields | Initialization Message: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Initialization Message' tile 4. Scroll down, enter test inputs and click the 'Add' button | An error message should be displayed to the user, indicating which field(s) are incorrect | No error message is displayed to the user to indicate which field(s) are incorrect | Fail (validation is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Edit Initialization Message (no missing required fields) | HR | To ensure that users are able to edit initialization messages when there are no missing required fields | Initialization Message: An Edited Initialization Message | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Initialization Message' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Submit Edits' button | 1. A success message should be displayed to the user 2. The updated initialization message should be reflected in the list of existing initialization messages | 1. A success message is displayed to the user 2. The updated initialization message is reflected in the list of existing initialization messages | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Initialization Message (with missing required fields) | HR | To ensure that users are not able to edit initialization messages when there are missing required fields | Initialization Message: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Initialization Message' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Submit Edits' button | An error message should be displayed to the user, indicating which field(s) are incorrect | No error message is displayed to the user, indicating which field(s) are incorrect | Fail (validation is yet to be implemented) | Rafid Rafid | NA | NA | NA | NA
Delete Initialization Message | HR | To ensure that users are able to delete initialization messages | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Initialization Message' tile 4. Click on any one of the pen icon button in blue 5. Click the 'Delete' button 6. Click the 'Delete' button again in the confirmation page | A success message should be displayed to the user | A success message is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
View List of Existing Help Questions | HR | To ensure that users are able to view the list of existing help questions | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile | The list of existing help questions should be displayed to the user | The list of existing help questions is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Add Help Question (no missing required fields) | HR | To ensure that users are able to add help questions when there are no missing required fields | Help Question: A New Help Question | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile 4. Scroll down, enter test inputs and click the 'Add' button | 1. A success message should be displayed to the user 2. The new help question should be added into the list of existing help questions | 1. A success message is displayed to the user 2. The new help question is added into the list of existing help questions | Pass | Rafid Rafid | NA | NA | NA | NA
Add Help Question (with missing required fields) | HR | To ensure that users are not able to add help questions when there are missing required fields | Help Question: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile 4. Scroll down, enter test inputs and click the 'Add' button | An error message should be displayed to the user, indicating which field(s) are incorrect | An error message is displayed to the user, indicating which field(s) are incorrect | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Help Question (no missing required fields) | HR | To ensure that users are able to edit help questions when there are no missing required fields | Help Question: An Edited Help Question | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Submit Edits' button | 1. A success message should be displayed to the user 2. The updated help question should be reflected in the list of existing help questions | 1. A success message is displayed to the user 2. The updated help question is reflected in the list of existing help questions | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Help Question (with missing required fields) | HR | To ensure that users are not able to edit help questions when there are missing required fields | Help Question: [blank] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile 4. Click on any one of the pen icon button in blue to edit the answer 5. Enter test inputs and click the 'Submit Edits' button | An error message should be displayed to the user, indicating which field(s) are incorrect | An error message is displayed to the user, indicating which field(s) are incorrect | Pass | Rafid Rafid | NA | NA | NA | NA
Delete Help Question | HR | To ensure that users are able to delete help questions | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile 4. Click on any one of the pen icon button in blue 5. Click the 'Delete' button 6. Click the 'Delete' button again in the confirmation page | A success message should be displayed to the user | A success message is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Search Help Question | HR | To ensure that users are able to search for help questions | Search: Help OR [any other word(s)] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Help Questions' tile 4. Enter test inputs in search bar | A list of help questions which matches the user's search words should be displayed to the user | A list of help questions which matches the user's search words is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
View List of Feedback | HR | To ensure that users are able to view the list of feedback | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Emma's Feedback' tile | The list of feedback should be displayed to the user | The list of feedback is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Search Feedback | HR | To ensure that users are able to search for feedback | Search: Good OR [any other word(s)] | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Emma's Feedback' tile 4. Enter test inputs in search bar | A list of feedback which matches the user's search words should be displayed to the user | A list of feedback which matches the user's search words is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
View Emma's Instructions | HR | To ensure that users are able to view Emma's instructions | - | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Instructions' tile | Emma's instructions should be displayed to the user | Emma's instructions is displayed to the user | Pass | Rafid Rafid | NA | NA | NA | NA
Edit Emma's Instructions | HR | To ensure that users are able to edit Emma's instructions | "I am editing Emma's instructions" | 1. Login to a HR's account 2. On the bottom right of the screen, click on 'Ask Emma' button > Gear button 3. Click the 'Instructions' tile 4. Enter test inputs and click the 'Save' button | A success message should be displayed to the user | A success message is displayed to the user | Fail in localhost Pass in cloud | Rafid Rafid | NA | NA | NA | NA

## Questions
Questions | Example

## Testing Notes
Testing Notes