## Bug Metric & Action Plan
Bug Metrics: Queue Ticketing Web Application - Rainbow Solutions
Objective
MAIN OBJECTIVE: To track the level of complexity and severity of any present bugs. By doing so, we will analyze how these bugs are affecting the progress of our web application.
Example:
Iteration | Function | Description of bug | Bug Complexity | Coded By | Spotted by | Bug Rating
1 | Make a Move | User is unable to login into the system | Moderate | Wilfred/Haja | Chen | 3
1 | Make a move | Validation not working | Moderate | Kris/Jasper | Chen | 3
[5 empty] | Total Points | 6
[5 empty] | Status | Guarded
Formula:
The total points will be base on the bug rating from the bug severity table, actions are taken base on the action plan given below and it corresponding total points.
Note: The sum of the total points will be taken for the bugs under the same category
Bug Severity Table |  |  |  |  | Action Plan
Severity | Descriptions | Bug Rating |  |  | Points | Status | Actions
Low | Simple and minor cosmetic bug such as inconsistency of displayed text, or typo mistakes. | 1 |  |  | 0 to 5 | Safe | Bugs are of less complexity and need to be solved almost immediately or during the next pair programming session or buffer time
| The bugs under this category are the bugs that that required not much time for debugging or when the exact issue is easily identified |  |  |  | 6 to 9 | Guarded | On top of the weekly debugging time set aside, 1 extra day will be allocated to fix the bug if needed. Bug score will have to be lowered to safe status before proceeding to next task.
Moderate | Moderate bug whereby a less important functionality is affected. | 3 |  |  | 10 or more | Danger | Stop current development and resolve the bug immediately as a team If needed to. Project Manager reschedules the project.
The bugs under this category might only lead into a moderate problem, but leads to wasted time
High | Critical and severe problem that hinders the progress of the project. | 10
The main functionalities of the project are greatly affected
The bugs which are considered under this category is highly prioritized during our “bug squashing” time if needed to, the team should solve the bug together

## Iteration 1
Iteration 1
No. | Function | Description of bug | Bug Severity | Coded By | Spotted by | Bug Rating
1
2
3
4
[5 empty] | Total | 0
[5 empty] | Status | Safe

## Iteration 2 (hidden)
Iteration 2
No. | Function | Description of bug | Bug Severity | Coded By | Spotted by | Bug Rating
1
2
3
4
Total
Status

## Iteration 3 (hidden)
No. | Function | Description of bug | Bug Severity | Coded By | Spotted by | Bug Rating
1
2
3
4
5
Total
Status

## Iteration 4 (hidden)
No. | Function | Description of bug | Bug Severity | Coded By | Spotted by | Bug Rating
1
2
3
4
Total
Status

## Iteration 5 (hidden)
No. | Function | Description of bug | Bug Severity | Coded By | Spotted by | Bug Rating
1
2
3
4
5
6
Total
Status

## Iteration 6 (hidden)
No. | Function | Description of bug | Bug Severity | Coded By | Spotted by | Bug Rating
1
2
3
4
5
6
Total
Status