## Sheet1
No | Type | Risk | Consequence | Likelihood | Impact Level | Risk Assessment Level | Mitigation Strategy
| Business | Misunderstanding of technical requirements between client and project team as clients are not technically-inclined | Re-doing of development work as a result of mismatched expectations between different parties, leading to time wastage. | Likely - Clients are non-technical trained | Severe - Severe mismatch between what clients wants and what team wants means a repetition of | High | 1. Conduct requirements clarifications before the start of every iteration between team and client to clarify the requirements 2. Using process flow diagrams and storyboards to communicate features with client and team. 3. Discuss about feature design before each development session 4. Recommend and propose technical requirements to client
| Team | Different workloads and committment in team due to varying workloads and outside commitments | Inaccurate allocation and expectation of team and project manager upon each team member, obstructing accurate time estimation and affects schedule allocation. Unhappiness in team due to unfair work allocations throughout the entire project | Likely | Major | High | 1. Set expectations instead of micro-managing how work would be done by individuals 2. Schedule shorter iterations to ensure that targets are met and not piled up. 3. Allocate common coding sessions to allow team to ensure accountability and transparency
| Resources | Hardware and software failure during the development of the project. | .Failure of hardware would cause latest work that is being developed to be lost. Redundancy and repetition of work is necessary in order to keep up to the pace that is being set by the schedule in the event of a software and hardware failure. | Unlikely | Moderate | Moderate | 1. Save development codes onto Subversion 2. Business Analyst to do a weekly backup of all documents and source code.
| Resources | Multiple users working on the same files resulting in conflicting versions of documentation | Loss of information or mismatch in understanding | Likely | Minor | Minor | 1. Segregating editing responsibilities - Business Team to edit business related documents while Technical Team to edit technical-related documents 2. Use of Subversion during the committing of code. Lead Developer would be responsible for any code conflicts.
| Project | Change in volunteer matching business process during the development of the system | Decrease in value of system brought to the business. | Possible | Major | High | 1. Analyse client's As-Is Process and verify with client about current As-Is Model 2. Consider longevity of the system during the design of system
| Business | Difference in understanding of terminologies and terms used in describing the business process (e.g. task, questions, assignments) | Confusion over terms that may lead to the wrong picture being conveyed between client and team | Possible | Minor | Medium | 1. Implement a project dictionary where common terms of use are being recorded down 2. Proactive logging down of common terms of use in the project dictionary
| Team | Group members making assumptions of technical scope required within the project | Inaccurate estimates of time required to complete tasks that leads to unreliable project deadlines and milestones | Possible | Moderate | High | 1. Lay down milestones, deadlines and tasks to do with team before the start of every iteration and review estimates together as a team 2. Project Maanger to actively manage the overrun of schedule through tracking of metrics
| Project | Unfamiliarity with mobile development frameworks required for the project | 1. Inability to make decision about best framework to use 2. Slow project progress because of unfamiliarity | Likely | Major | High | 1. Conduct research on possible mobile development technologies and consult peers and supervisors for advice on which framework to use, in view of mobile app's scope 2. Development of mobile application in parallel with web application to highlight any possible loopholes and to buffer for any major changes needed early.
| Team | Focusing too much on either application platform that causes team to lose focus of the other platform to develop | 1. Imbalanced Development schedules and commitments for different platforms 2. Inconsistency among different platforms | Likely | Minor | Low | 1. Project Manager to review project schedule at the start of every iteration to evaluate if development has been on both platforms