## Sheet1
S/n | Affected Iteration | Who requested | Affected Function | Change Description | Priority (project value) (Priority 1 - Will impact the completeness of process and need to be implemented now Priority 2 - Will not impact the completeness of process but will add significant value to our project Priority 3 - Cosmetic Issues which will not add significant value to project) | Indicator for the impact on project (project schedule) (1= Strong 2 = Moderate 3 =None) | To implement or not | Estimated hours needed | Iteration Completed | Status (open/closed) | *take note: A change is something specific (a feature) that needs to be coded.
1 | 5 | Kar Way | all functions | Restructuring of Database for scalability of project in future | 1 | 2 | Implement | 7 | 5 | closed
2 | 5 | Pang Jin | marker management, scenario mgmt | Able to save markers that does not have lanes | 2 | 2 | Implement | 6 | 5 | closed
3 | 5 | Shemin | lane management | Changing of the interface for create lane function. (user able to view what markers they have clicked on) | 2 | 2 | Implement | 3 | 5 | closed
4 | 5 | Gwendolin | Nil | change the interface of the home page (instead of putting instructions at home page, put the "view scenarios, products, export and import" at homepage) | 2 | 2 | Implement | 3 | 5 | closed
5 | 5 | Gwendolin | Nil | change the interface of how the lane table looks. (have a "view lane table" tab) | 2 | 2 | Implement | 3 | 5 | closed
6 | 5 | Shemin | lane management | For markers which has lane, allow the markers to be bouncy when user hover over to the lane name. This will allow user to know which lane is user currently looking at | 2 | 2 | Implement | 3 | 5 | closed
7 | 6 | Pang Jin | lane management | Able to edit location of markers (with lanes) | 2 | 2 | Implement | 8 | 6 | closed
8 | 7 | Team | Scenario mgmt, marker mgmt, lane mgmt | revamp the interface of the application, focusing on the map interface. | 1 | 2 | Implement | 10 | 7 | closed