## Detailed Schedule
No. | Scenario | Description | Assigned To: | Planned Start | Planned End | Planned Duration | Actual Start | Actual End | Actual Duration | PM Remarks | Members' Remarks | Supervisor's Remarks
Box.Us Project Schedule
Iteration #0 - Project Initiation (30/09/2012 - 06/10/2012)
1 | Project Management | Establish Team Charter | Kevin | 2012-09-30 | 2012-09-30 | 1 day | 2012-09-30 | 2012-09-30 | 1 day
|  | Establish Roles And Responsibilities | Sherrie | 2012-09-30 | 2012-09-30 | 1 day | 2012-09-30 | 2012-09-30 | 1 day
|  | Establish Team Vision, Mission, Values | All | 2012-09-30 | 2012-09-30 | 1 day | 2012-10-05 | 2012-10-05 | 1 day
|  | Establish Team Learning Outcomes | All | 2012-09-30 | 2012-09-30 | 1 day | 2012-10-05 | 2012-10-05 | 1 day
|  | Establish Team Charter | Kevin | 2012-09-30 | 2012-09-30 | 1 day | 2012-09-30 | 2012-09-30 | 1 day
|  | Establish Team Identity | Jervenne | 2012-09-30 | 2012-09-30 | 1 day | 2012-09-30 | 2012-09-30 | 1 day
|  | Define Team Risks | Kevin | 2012-09-30 | 2012-09-30 | 1 day | 2012-09-30 | 2012-09-30 | 1 day
|  | Establish Risk Assessment/Mitigation Procedures | Kevin | 2012-10-01 | 2012-10-01 | 1 day | 2012-10-01 | 2012-10-02 | 2 day
|  | Establish Communication Plan | Jenzus | 2012-10-01 | 2012-10-01 | 1 day | 2012-10-01 | 2012-10-01 | 1 day
2 | Sponsor Sourching | Brainstorm For Sponsor | All | 2012-10-03 | 2012-10-03 | 1 day | 2012-10-03 | 2012-10-03 | 1 day
|  | Decide on Sponsor | All | 2012-10-05 | 2012-10-05 | 1 day | 2012-10-05 | 2012-10-05 | 1 day
3 | Technology Research | Research on relevant technologies | Boon Kheng | 2012-10-05 | 2012-10-05 | 1 day | 2012-10-06 | 2012-10-06 | 1 day
4 | Wiki Update | Prepare Wiki | Waimun | 2012-10-05 | 2012-10-05 | 1 day | 2012-10-09 | 2012-10-09 | 1 day
Iteration #1 - Identify Business Needs (07/10/2012 - 20/10/2012)
1 | Project Management | Review Project Schedule | Kevin | 2012-10-07 | 2012-10-07 | 1 day | 2012-10-07 | 2012-10-07 | 1 day
|  | Establish Standardized Terms Dictionary | Kevin | 2012-10-07 | 2012-10-07 | 1 day | 2012-10-07 | 2012-10-07 | 1 day
2 | Requirements Gathering | Identify Process Stakeholders | Kevin | 2012-10-07 | 2012-10-07 | 1 day | 2012-10-07 | 2012-10-07 | 1 day
|  | As-Is Business Process | Waimun | 2012-10-08 | 2012-10-08 | 1 day | 2012-10-08 | 2012-10-08 | 1 day
|  | To-Be Business Process | Waimun | 2012-10-08 | 2012-10-08 | 1 day | 2012-10-08 | 2012-10-08 | 1 day
|  | Identify Business Goals and Indicators | Sherrie | 2012-10-08 | 2012-10-08 | 1 day | 2012-10-08 | 2012-10-08 | 1 day
3 | Use Case Scenarios | Identify Use Cases | All | 2012-10-09 | 2012-10-09 | 1 day | 2012-10-09 | 2012-10-09 | 1 day
4 | Technology Research | Research on Java Frameworks | Jenzus | 2012-10-09 | 2012-10-10 | 2 day | 2012-10-09 | 2012-10-11 | 3 day
|  | Investigate Matching Mechanism | Boon Kheng | 2012-10-09 | 2012-10-10 | 2 day | 2012-10-09 | 2012-10-10 | 2 day
|  | Research on Mobile Platform Development | Jervenne | 2012-10-09 | 2012-10-10 | 2 day | 2012-10-09 | 2012-10-11 | 3 day
|  | Research on User Experience | Waimun | 2012-10-09 | 2012-10-10 | 2 day | 2012-10-09 | 2012-10-10 | 2 day
|  |  | Kevin | 2012-10-14 | 2012-10-14 | 1 day | 2012-10-14 | 2012-10-14 | 1 day
| Requirements Gathering | Review Requirements | Kevin | 2012-10-14 | 2012-10-15 | 1 day | 2012-10-14 | 2012-10-15 | 1 day
2 | Storyboard | Identify User Scenarios | Jenzus | 2012-10-14 | 2012-10-14 | 1 day | 2012-10-14 | 2012-10-14 | 1 day
|  | Create Paper Prototype for Web Application | Waimun | 2012-10-14 | 2012-10-16 | 3 days | 2012-10-14 | 2012-10-14 | 1 day
|  | Create Paper Prototype for Mobile Appplication | Sherrie | 2012-10-14 | 2012-10-15 | 2 days | 2012-11-02 | 2012-11-02 | 2 days | Delayed due to client expectation
|  | Review User Scenarios | Kevin | 2012-10-15 | 2012-10-15 | 1day | 2012-10-15 | 2012-10-15 | 1day
3 | Solutioning | Identify System Domain | All | 2012-10-16 | 2012-10-16 | 1 day | 2012-10-16 | 2012-10-16 | 1 day
|  | Identify Main Functionalities | Boon Kheng | 2012-10-17 | 2012-10-18 | 2 day | 2012-10-17 | 2012-10-18 | 2 day
|  | Identify System Architecture | Jenzus | 2012-10-17 | 2012-10-17 | 1 day | 2012-10-17 | 2012-10-17 | 1 day
4 | Technology Research | Research on Java Frameworks | Jervenne | 2012-10-18 | 2012-10-18 | 1 day | 2012-10-18 | 2012-10-18 | 1 day
|  | Research on Hosting Providers | Boon Kheng | 2012-10-18 | 2012-10-18 | 1 day | 2012-10-18 | 2012-10-18 | 1 day | To continue to revert to Empact about status of hosting providers
7 | Documententation | Business Analysis Document | Sherrie | 2012-10-19 | 2012-10-20 | 2 day | 2012-10-19 | 2012-10-20 | 2 day
|  | Requirements Document | Jervenne | 2012-10-19 | 2012-10-20 | 2 day | 2012-10-19 | 2012-10-20 | 2 day
|  | Use Case Scenarios | Jenzus | 2012-10-19 | 2012-10-20 | 2 day | 2012-10-19 | 2012-10-20 | 2 day
6 | Buffer |  |  | 2012-10-19 | 2012-10-20 | 2 day | 2012-10-19 | 2012-10-20 | 2 day
8 | PM Email Update |  | Kevin | 2012-12-20 | 2012-12-20 | 0.5 day | 2012-12-20 | 2012-12-20 | 1 day
9 | Wiki Update | Update Wiki for Project Overview and Documentation | Waimun | 2012-12-20 | 2012-12-20 | 1 day | 2012-12-20 | 2012-12-20 | 1 day
Iteration #3 - Solutioning (21/10/2012 - 27/10/2012 )
1 | Project Management | Review Project Schedule | Kevin | 2012-10-21 | 2012-10-21 | 1 days | 2012-10-21 | 2012-10-21 | 1 days
|  | Review Use Case Scenarios | Kevin | 2012-10-21 | 2012-10-21 | 1 days | 2012-10-21 | 2012-10-21 | 1 days
2 | Design and Analysis | Refine Requirements | Jervenne | 2012-10-21 | 2012-10-21 | 1 days | 2012-10-21 | 2012-10-21 | 1 days
|  | Analyze Changes to Business Objectives | Sherrie | 2012-10-21 | 2012-10-21 | 1 days | 2012-10-21 | 2012-10-21 | 1 days
| User Interface | Design Wireframe for User Interface | Waimun | 2012-10-21 | 2012-10-21 | 1 days | 2012-10-21 | 2012-10-21 | 1 days
| System Design | Research on Mobile Platform Development | Boon Kheng | 2012-10-21 | 2012-10-21 | 1 days | 2012-10-21 | 2012-10-21 | 1 days
|  | Identify Entity Relationship Diagram | Jervenne, Boon Kheng | 2012-10-21 | 2012-10-22 | 2 days | 2012-10-21 | 2012-10-24 | 4 days
|  | Identify Deployment Diagram | Boon Kheng | 2012-10-22 | 2012-10-22 | 1 days | 2012-11-01 | 2012-11-01 | 1 day | Empact has been informed about new server purchase
|  | Identify Functionalities | Jervenne | 2012-10-23 | 2012-10-23 | 1 days | 2012-10-23 | 2012-10-23 | 1 days
5 | Development Preparation | Prepare IDE for Mobile Development | Developers | 2012-10-23 | 2012-10-23 | 1 days | 2012-11-05 | 2012-11-05 | 1 day | Delayed as Empact was still in discussion about mobile development
|  | Prepare IDE for Web Development | Developers | 2012-10-23 | 2012-10-23 | 1 days | 2012-10-23 | 2012-10-23 | 1 days
|  | Prepare Database | Jenzus | 2012-10-24 | 2012-10-24 | 1 days | 2012-10-24 | 2012-10-24 | 1 days
|  | Prepare Deployment Server | Boon Kheng | 2012-10-24 | 2012-10-24 | 1 days | 2012-10-24 | 2012-10-24 | 1 days
9 | Documentation | System Design Documentation | Jervenne | 2012-10-24 | 2012-10-24 | 1 days | 2012-10-24 | 2012-10-24 | 1 days
10 | Buffer |  |  | 2012-10-25 | 2012-10-26 | 2 days | 2012-10-25 | 2012-10-26 | 2 days
11 | PM Email Update |  | Kevin | 2012-10-27 | 2012-10-27 | 1 days | 2012-10-28 | 2012-10-28 | 1 days
12 | Wiki Update | Update Wiki | Waimun | 2012-10-27 | 2012-10-27 | 1 days | 2012-10-29 | 2012-10-29 | 1 days
Iteration #3 - Prototyping (27/10/2012 - 03/11/2012)
1 | Project Management | Review Project Schedule | Kevin | 2012-10-28 | 2012-10-28 | 1 days | 2012-10-28 | 2012-10-28 | 1 days
|  | Review Use Case Scenarios | Kevin | 2012-10-28 | 2012-10-28 | 1 days | 2012-10-28 | 2012-10-28 | 1 days
2 | Design Review | Review Storyboard Scenario | Waimun | 2012-10-28 | 2012-10-28 | 1 days | 2012-10-31 | 2012-10-31 | 1 days
|  | Review Entity Relationship Diagram | Boon Kheng | 2012-10-28 | 2012-10-28 | 1 days | 2012-10-28 | 2012-10-28 | 1 days
|  | Review High Fidelity Prototype Functionalities | Jervenne | 2012-10-28 | 2012-10-28 | 1 days | 2012-10-28 | 2012-10-28 | 1 days
3 | Build | Set up MySQL Database | Jenzus | 2012-10-29 | 2012-10-29 | 1 days | 2012-10-29 | 2012-10-29 | 1 days
|  | Build Web Prototype (Register for Account) | Jenzus | 2012-10-29 | 2012-10-30 | 2 days | 2012-10-31 | 2012-10-31 | 1 days
4 | Build Mobile Prototype | Set up Mobile Environment | Boon Kheng | 2012-10-31 | 2012-10-31 | 2 days | 2012-11-02 | 2012-11-02 | 2 days
|  | Build Mobile Prototype | Boon Kheng | 2012-10-31 | 2012-11-01 | 1 day | 2012-10-31 | 2012-11-02 | 3 days
|  | Integrate Mobile UI Framework | Jervenne | 2012-10-31 | 2012-11-01 | 1 day | 2012-11-01 | 2012-11-02 | 1 day
5 | Release | Deploy Web Prototype | Jenzus | 2012-11-01 | 2012-11-01 | 1 days | 2012-11-04 | 2012-11-04 | 1 days
|  | Deploy Mobile Prototype | Boon Kheng | 2012-11-01 | 2012-11-01 | 1 day | 2012-11-01 | 2012-11-01 | 1 day
6 | Acceptance Preparation | Prepare Acceptance Materials | Kevin | 2012-10-29 | 2012-10-29 | 2days | 2012-11-02 | 2012-11-03 | 2 days
|  | Prepare Acceptance Slides | Sherrie | 2012-10-29 | 2012-10-29 | 1 days | 2012-11-03 | 2012-11-03 | 1 day
|  | Rehearse for Acceptance | All | 2012-10-30 | 2012-10-30 | 1 days | 2012-11-04 | 2012-11-04 | 1 day
|  | Acceptance Presentation | All | 2012-11-06 | 2012-11-06 | 1 day | 2012-11-06 | 2012-11-06 | 1 day
|  | Acceptance Feedback Review | All | 2012-11-07 | 2012-11-07 | 1 day | 2012-11-16 | 2012-11-16 | 1 day | To be completed during next Supv Meeting
9 | Buffer |  |  | 2012-11-08 | 2012-11-09 | 2 days | 2012-11-08 | 2012-11-09 | 2 days
10 | PM Email Udpate |  | Kevin | 2012-11-09 | 2012-11-09 | 1 day | 2012-11-09 | 2012-11-09 | 1 day
11 | Wiki Update | Update Wiki | Waimun | 2012-11-09 | 2012-11-09 | 1 day | 2012-11-16 | 2012-11-16 | 1 day | Delayed until during after supervisor meeting
Milestone #2 - Acceptance Reached: 06/11/2012
Iteration #4 (10/11/2012-21/11/2012)
1 | Project Management | Review Project Schedule | Kevin | 2012-11-10 | 2012-11-10 | 1 day | 2012-11-10 | 2012-11-10 | 1 day
|  | Acceptance Review | All | 2012-11-11 | 2012-11-11 | 1 day | 2012-11-13 | 2012-11-13 | 1 day | To be done during Supv Meeting
2 | Design | Paper Prototyping | Waimun | 2012-11-12 | 2012-11-13 | 2 days | 2012-11-07 | 2012-11-07 | 1 day
|  | Review Functionality | Jenzus | 2012-11-12 | 2012-11-12 | 1 day | 2012-11-08 | 2012-11-08 | 1 day
|  | Review User Interface | Waimun | 2012-11-12 | 2012-11-12 | 1 day | 2012-11-13 | 2012-11-13 | 1 day
|  | Review Development Tasks | Boon Kheng | 2012-11-12 | 2012-11-12 | 1 day | 2012-11-13 | 2012-11-13 | 1 day
|  | Script Test Cases | Jervenne | 2012-11-12 | 2012-11-12 | 1 day | 2012-11-12 | 2012-11-12 | 1 day
3 | Build (Web) | Register for Account (Review Design) | Jervenne | 2012-11-13 | 2012-11-13 | 1 day | 2012-11-13 | 2012-11-13 | 1 day
|  | Edit Account | Jenzus | 2012-11-13 | 2012-11-14 | 2 days | 2012-11-13 | 2012-11-14 | 2 days
|  | Remove Account | Jervenne | 2012-11-14 | 2012-11-14 | 1 day | 2012-11-14 | 2012-11-14 | 1 day
|  | Reset Password | Boon Kheng | 2012-11-14 | 2012-11-14 | 1 day | 2012-11-14 | 2012-11-14 | 1 day
|  | Login/Logout | Boon Kheng | 2012-11-15 | 2012-11-15 | 1 day | 2012-11-15 | 2012-11-15 | 1 day
|  | Integration | Jenzus | 2012-11-16 | 2012-11-16 | 1 day | 2012-11-16 | 2012-11-16 | 1 day
4 | Test | Integration Testing | Sherrie, Kevin | 2012-11-17 | 2012-11-17 | 1 day
|  | Fix Bugs | Boon Kheng | 2012-11-18 | 2012-11-18 | 1 day
5 | Release | Deployment | Jenzus | 2012-11-19 | 2012-11-19 | 1 day
|  | Review Improvements | All | 2012-11-19 | 2012-11-19 | 1 day
6 | Buffer |  |  | 2012-11-20 | 2012-11-20 | 1 day
7 | PM Email Update |  | Kevin | 2012-11-21 | 2012-11-21 | 1 day
8 | Wiki Update | Update Wiki | Sherrie | 2012-11-21 | 2012-11-21 | 1 day
Iteration #5 (22/11/2012 - 01/12/2012)
1 | Project Management | Review Project Schedule | Kevin | 2012-11-22 | 2012-11-22 | 1 day | 2012-11-22 | 2012-11-22 | 1 day
2 | Design | Review Use Case Scenarios | Jenzus | 2012-11-22 | 2012-11-22 | 1 day
|  | Paper Prototyping | Waimun | 2012-11-22 | 2012-11-22 | 1 day | 2012-11-22 | 2012-11-22 | 1 day
|  | Review Paper Prototype with Client | All | 2012-11-22 | 2012-11-22 | 1 day
|  | Review Functionality List | Jenzus | 2012-11-22 | 2012-11-22 | 1 day | 2012-11-22 | 2012-11-22 | 1 day
|  | Review User Interface | Waimun | 2012-11-22 | 2012-11-22 | 1 day | 2012-11-22 | 2012-11-22 | 1 day
|  | Review Development Tasks | Development Team | 2012-11-22 | 2012-11-22 | 1 day
|  | Script Test Cases | Jervenne | 2012-11-22 | 2012-11-22 | 1 day
3 | Build (Web) | Viewing Profile Details | Development Team | 2012-11-23 | 2012-11-27 | 4 days
|  | Editing Profile Details | Development Team | 2012-11-23 | 2012-11-27 | 1 day
| Build(Mobile) | Login/Logout | Development Team | 2012-11-22 | 2012-11-22 | 1 day
|  | View Account | Development Team | 2012-11-23 | 2012-11-23 | 1 day
|  | Reset Password | Development Team | 2012-11-23 | 2012-11-24 | 1 day
|  | Edit Account Details | Development Team | 2012-11-26 | 2012-11-27 | 1 day
|  | Integration (Web) | Development Team | 2012-11-28 | 2012-11-28 | 1 day
|  | Integration (Mobile) | Development Team | 2012-11-28 | 2012-11-28 | 1 day
4 | Test | Integration Testing | Sherrie | 2012-11-29 | 2012-11-29 | 1 day
|  | Fix Bugs | Development Team | 2012-11-29 | 2012-11-29 | 1 day
5 | Release | Deployment | Boon Kheng | 2012-11-30 | 2012-11-30 | 1 day
|  | Review Improvements | Kevin | 2012-11-30 | 2012-11-30 | 1 day
6 | Buffer |  |  | 2012-12-01 | 2012-12-01 | 1 day
7 | PM Email Update |  | Kevin | 2012-12-01 | 2012-12-01 | 1 day
8 | Wiki Update | Update Wiki | Sherrie | 2012-12-01 | 2012-12-01 | 1 day
Iteration 6 (02/12/2012 - 15/12/2012)
1 | Project Management | Review Project Schedule | Kevin | 2012-12-02 | 2012-12-02 | 1 day
2 | Design | Review Use Case Scenarios | Sherrie | 2012-12-02 | 2012-12-02 | 1 day
|  | Paper Prototyping | Waimun | 2012-12-02 | 2012-12-02 | 1 day
|  | Review Functionality List | Jenzus | 2012-12-04 | 2012-12-04 | 1 day
|  | Review User Interface | Waimun | 2012-12-04 | 2012-12-04 | 1 day
|  | Review Development Tasks | Development Team | 2012-12-05 | 2012-12-05 | 1 day
|  | Script Test Cases | Jervenne | 2012-12-05 | 2012-12-05 | 1 day
3 | Build (Web) | Posting of Task | Development Team | 2012-12-06 | 2012-12-07 | 2 day
|  | Browsing of Task | Development Team | 2012-12-06 | 2012-12-06 | 1 day
|  | View Task | Development Team | 2012-12-06 | 2012-12-07 | 1 day
|  | View Recommended Task | Development Team | 2012-12-06 | 2012-12-08 | 2 day
|  | Apply for Other Task | Development Team | 2012-12-10 | 2012-12-11 | 2 day
| Build (Mobile) | View Own Profile | Development Team | 2012-12-10 | 2012-12-10 | 1 day
|  | Edit Own Profile | Development Team | 2012-12-10 | 2012-12-11 | 2 day
|  | Integration (Mobile) | Development Team | 2012-12-11 | 2012-12-12 | 2 day
|  | Integration (Web) | Development Team | 2012-12-11 | 2012-12-12 | 2 day
4 | Test | Integration Testing | Development Team | 2012-12-12 | 2012-12-12 | 1 day
|  | Fix Bugs | Development Team | 2012-12-12 | 2012-12-13 | 2 day
5 | Release | Deployment | Boon Kheng | 2012-12-13 | 2012-12-13 | 1 day
6 | Buffer |  |  | 2012-12-14 | 2012-12-14 | 1 day
7 | PM Email Update |  | Kevin | 2012-12-15 | 2012-12-15 | 1 day
8 | Wiki Update | Update Wiki | Kevin | 2012-12-15 | 2012-12-15 | 1 day
Iteration 7 (16/12/2012 - 29/01/2013)
1 | Project Management | Review Project Schedule | Kevin | 2012-12-16 | 2012-12-16 | 1 day
2 | Design | Review Use Case Scenarios | Kevin | 2012-12-16 | 2012-12-16 | 1 day
|  | Review Functionality List | Sherrie | 2012-12-16 | 2012-12-16 | 1 day
|  | Review User Interface | Waimun | 2012-12-16 | 2012-12-16 | 1 day
|  | Review Development Tasks | Boon Kheng | 2012-12-16 | 2012-12-16 | 1 day
|  | Script Test Cases | Jervenne | 2012-12-16 | 2012-12-16 | 1 day
3 | Build (Web) | Receiving Notification | Development Team | 2012-12-17 | 2012-12-17 | 2 day
|  | Posting A Question | Development Team | 2012-12-18 | 2012-12-19 | 2 day
|  | Replying A Question | Development Team | 2012-12-19 | 2012-12-20 | 2 day
|  | Organising A Question | Development Team | 2012-12-19 | 2012-12-20 | 2 day
| Build (Mobile) | Browsing for Task | Development Team | 2012-12-19 | 2012-12-19 | 1day
|  | Viewing Recommended Task | Development Team | 2012-12-19 | 2012-12-19 | 2 day
|  | Integration (Web) | Development Team | 2012-12-20 | 2012-12-21 | 2 day
|  | Integration (Mobile) | Development Team | 2012-12-20 | 2012-12-21 | 2 day
4 | Test | Integration Testing | Sherrie | 2012-12-22 | 2012-12-22 | 1 day
|  | Fix Bugs | Development Team | 2012-12-24 | 2012-12-25 | 1 day
5 | Release | Deployment | Development Team | 2012-12-26 | 2012-12-26 | 1 day
6 | Buffer |  |  | 2012-12-27 | 2012-12-28 | 2 days
7 | PM Email Update |  | Kevin | 2012-12-29 | 2012-12-29 | 1 day
8 | Wiki Update | Update Wiki | Kevin | 2012-12-29 | 2012-12-29 | 1 day
Iteration 8 (30/12/2012 - 12/01/2013)
1 | Project Management | Review Project Schedule | Kevin | 2012-12-30 | 2012-12-30 | 1 day
2 | Design | Review Use Case Scenarios | Kevin | 2012-12-30 | 2012-12-30 | 1 day
|  | Review Functionality List | Sherrie | 2012-12-30 | 2012-12-30 | 1 day
|  | Review User Interface | Waimun | 2012-12-30 | 2012-12-30 | 1 day
|  | Review Development Tasks | Boon Kheng | 2012-12-30 | 2012-12-30 | 1 day
|  | Script Test Cases | Jervenne | 2012-12-30 | 2012-12-30 | 1 day
3 | Build (Web) | Posting of Assignments | Development Team | 2012-12-30 | 2012-12-30 | 1 day
|  | Assignments | Development Team | 2013-01-01 | 2013-01-01 | 1 day
|  | Filling Up of Feedback Form | Development Team | 2013-01-01 | 2013-01-02 | 2 days
| Build (Mobile) | Receiving Notification for Task | Development Team | 2013-01-02 | 2013-01-02 | 1 day
|  | Posting Question | Development Team | 2013-01-03 | 2013-01-04 | 2 day
|  | Replying Question | Development Team | 2013-01-04 | 2013-01-05 | 2 day
|  | Integration (Web) | Development Team | 2013-01-05 | 2013-01-06 | 2 days
|  | Integration (Mobile) | Development Team | 2013-01-05 | 2013-01-06 | 2 days
4 | Test | Integration Testing | Sherrie | 2013-01-06 | 2013-01-06 | 1 day
|  | Fix Bugs | Development Team | 2013-01-07 | 2013-01-08 | 1 day
5 | Release | Deployment | Development Team | 2013-01-09 | 2013-01-09 | 1 day
6 | Buffer |  |  | 2013-01-09 | 2013-01-10 | 1 day
7 | PM Email Update |  | Kevin | 2013-01-11 | 2013-01-11 | 1 day
8 | Wiki Update | Update Wiki | Kevin | 2013-01-11 | 2013-01-11 | 1 day
Iteration 9 (13/01/2013 - 26/01/2013)
1 | Project Management | Review Project Schedule | Kevin | 2013-01-13 | 2013-01-13 | 1 day
2 | Design | Review Use Case Scenarios | Jenzus | 2013-01-13 | 2013-01-13 | 1 day
|  | Review Functionality List | Sherrie | 2013-01-13 | 2013-01-13 | 1 day
|  | Review User Interface | Waimun | 2013-01-13 | 2013-01-13 | 1 day
|  | Review Development Tasks | Boon Kheng | 2013-01-13 | 2013-01-13 | 1 day
|  | Script Test Cases | Jervenne | 2013-01-13 | 2013-01-13 | 1 day
3 | Build | Setting Reviewers for Task | Development Team | 2013-01-14 | 2013-01-16 | 3 days
|  | Approving/Reject Task Completion | Development Team | 2013-01-16 | 2013-01-18 | 3 days
|  | Add in Graphics from Designer | Development Team | 2013-01-19 | 2013-01-20 | 1 day
|  | Fine Tune User Interface | Development Team | 2013-01-21 | 2013-01-21 | 1 day
|  | Integration | Development Team | 2013-01-21 | 2013-01-22 | 2 day
4 | Test | Integration Testing | Sherrie | 2013-01-22 | 2013-01-22 | 1 day
|  | Fix Bugs | Development Team | 2013-01-22 | 2013-01-23 | 2 day
5 | Release | Deployment | Development Team | 2013-01-23 | 2013-01-23 | 1 day
6 | Buffer |  |  | 2013-01-24 | 2013-01-25 | 2 days
7 | PM Email Update |  | Kevin | 2013-01-26 | 2013-01-26 | 1 day
8 | Wiki Update | Update Wiki | Kevin | 2013-01-26 | 2013-01-26 | 1 day
Milestone - User Test #1 Reached (03/02/2013)
Iteration 10 - User Test #1 (03/02/2013 - 16/02/2013)
1 | Project Management | Review Project Schedule | Kevin | 2013-02-03 | 2013-02-03 | 1 day
2 | Prepare Questionnaire | Prepare Questionnaire | Sherrie | 2013-02-03 | 2013-02-04 | 2 day
|  | Finalize Questionnaire | Sherrie | 2013-02-04 | 2013-02-04 | 1 day
|  | Invite Users | All | 2013-02-04 | 2013-02-04 | 1 day
3 | Build | Prepare Application | Development Team | 2013-02-05 | 2013-02-05 | 1 day
|  | Deploy Web Application to Staging | Development Team | 2013-02-06 | 2013-02-06 | 1 day
|  | Deploy Mobile Application | Development Team | 2013-02-06 | 2013-02-06 | 1 day
4 | Conduct User Test | Conduct User Test | All | 2013-02-06 | 2013-02-08 | 3 days
5 | Analyze Results | Analyze Results | Sherrie | 2013-02-09 | 2013-02-10 | 2 days
6 | Make Improvements | Determine Improvements to Make | All | 2013-02-10 | 2013-02-10 | 1 day
|  | Review Development Tasks | Development Team | 2013-02-10 | 2013-02-10 | 1 day
|  | Implement Improvements | Development Team | 2013-02-11 | 2013-02-12 | 2 day
7 | Buffer |  |  | 2013-02-13 | 2013-02-14 | 2 day
8 | PM Email Update |  | Kevin | 2013-02-15 | 2013-02-15 | 1 day
9 | Wiki Update | Update Wiki | Kevin | 2013-02-15 | 2013-02-15 | 1 day
Buffer (17/02/2013 - 23/02/2013)
Milestone - Mid Term Presentation
Iteration 11 (24/02/2013 - 09/03/2013)
1 | Project Management | Review Project Schedule | Kevin | 2013-02-24 | 2013-02-24 | 1 day
2 | Design | Review Use Case Scenarios | Kevin | 2013-02-24 | 2013-02-24 | 1 day
|  | Review Functionality List | Sherrie | 2013-02-24 | 2013-02-24 | 1 day
|  | Review User Interface | Waimun | 2013-02-24 | 2013-02-24 | 1 day
|  | Review Development Tasks | Boon Kheng | 2013-02-24 | 2013-02-24 | 1 day
|  | Script Test Cases | Jervenne | 2013-02-24 | 2013-02-24 | 1 day
3 | Build | Receiving Notification | Development Team | 2013-02-25 | 2013-02-26 | 2 day
|  | Viewing a Volunteer | Development Team | 2013-02-27 | 2013-02-28 | 2 day
|  | View Key Statistics about Business Performance | Development Team | 2013-02-27 | 2013-02-28 | 2 day
|  | Integration | Development Team | 2013-02-28 | 2013-03-01 | 1 day
4 | Test | Integration Testing | Sherrie | 2013-03-02 | 2013-03-02 | 1 day
|  | Fix Bugs | Development Team | 2013-03-03 | 2013-03-04 | 1 day
5 | Release | Deployment | Development Team | 2013-03-05 | 2013-03-05 | 1 day
6 | Buffer |  |  | 2013-03-06 | 2013-03-07 | 2 day
7 | PM Email Update |  | Kevin | 2013-03-08 | 2013-03-08 | 1 day
8 | Wiki Update | Update Wiki | Kevin | 2013-03-08 | 2013-03-08 | 1 day
Milestone - User Test #2 Reached
Iteration 12 (11/03/2013 - 24/03/2013)
1 | Project Management | Review Project Schedule | Kevin | 2013-03-11 | 2013-03-11 | 1 day
2 | Prepare Questionnaire | Prepare Questionnaire | Sherrie | 2013-03-11 | 2013-03-12 | 2 day
|  | Finalize Questionnaire | Sherrie | 2013-03-12 | 2013-03-12 | 1 day
|  | Invite Users | Waimun | 2013-03-12 | 2013-03-12 | 1 day
3 | Build | Prepare Application | Development Team | 2013-03-13 | 2013-03-13 | 1 day
|  | Deploy Web Application to Staging | Development Team | 2013-03-14 | 2013-03-14 | 1 day
|  | Deploy Mobile Application | Development Team | 2013-03-14 | 2013-03-14 | 1 day
4 | Conduct User Test | Conduct User Test | All | 2013-03-15 | 2013-03-18 | 3 days
5 | Analyze Results | Analyze Results | Sherrie | 2013-03-19 | 2013-03-20 | 2 days
6 | Make Improvements | Determine Improvements to Make | All | 2013-03-20 | 2013-03-20 | 1 day
|  | Review Development Tasks | Development Team | 2013-03-20 | 2013-03-20 | 1 day
|  | Implement Improvements | Development Team | 2013-03-20 | 2013-03-21 | 2 day
7 | Buffer |  |  | 2013-03-21 | 2013-03-22 | 2 day
8 | PM Email Update |  | Kevin | 2013-03-24 | 2013-03-24 | 1 day
9 | Wiki Update | Update Wiki | Kevin | 2013-03-24 | 2013-03-24 | 1 day
Milestone - User Acceptance Test
Iteration 13 (25/03/2013 - 07/04/2013)
1 | Project Management | Review Project Schedule | Kevin | 2013-03-25 | 2013-03-25 | 1 day
2 | Prepare Test | Prepare Scenarios | Sherrie | 2013-03-25 | 2013-03-25 | 1 day
|  | Prepare Test Plans | Jervenne | 2013-03-25 | 2013-03-25 | 1 day
3 | Build | Prepare Application | Development Team | 2013-03-26 | 2013-03-26 | 1 day
|  | Deploy Web Application to Staging | Development Team | 2013-04-26 | 2013-03-26 | 1 day
|  | Deploy Mobile Application | Development Team | 2013-03-26 | 2013-03-26 | 1 day
4 | Conduct User Test | Conduct User Acceptance Test (Volunteers) | All | 2013-03-27 | 2013-03-29 | 3 days
|  | Conduct User Acceptance Test (Empact Staff) | All | 2013-03-28 | 2013-03-28 | 1 day
|  | Conduct User Acceptance Test (NPO) | All | 2013-03-29 | 2013-03-29 | 1 day
5 | Analyze Results | Analyze Results | Sherrie | 2013-03-30 | 2013-03-30 | 1 day
6 | Make Improvements | Determine Fixes to Do | All | 2013-03-31 | 2013-03-31 | 1 day
|  | Determine Improvements to Do | All | 2013-03-31 | 2013-03-31 | 1 day
|  | Review Development Tasks | Development Team | 2013-03-31 | 2013-03-31 | 1 day
|  | Implement Improvements | Development Team | 2013-03-31 | 2013-04-02 | 1 day
7 | Buffer |  |  | 2013-04-02 | 2013-04-03 | 2 day
8 | PM Email Update |  | Kevin | 2013-04-04 | 2013-04-04 | 1 day
9 | Wiki Update | Update Wiki | Kevin | 2013-04-04 | 2013-04-04 | 1 day
Iteration 14 (08/04/2013 - 29/04/2013)
1 | Project Management | Review Project Schedule | Kevin
|  | Tidy Documentation | Kevin
|  | Package Code | Sherrie
|  | Script Deployment Test Cases | Jervenne
2 | Development Task | Review Development Tasks | Waimun
|  | Deploy to Live Server | Boon Kheng
| Handover | Pass Source Code and Documentation | Development Team
|  | Clean Up Wiki | Kevin
| Final Presentation | Prepare for Final Presentation | All
|  | Create Final Presentation Slides | Sherrie
|  | Final Presentation Rehearsal | All
|  | Final Presentation | All
| Poster Day | Poster Day Preparation | All
|  | Poster Day | All
Milestone - Final Presentation

## Milestones List
| Project Milestones | Date
1 | Proposal | 2012-10-26
2 | Acceptance Presentation | 2012-11-06
4 | Mid Term Presentation | 2013-02-18
6 | Final Presentation | 2013-04-15
7 | Poster Day | 2013-04-22
| Internal Milestones | Date
8 | User Test 1 | 2013-02-04
9 | User Test 2 | 2013-03-11
10 | User Acceptance Test | 2013-03-25

## Iteration 0
S
End of Iteration Report for Iteration 0 |  |  | KEY INDICATORS
SCHEDULE ESTIMATION |  | Actions To Be Taken
Iteration | 1 | Within the healthy range. No action needs to be taken. Task that overshot was assessing of risks
Total Days Planned | 13
Total Days Taken | 14
Schedule Ratio | 1.0769
Previous Ratio | N/A
BUG RATIO | Qty | Actions to Be Taken
Low Bugs | N/A
Medium Bugs | N/A
High Bugs | N/A
Total Score | N/A
MEMBER COMMITTMENTS
Member | Days Spent | Total Days Team Spent
Kevin | 9 | 34
Jenzus | 5 | 34
Sherrie | 5 | 34
Waimun | 5 | 34
Boon Kheng | 5 | 34
Jervenne | 5 | 34
COMMENTS ABOUT MEMBER'S COMMITTMENTS
Overall committment looks good. Maintain but review velocity of the team at critical junctures.
STORIES COMPLETED
- NIL -
ACTIONS TO BE TAKEN |  | ASSIGNED TO

## Iteration 1
S
End of Iteration Report for Iteration 1 |  |  | KEY INDICATORS
SCHEDULE ESTIMATION |  | Actions To Be Taken
Iteration | 2 | Within the healthy range. No action needs to be taken. Task that overshot was assessing of risks
Total Days Planned | 39.5
Total Days Taken | 40
Schedule Ratio | 1.0127
Previous Ratio | 1.0769
BUG RATIO | Qty | Actions to Be Taken
Low Bugs | N/A
Medium Bugs | N/A
High Bugs | N/A
Total Score | N/A
MEMBER COMMITTMENTS
Member | Days Spent | Total Days Team Spent
Kevin | 9 | 40
Jenzus | 5 | 40
Sherrie | 5 | 40
Waimun | 7 | 40
Boon Kheng | 5 | 40
Jervenne | 5 | 40
COMMENTS ABOUT MEMBER'S COMMITTMENTS
Overall committment looks good. Maintain but review velocity of the team at critical junctures.
STORIES COMPLETED
- NIL -
ACTIONS TO BE TAKEN |  | ASSIGNED TO

## Iteration 2
S
End of Iteration Report for Iteration 2 |  |  | KEY INDICATORS
SCHEDULE ESTIMATION |  | Actions To Be Taken
Iteration | 3 | Schedule ratio has increased, although it is still within healthy range. No action to be taken
Total Days Planned | 19
Total Days Taken | 21
Schedule Ratio | 1.1053
Previous Ratio | 1.0136
BUG RATIO | Qty | Actions to Be Taken
Low Bugs | N/A
Medium Bugs | N/A
High Bugs | N/A
Total Score | N/A
MEMBER COMMITTMENTS
Member | Days Spent | Total Days Team Spent
Kevin | 3 | 20
Jenzus | 3 | 20
Sherrie | 1 | 20
Waimun | 2 | 20
Boon Kheng | 6 | 20
Jervenne | 5 | 20
COMMENTS ABOUT MEMBER'S COMMITTMENTS
Overall committment looks good. Maintain but review velocity of the team at critical junctures.
STORIES COMPLETED
- NIL -
ACTIONS TO BE TAKEN |  | ASSIGNED TO

## Iteration 3 (Acceptance)
S
Mid Iteration Report for Iteration 3 |  |  | KEY INDICATORS
SCHEDULE ESTIMATION |  | Actions To Be Taken
Iteration | 3 | Schedule ratio has increased, although it is still within healthy range. No action to be taken
Total Days Planned | 18
Total Days Taken | 19
Schedule Ratio | 1.0556
Previous Ratio | 1.105
BUG RATIO | Qty | Actions to Be Taken
Low Bugs | N/A
Medium Bugs | N/A
High Bugs | N/A
Total Score | N/A
MEMBER COMMITTMENTS
Member | Days Spent | Total Days Team Spent
Kevin | 4 | 20
Jenzus | 4 | 20
Sherrie | 2 | 20
Waimun | 2 | 20
Boon Kheng | 5 | 20
Jervenne | 3 | 20
COMMENTS ABOUT MEMBER'S COMMITTMENTS
Overall committment looks good. Be careful of Boon Kheng's commitment. It seems to be scaling, although it is natural for him to be more taxed as this phase is about coming up with the system design
STORIES COMPLETED
- NIL -
ACTIONS TO BE TAKEN |  | ASSIGNED TO

## Iteration 3
S
Iteration Report for Iteration 3 |  |  | KEY INDICATORS
SCHEDULE ESTIMATION |  | Actions To Be Taken
Iteration | 3 | Schedule ratio is still within healthy range. Event that overshot was due to unforeseen difficult in getting mobile prototype up and working. More time would be catered for mobile development in the future
Total Days Planned | 22
Total Days Taken | 24
Schedule Ratio | 1.0909
Previous Ratio | 1.05
BUG RATIO | Qty | Actions to Be Taken
Low Bugs | N/A
Medium Bugs | N/A
High Bugs | N/A
Total Score | N/A
MEMBER COMMITTMENTS
Member | Days Spent | Total Days Team Spent
Kevin | 7 | 30
Jenzus | 5 | 30
Sherrie | 3 | 30
Waimun | 3 | 30
Boon Kheng | 8 | 30
Jervenne | 4 | 30
COMMENTS ABOUT MEMBER'S COMMITTMENTS
For next iteration, to be aware of Boon Kheng's committment. He seems to be consistently overtaxed
STORIES COMPLETED
- NIL -
ACTIONS TO BE TAKEN |  | ASSIGNED TO
Acceptance Review delayed |  | Assign time in Iter 4
Wiki not updated |  | To update immediately after Acceptance Review

## _Technology Analysis (hidden)
Web or Native App Developement? | [5 empty] | Web or Native App Developement?
Options | Native App (e.g. Appcelerator) |  | Web App (e.g. Sencha) |  | Hybrid Apps (e.g. Sencha + PhoneGap)
| Pros | Cons | Pros | Cons | Pros | Cons
Platform In/dependence | (Multi-platform only after dev and deployment via Appcelerator) | Single platform. written in Objective C and runs only on iOS. Not portable to other platforms | Runs on web browsers; multi-platform. | While multi-platform, web apps may not be interpreted in the same manner by some browsers and in some cases, may not be interpreted at all. (Safari should be fine) | Multi-platform.
User-end Usage |  | This means that the app, and any updates, must be installed by the user via Apple’s App Store distribution and approval process. | Does not require installation. Any user interaction with Apple’s App Store is unnecessary, although, the option of packaging the application for distribution by the App Store is available thru the Hybrid option: PhoneGap *Additionally, users can install a web app, adding it to their home screen with an icon and splash screens just like a native app. *Web apps can be cached on the iPhone for offline use when a wifi or 3G connection is not available. |  |  | Like native apps, these applications must be distributed through the respective App Stores. Apple, Google Android, Windows Mobile etc.
Native Hardware Access | Access to native hardware features such as the camera, accelerometer, and compass, GPS position change, audio playback and capture, etc. |  |  | Minimal, but is slowly being opened up. On the iPhone, web apps can get the user’s current location from the GPS. Only option is via Hybrid (PhoneGap) | “wraps” the web app with a native app to gain access to more native features.
Access to features | Access to iPhone resources like contacts, calendar events, and photos. |  | Nil. (only via Hybrid option) |  | Yes, like Native
User Interface + User Experience | Allows developers to design complex UIs and richer user experiences |  | New Javascript frameworks make it easy to create near-native UI for web apps. Sencha Touch aids in building applications for iOS and Android phones and tablets. It offers design of a rich user experience, but is more difficult to learn than some simpler JavaScript frameworks such as jQTouch. jQTouch is the better option when emphasis is on the development of web content. |  | Probably not as good as Native option, but will be comparative.
Storage | Large storage |  | Can also store local data, even a client-side database on the mobile device. |  | Large
Performance | Fast |  |  | Poor to Average |  | Unclear - requires industry testing.
Development Difficulty | challenging. the learning curve can be steep, depending on your background (side note: will have to deal with memory management, pointers, and lots of delegate pattern use) ZM: The deployment for appcelerator is easier also, all done within the IDE without worrying about wrapping it up with phonegap |  | Easier to learn; Simpler to code |  | Average to Simple
Developers' Support | Well documented framework with lots of example code |  |  | Average |  | Average
Technologies | - Objective-C (iPhone) - Objective-C + web technology extensions like HTML5, CSS3, JavaScript (Appcelerator) - Java (Android) |  | - Sencha |  | - Sencha + PhoneGap PhoneGap is the leading framework for hybridization, with wrappers for multiple platforms, so the same core web app can be turned into a native iPhone, Android, BlackBerry, WebOS, or Symbian app.
Paid / Open Source | **Appcelerator - open source! | Usually Paid e.g. iOS | Usually Open Source |  | Usually Open Source
| Reasons to choose Native: |  | Reasons to choose Web: |  | Reasons to choose Hybrid:
| application is complex in that it contains many screens or steps, such as a game or complex animation |  | Coss-platform; when portability IS crucial. Users can easily access web app from different types of mobile devices |  | When the developer is used to writing web apps, yet wants to develop a standard app with a native UI
| lots of data must be stored on the phone |  | When only small amounts of on-phone data is required. |  | Looking to save time over learning Objective C (the iOS option)
| processing speed is a crucial |  | When speed is NOT crucial
| application requires access to hardware features, for example knowing how the device is tilted; this info cannot be attained through a web application. |  | When hardware features are not required, except for, perhaps, a simple GPS
it's impt to note that choosing Appcelerator means that we're picking the *native* route, where the learning curve is much steeper. The only difference between traditional iPhone-apps development AND Appcelerator, is that the latter provides greater extensibility. It includes Titanium modules that supports HTML5 and CSS3, Social Networking capabilities etc, as stated on this page http://www.appcelerator.com/products/native-iphone-android-development/

## _Research Log (hidden)
Research Log
Date | Jon | ZM | Wil | JW
April
2011-04-23 | Wallaby is a preview of an experimental technology that enables us to covert some of their FLA files to HTML. allows us to reuse or extend the reach of our content to devices that do not support the Flash runtimes. Once these files are converted to HTML, can edit using HTML editor, include Notepad++. Output can be viewed on supported browsers or on an iOS device. | did some research on sencha, basically it's a mobile framework to develop apps. i downloaded the sencha touch but it requires me to unzip in our web server, can't do it now. basically there are commerical tools (those that we have to buy) out there that offers conversion of .swf files to something compatible with iOS, like converting it to .mp4 formats. but i think we need to figure out how to do that. as of now, i haven't found anything about sencha being able to convert .swf files. "One of the most positive things about Sencha Animator is that, since it works with CSS3, the animation will be able to be seen on portable devices that don't support Flash, like the iPhone or the iPad." i dont think this is what stanchart wants because we'll have to code our own learning modules | Found existing learning management platforms that have mobile apps like BlackBoard Mobile This means that along with the mobile devices are able to access the BB portal wherever they are BB's by far the largest company. Then we also have Schoology, who do a digital classroom. Not quite what we're looking for but it does combine social networking with learning management My feel is that these are large commercial packages which will cost a lot to implement. Will look at trials for Schoology since they have one
2011-04-26 | - Installed Wallaby. Key Findings: (1) Takes in .FLA files as input, throws out html5 as output. (2) Able to convert graphical content like complex, timeline-based animation into HTML5 (3) Currently does not support conversion of Flash Professional features like ActionScript, Movies, and Sound (4) Wallaby HTML5 output uses Webkit specific CSS3 tags. Therefore it is only compatible with Safari and Google Chrome. Firefox and IE are NOT Webkit browsers. (*note: Webkit is a layout engine that powers Safari and Chrome. reference: http://en.wikipedia.org/wiki/WebKit) (5) Output from Wallaby is not in a format that is ready for deployment to web pages. That is not the goal of the Wallaby tool. It's goal is to extract content from .FLA, which can then be imported into other web pages in development. -> Documentation states that import can be done via web design tools like Dreamweaver. Assuming we're Notepad++, I'm not sure if that's possible. Got to try to find out more. | Remarks (Jon): Well we can confirm for now, that Sencha does no conversion of any sort. So you don't have to continue researching on what you mentioned in your first para. I confirm that Wallaby is a definite solution to converting .FLA to HTML5 (in other words, obtain the e-Learning materials). The question is can we use Sencha? I'm curious to know if this is a viable alternative to Apple for developing the application for SCB (StanCartBank). If so, we don't have to go through the trouble of installing Apple (VMware) on our computers. | Remarks (Jon): Do find out if Schoology is flexible enough for integration with external systems. Essentially, SCB employees will be doing the e-Learning modules, with their scores submitted to the SCB's internal servers. If Schoology doesn't allow that, it is unlikely that they will accept Schoology as a platform to host their e-Learning modules. Now this is not even considering that Schoology is a third-party application/platform, of which may be enough for SCB to reject it entirely. We need more info Wil. :)
May
2011-05-03 |  |  | Dug more into Schoology and it's quite 'academic' Touting itself to be close to Gmail and Facebook. Watched the demo video which further reaffirms that face It's got grades and what not but doesn't seem to be able to integrate with something existing. It merely tracks
2011-05-06 | Wallaby is unable to accept files in the .swf format. It only accepts files in the .fla format as input. refer to https://picasaweb.google.com/104979840933648817463/FYPScreenshots?locked=true#5603599483719841698 The FLA file format is the “master” document format for Flash projects created in authoring tools like Adobe Flash Professional CS5. The contents of an FLA file is ‘uncomplied’, ‘uncompressed’, and not executable/playable. This is very different from the SWF file format. In comparison, the SWF is compiled from the FLA project, compressed, and playable via the Flash Player. Here’s an analogy: the .java is created via authoring IDEs, while the .class is compiled/generated from the .java file, and is executable. Tried to convert .fla of that sample project i downloaded. failed with errors too. refer to https://picasaweb.google.com/104979840933648817463/FYPScreenshots?locked=true#5603599948584178466 will need to continue looking for a more suitable .fla project to convert.
2011-05-08 | Research on Titanium (http://www.appcelerator.com/products/titanium-cross-platform-application-development/) Key Findings: (1) Similar technologies employed - HTML5, CSS3, JavaScript to build the core application logic and UI (2) Entails APIs that accesses native device functionalities, similar to PhoneGap :) (3) Run-time shell packages the application for cross-platform distribution -> Platform Independent - but appears to be only available for iPhone and Android phones. (4) deploys through the cloud (5) open sourceSeems pretty good. Titanium Mobile encapsulates everything.. Sencha requires the PhoneGap add-on.. Both are more or less the same, but Titanium seems to have stronger support due to the wider developer community. I'm withholding my vote till Sunday. | Appcelerator - i seem to be bought over by it haha. | Appcelerator and the Native Advantage - over 300 APIs - Native UI possible - Readily available dev tools Personal thoughts: the more I read from both your research and mine, the more I'm leaning toward Appcelerator. Learning curve will still be there as with everything but it seems more established.
| Remark: Yes, Appcelerator bao ka liao.. so it's much easier. | uses javascript and other web technologies like html 5, php, python etc. to help develop app. seems pretty managable and niffty. The deployment for appcelerator is easier also, all done within the IDE without worrying about wrapping it up with phonegap | These will add to our learning curve along with Obj-C
| Remark: Correct. Appcelerator is essentially building the app through the native route, that's why we require the iOS SDK, and be programming in Objective-C. as mentioned above, run-time shell packages the application for cross-platform distribution. | The free open source compiler available for download does not support cross platform. Only when deployed onto the server does Appcelerator makes it platform independent. PhoneGap is more platform independent as compared to appcelerator. however not a major concern since Stanchart wanted iOS only.
|  | For mobile compilation we will require Mac OS X and iPhone SDK. I login with password which LC gave us earlier and tried downloading the sdk into my comp but can't. If we use Appcelerator, this is a obstacle for us. if we can get the vmware, should be fine. | Will be getting VM from Patrick tmr. - Need the go ahead to use from LC after understanding that it's actually illegal
| Remark: Not so sure about that.. I think learning curve for Appcelerator is steeper than PhoneGap. Appcelerator is essentially programming via the traditional Objective-C route, which gives access to native features.. PhoneGap provides a set of high-level APIs to help us make accessing of native features easier. | Appcelerator has better user documentations and API, learning curve may not be as steep as PhoneGap with limited API. included a useful link for the comparison between appcelerator and phonegap. | I do feel better about support from the open source community. And like ZM said, there's more documentation
2011-05-08 | Added remarks to your research.. scroll down and look under the archive section. I've also found a VERY USEFUL article (through your article ZM), with comprehensive analysis of choosing between Native or Web for app developement. http://monolithinteractive.com/2011/02/04/web-or-native/ The info there + your research are place in the new tab: *impt* Technology Analysis. Information is organized into that format so that it can be used to present to Lian Chee + SCB.. perhaps also for use in the FYP proposal.
Read the new tab first before this conclusion: it's impt to note that choosing Appcelerator means that we're picking the *native* route, where the learning curve is much steeper. The only difference between traditional iPhone-apps development AND Appcelerator, is that the latter provides greater extensibility. It includes Titanium modules that supports HTML5 and CSS3, Social Networking capabilities etc, as stated on this page http://www.appcelerator.com/products/native-iphone-android-development/

## _Useful Links (hidden)
Useful Links
Desc | Link | Remarks
IS480 Page | http://blue.smu.edu.sg/IS480/2010-2011/IS480/Schedule.html
Wallaby | http://labs.adobe.com/technologies/wallaby/
wiki | http://labs.adobe.com/wiki/index.php/Main_Page
Video Tutorials | http://labs.adobe.com/wiki/index.php/Wallaby:Technical_Tips
Forums | http://forums.adobe.com/community/labs/wallaby/
Appcelerator | http://www.appcelerator.com/products/titanium-cross-platform-application-development/
good info | http://www.appcelerator.com/products/native-iphone-android-development/
Titanium API | http://wiki.appcelerator.org/display/guides/Getting+Started+with+Titanium
Titanium Zero-to-App | http://training.appcelerator.com/zero-to-app
| http://www.appcelerator.com/showcase/videos/titanium-for-new-developers/ | Titanium for new Developers Webinar (on-demand)
Would you consider Sencha? | http://developer.appcelerator.com/question/35691/would-you-consider-sencha | Question posed by Appcelerator Dev
Web or Native? | http://monolithinteractive.com/2011/02/04/web-or-native/ | Very good comprehensive article.
Sencha Touch | http://www.sencha.com/products/touch/
Sencha demos | http://www.sencha.com/products/touch/demos/
VERY USEFUL | http://dev.sencha.com/deploy/touch/examples/
Getting Started | http://dev.sencha.com/deploy/touch/getting-started.html
PhoneGap | http://www.phonegap.com/
iOS Appstore greenlight | http://blogs.nitobi.com/jesse/2009/11/20/phonegapp-store-approval/
Titanium & Phonegap comparison | http://savagelook.com/blog/portfolio/a-deeper-look-at-appcelerator-and-phonegap
Archived
LMS | http://www.learningsolutionsmag.com/articles/496/apples-ios-4-ready-for-the-enterprise-but-what-about-e-learning
BlackBoard Mobile | http://www.blackboard.com/Platforms/Mobile/Overview.aspx