## Schedule (Planned)
SPRINT NO | Task ID |  | Module | DESCRIPTION | ESTIMATED TIME TAKEN | HOURS SPENT ACTUAL | STORY POINTS | TAKEN BY
1 | 1 |  | - | Finalize Project Scope | 2 | 1.5 | 2
1 | 2 |  |  | Use Case Diagram | 2 | 2 | 2
1 | 3 |  |  | ER Diagram | 2 | 3 | 2
1 | 4 |  |  | As-Is Diagram | 0.5 | 0.5 | 0.5
1 | 5 |  |  | To-Be Diagram | 1 | 1.5 | 1
1 | 6 |  |  | Navigation Diagram - Web App | 3.5 | 5 | 3.5
1 | 7 |  |  | Navigation Diagram - Mobile App | 4 | 3.5 | 4
1 | 8 |  |  | Lo-Fi Wireframing - Admin Web App | 5 | 6 | 5
1 | 9 |  |  | Lo-Fi Wireframing - Mobile App | 6 | 6 | 6
1 | 10 |  |  | Technical Research-React Native | 3 | 5 | 3
1 | 11 |  |  | Technical Research-Nodejs | 3 | 4 | 3
2 | 1 | Web App | Web Admin Module (Backend) | WebApp - Login/Logout | 2 | 4 | 2
2 | 2 |  |  | WebApp - Change Password | 1 | 1 | 1
2 | 3 |  | Web Admin Module (Frontend) | WebApp - Login/Logout | 2 | 4 | 2
2 | 4 |  |  | WebApp - Change Password | 1 | 1 | 1
2 | 5 | Nodejs | App Account Module (Backend) | MobileApp - Login | 4 | 4 | 4
2 | 6 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3
2 | 7 | Android | App Account Module (Frontend) | MobileApp - Login | 4 | 4 | 4
2 | 8 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3
2 | 9 |  | - | Scenario | 1 | 0.5 | 1
2 | 10 |  |  | Persona | 1 | 0.5 | 1
2 | 11 |  |  | Git and Viroreact set-up | 0.5 | 0.5 | 0.5
2 | 12 |  |  | Proposal Preparation | 2 | 2 | 2
3 | 1 | Nodejs | App Account Module (Backend) | MobileApp - Connect to Trail | 0.5 | 0.5 | 0.5
3 | 2 |  |  | MobileApp - View Narrative | 1 | 0.75 | 1
3 | 3 |  |  | MobileApp - Complete Missions(Quiz, Wefie) | 2 | 3 | 2
3 | 4 |  |  | MobileApp -View Past Submissions | 4 | 5 | 4
3 | 5 |  |  | MobileApp - Upload Submissions | 1 | 2.5 | 1
3 | 6 |  |  | MobileApp - View map with pinned location(with location tracking) | 3.5 | 3 | 3.5
3 | 7 | Android | App Account Module (Frontend) | MobileApp -Connect to Trail | 1 | 0.5 | 1
3 | 8 |  |  | MobileApp - View Narrative | 0.5 | 0.5 | 0.5
3 | 9 |  |  | MobileApp - Complete Missions(Quiz, Wefie) | 2 | 3 | 2
3 | 10 |  |  | MobileApp - View Past Submissions | 4 | 3 | 4
3 | 11 |  |  | MobileApp - Upload Submissions | 3 | 2 | 3
3 | 12 |  |  | MobileApp -View map with pinned location(with location tracking) | 2 | 1 | 2
3 | 13 |  | - | MobileApp - Sequence Diagrams | 0.5 | 0.5 | 0.5
3 | 14 |  |  | WebApp - Sequence Diagram | 1 | 1 | 1
3 | 15 |  |  | User Testing Preparation | 1.5 | 2 | 1.5
3 | 16 |  |  | Acceptance Preparation | 3 | 3 | 3
B
4 | 1 | WebApp | Admin Trail Monitoring Module (Backend) | WebApp - Monitor Groups' Progress | 0.5 | 0 | 0.5
4 | 2 |  |  | WebApp - Monitor Groups' Location | 2 | 0 | 2
4 | 3 |  |  | WebApp - Monitor and manage Leaderboard | 0.5 | 0.5 | 0.5
4 | 4 |  |  | WebApp - Monitor and manage Activity Feed | 1.5 | 0 | 1.5
4 | 5 |  |  | WebApp - Monitor and manage Mission Submission | 1 | 1 | 1
4 | 6 |  |  | WebApp - Monitor Trail Duration | 1.5 | 1.5 | 1.5
4 | 7 |  | Admin Upload Module Backend | WebApp - Upload Multimedia (Images and Videos) | 2.5 | 2.5 | 2.5
4 | 8 |  |  | WebApp - View Uploads | 2 | 2 | 2
4 | 9 |  | Admin Trail Monitoring Module Frontend | WebApp - Monitor Groups' Progress | 1 | 0 | 1
4 | 10 |  |  | WebApp - Monitor Groups' Location | 2.5 | 0 | 2.5
4 | 11 |  |  | WebApp - Monitor and manage Leaderboard | 1 | 1 | 1
4 | 12 |  |  | WebApp - Monitor and manage Activity Feed | 1 | 0 | 1
4 | 13 |  |  | WebApp - Monitor and manage Mission Submission | 1.5 | 1.5 | 1.5
4 | 14 |  |  | WebApp - Monitor Trail Duration | 1 | 1 | 1
4 | 15 |  | Admin Upload Module Frontend | WebApp - Upload Multimedia (Images and Videos) | 0.5 | 0.5 | 0.5
4 | 16 |  |  | WebApp - View Uploads | 1.5 | 1.5 | 1.5
4 | 17 | Android | User Trail Module (Frontend) | MobileApp - View Activity Feed | 1.5 | 1.5 | 1.5
4 | 18 |  |  | MobileApp - View Leaderboard | 1 | 1 | 1
4 | 19 |  | User Trail Module (Backend) | MobileApp - View Activity Feed | 2 | 2 | 2
4 | 20 |  |  | MobileApp - View Leaderboard | 1 | 1 | 1
5 | 7 |  | Hotspot Module (Backend) | WebApp - Add/Edit/Remove Hotspot Location | 0.5 | 0.5 | 0.5
5 | 8 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 0.5 | 0.5 | 0.5
5 | 9 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 0.5 | 0.5 | 0.5
5 | 10 |  | Hotspot Module (Frontend) | WebApp - Add/Edit/Remove Hotspot Location | 1 | 1 | 1
5 | 11 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 1 | 1 | 1
5 | 12 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 1.5 | 1.5 | 1.5
5 | 13 | IOS | App Account Module (Backend) | MobileApp - Login | 4 | 4 | 4
5 | 14 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3
5 | 15 |  | App Account Module (Frontend) | MobileApp - Login | 4 | 4 | 4
5 | 16 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3
6 | 7 |  | Narrative Module (Backend) | WebApp - Add/Edit/Remove Text/Story | 1.25 | 1.25 | 1.25
6 | 8 |  |  | WebApp - Attach photos or videos to Narrative | 2 | 2 | 2
6 | 9 |  | Narrative Module (Frontend) | WebApp - Add/Edit/Remove Text/Story | 1 | 1 | 1
6 | 10 |  |  | WebApp - Attach photos or videos to Narrative | 2.5 | 2.5 | 2.5
6 | 11 | Nodejs | Complete Mission Module (Backend) | MobileApp - Drag and Drop | 2 | 2 | 2
6 | 12 |  |  | MobileApp - CrossWord | 1.5 | 1.5 | 1.5
6 | 13 | Android | Complete Mission Module (Frontend) | MobileApp - Drag and Drop | 1 | 1 | 1
6 | 14 |  |  | MobileApp - CrossWord | 2.5 | 2.5 | 2.5
6 | 15 | IOS | User Trail Module (Backend) | Connect to Trail | 0.5 | 0.5 | 0.5
6 | 16 |  |  | View Narrative | 2 | 2 | 2
6 | 17 |  |  | Complete Missions(Quiz, Wefie) | 0.5 | 0.5 | 0.5
6 | 18 |  |  | View Past Submissions | 1.5 | 1.5 | 1.5
6 | 19 |  |  | Upload Submissions | 1 | 1 | 1
6 | 20 |  |  | View map with pinned location(with location tracking) | 1.5 | 1.5 | 1.5
6 | 21 |  | User Trail Module (Frontend) | Connect to Trail | 1 | 1 | 1
6 | 22 |  |  | View Narrative | 2.5 | 2.5 | 2.5
6 | 23 |  |  | Complete Missions(Quiz, Wefie) | 1 | 1 | 1
6 | 24 |  |  | View Past Submissions | 1 |  | 1
6 | 25 |  |  | Upload Submissions | 1.5 | 1.5 | 1.5
6 | 26 |  |  | View map with pinned location(with location tracking) | 1 | 1 | 1
7 | 7 |  | Mission Module (Backend) | WebApp - Add/Edit/Remove mission description | 1 | 1 | 1
7 | 8 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 | 2 | 2
7 | 9 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission description | 1.5 |  | 1.5
7 | 10 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 |  | 2
7 | 12 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 0.5 | 0.5 | 0.5
7 | 13 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 0.5 | 0.5 | 0.5
7 | 14 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 0.5 | 0.5 | 0.5
7 | 16 |  |  | WebApp - Add/Edit/Remove Groups | 0.5 | 0.5 | 0.5
7 | 18 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 1 |  | 1
7 | 19 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 1 |  | 1
7 | 20 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 1 |  | 1
7 | 22 |  |  | WebApp - Add/Edit/Remove Groups | 1 |  | 1
7 | 23 | Nodejs | Mission Module (Backend) | MobileApp - Complete missions - Word Search - Anagram - Drawing | 2.5 | 2.5 | 2.5
7 | 24 | Android | Mission Module (Frontend) | MobileApp - Complete missions - Word Search - Anagram - Drawing | 2 |  | 2
7 | 25 | IOS | User Trail Module (Backend) | View Activity Feed | 1.5 |  | 1.5
7 | 26 |  |  | View Leaderboard | 1 | 1 | 1
7 | 27 |  | User Trail Module (Frontend) | View Activity Feed | 2 |  | 2
7 | 28 |  |  | View Leaderboard | 1 | 1 | 1
7 | 29 | Others | - | User Testing Preparation
8 | 11 | Android | Complete Mission Module (Backend) | MobileApp - Complete missions - Anagram - Drawing | 2 | 2 | 2
8 | 12 |  | Complete Mission Module (Frontend) | MobileApp - Complete missions - Anagram - Drawing | 2 | 2 | 2
9 | 5 |  | Mission Module (Backend) | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 | 2 | 2
9 | 6 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 | 0 | 2
9 | 7 |  | Admin Trail Creation Module (Backend) | WebApp - Add/Edit/Remove Mission to trail map | 1 | 1 | 1
9 | 8 |  |  | WebApp - Add/Edit/Remove Participants | 1 | 1 | 1
9 | 9 |  |  | WebApp - Add/Edit/Remove Groups | 1 | 1 | 1
9 | 13 | Android | Mission Module (Backend) | MobileApp - Complete missions - Word Search | 2 | 2 | 2
9 | 14 |  | Mission Module (Frontend) | MobileApp - Complete missions - Word Search | 2 | 2 | 2
9 | 15 | IOS | User Trail Module (Back end) | View Activity Feed | 1 | 1 | 1
9 | 16 |  | User Trail Module (Frontend) | View Activity Feed | 1 | 1 | 1
9 | 17 |  | Complete Mission Module (Backend) | MobileApp - Complete missions - Drag & Drop - Anagram | 3 | 3 | 3
9 | 18 |  | Complete Mission Module (Frontend) | MobileApp - Complete missions - Drag & Drop - Anagram | 2 | 2 | 2
10 | 1 | Web App** | Admin Trail Monitoring Module (Front end) | WebApp - Monitor Groups' Location | 1 | 1 | 1
10 | 2 |  |  | WebApp - Monitor Trail Duration | 1 | 1 | 1
10 | 5 |  | Mission Module (Backend) | WebApp - Add/Edit/Remove mission type: - Drag & Drop | 2 | 2 | 2
10 | 6 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission type: - Drag & Drop | 2 | 2 | 2
10 | 7 |  | Admin Trail Creation Module (Frontend) | WebApp - Add/Edit/Remove Mission to trail map | 1 | 1 | 1
10 | 8 |  |  | WebApp - Add/Edit/Remove Participants | 1 | 1 | 1
10 | 9 |  |  | WebApp - Add/Edit/Remove Groups | 1 | 1 | 1
10 | 10 | Android | Notification Module (Backend) | MobileApp - View Notification | 2 | 2 | 2
10 | 11 |  |  | MobileApp - Receive Notification | 1.5 | 1.5 | 1.5
10 | 12 |  | Notification Module (Frontend) | MobileApp - View Notification | 1.5 | 1.5 | 1.5
10 | 13 |  |  | MobileApp - Receive Notification | 2 | 2 | 2
10 | 14 |  | Deployment | Prep for deployment
10 | 15 | IOS | Complete Mission Module (Backend) | MobileApp - Complete missions - Word Search - Drawing | 2 | 2 | 2
10 | 16 |  | Complete Mission Module (Frontend) | MobileApp - Complete missions - Word Search - Drawing | 2 | 2 | 2
10 | 17 |  | Deployment | Prep for deployment
|  |  | Admin Trail Monitoring Module (Back end) | WebApp - Monitor and Manage Activity Feed | 2 | 2 | 2
|  |  | Admin Trail Monitoring Module (Front end) | WebApp - Monitor and Manage Activity Feed | 1.5 | 1.5 | 1.5
11 | 1 | Web App | Notification Module (Backend) | WebApp - Announcer Feature | 2.5 | 2.5 | 2.5
11 | 2 |  |  | WebApp - Reminder Feature | 2 | 2 | 2
11 | 3 |  | Mission Module (Backend) | WebApp - Add/Edit/Delete missions - Word Search - Anagram - Drawing - Crossword | 1 | 1 | 1
11 | 4 |  | Mission Module (Frontend) | WebApp - Add/Edit/Delete missions - Word Search - Anagram - Drawing - Crossword | 1 | 1 | 1
11 | 5 |  | Notification Module (Frontend) | WebApp - Announcer Feature | 1 | 1 | 1
11 | 6 |  |  | WebApp - Reminder Feature | 1 | 1 | 1
| 11 | Android | Usability Module (Backend) | MobileApp - User Help Page | 3 | 3 | 3
11 | 12 |  | Usability Module (Frontend) | MobileApp - User Help Page | 3 | 3 | 3
11 | 13 | IOS | Notification Module (Backend) | MobileApp - View Notification | 1.5 | 1.5 | 1.5
11 | 14 |  |  | MobileApp - Receive Notification | 2 | 2 | 2
11 | 16 |  | Usability Module (Backend) | MobileApp - User Help Page | 3 | 3 | 3
11 | 17 |  | Notification Module (Frontend) | MobileApp - View Notification
11 | 18 |  |  | MobileApp - Receive Notification | 2 | 2 | 2
11 | 20 |  | Usability Module (Frontend) | MobileApp - User Help Page | 3 | 3 | 3
11 | 21 | Others | - | USER TESTING PREPARATION
11 | 22 | Others | - | MID TERM PREPARATION
11 | 23 | Others | - | LIVE TRAIL PREPARATION
11 | 24 | Others | - | SPONSOR UAT
12 | 1 | Web App | Usability Module (Backend) | WebApp - Admin Help Page | 3 | 3 | 3
12 | 2 |  | Usability Module (Frontend) | WebApp - Admin Help Page | 3 | 3 | 3
12 | 3 | Others | - | UI/UX IMPROVEMENTS
12 | 4 | Others | - | LIVE TRAIL PREPARATION
12 | 5 | Others | - | OPTIMIZATION
12 | 6 | Others | - | DOCUMENTATION
13 | 5 | Web App | Data Analytcis (Back end) | WebApp - Record Trail Data | 3 | 3 | 3
13 | 6 |  |  | WebApp - Display Summary Report of Past Data | 2 | 2 | 2
13 | 7 |  | Data Analytcis (Front end) | WebApp - Record Trail Data | 4 | 4 | 4
13 | 8 |  |  | WebApp - Display Summary Report of Past Data | 3 | 3 | 3
13 | 9 | Others | - | UI/UX IMPROVEMENTS
13 | 10 | Others | - | POSTER PREPARATION
14 | 1 | Others | - | UI Improvement (Webapp, MobileApp)
14 | 2 | Others | - | FINAL PRESENTATION PREPARATION
14 | 3 | Others | - | SPONSOR UAT 2
15 | 1 |  | - | Preparation for Final Presentation

## Schedule (New)
SPRINT NO | Task ID |  | Module | DESCRIPTION | ESTIMATED TIME TAKEN | HOURS SPENT ACTUAL | STORY POINTS | STATUS | TAKEN BY
1 | 1 |  | - | Finalize Project Scope | 2 | 1.5 | 2 | Completed
1 | 2 |  |  | Use Case Diagram | 2 | 2 | 2 | Completed
1 | 3 |  |  | ER Diagram | 2 | 3 | 2 | Completed
1 | 4 |  |  | As-Is Diagram | 0.5 | 0.5 | 0.5 | Completed
1 | 5 |  |  | To-Be Diagram | 1 | 1.5 | 1 | Completed
1 | 6 |  |  | Navigation Diagram - Web App | 3.5 | 5 | 3.5 | Completed
1 | 7 |  |  | Navigation Diagram - Mobile App | 4 | 3.5 | 4 | Completed
1 | 8 |  |  | Lo-Fi Wireframing - Admin Web App | 5 | 6 | 5 | Completed
1 | 9 |  |  | Lo-Fi Wireframing - Mobile App | 6 | 6 | 6 | Completed
1 | 10 |  |  | Technical Research-React Native | 3 | 5 | 3 | Completed
1 | 11 |  |  | Technical Research-Nodejs | 3 | 4 | 3 | Completed
2 | 1 | Web App | Web Admin Module (Backend) | WebApp - Login/Logout | 2 | 4 | 2 | Completed
2 | 2 |  |  | WebApp - Change Password | 1 | 1 | 1 | Completed
2 | 3 |  | Web Admin Module (Frontend) | WebApp - Login/Logout | 2 | 4 | 2 | Completed
2 | 4 |  |  | WebApp - Change Password | 1 | 1 | 1 | Completed
2 | 5 | Nodejs | App Account Module (Backend) | MobileApp - Login | 4 | 4 | 4 | Completed
2 | 6 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3 | Completed
2 | 7 | Android | App Account Module (Frontend) | MobileApp - Login | 4 | 4 | 4 | Completed
2 | 8 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3 | Completed
2 | 9 |  | - | Scenario | 1 | 0.5 | 1 | Completed
2 | 10 |  |  | Persona | 1 | 0.5 | 1 | Completed
2 | 11 |  |  | Git and Viroreact set-up | 0.5 | 0.5 | 0.5 | Completed
2 | 12 |  |  | Proposal Preparation | 2 | 2 | 2 | Completed
3 | 1 | Nodejs | App Account Module (Backend) | MobileApp - Connect to Trail | 0.5 | 0.5 | 0.5 | Completed
3 | 2 |  |  | MobileApp - View Narrative | 1 | 0.75 | 1 | Completed
3 | 3 |  |  | MobileApp - Complete Missions(Quiz, Wefie) | 2 | 3 | 2 | Completed
3 | 4 |  |  | MobileApp -View Past Submissions | 4 | 5 | 4 | Completed
3 | 5 |  |  | MobileApp - Upload Submissions | 1 | 2.5 | 1 | Completed
3 | 6 |  |  | MobileApp - View map with pinned location(with location tracking) | 3.5 | 3 | 3.5 | Completed
3 | 7 | Android | App Account Module (Frontend) | MobileApp -Connect to Trail | 1 | 0.5 | 1 | Completed
3 | 8 |  |  | MobileApp - View Narrative | 0.5 | 0.5 | 0.5 | Completed
3 | 9 |  |  | MobileApp - Complete Missions(Quiz, Wefie) | 2 | 3 | 2 | Completed
3 | 10 |  |  | MobileApp - View Past Submissions | 4 | 3 | 4 | Completed
3 | 11 |  |  | MobileApp - Upload Submissions | 3 | 2 | 3 | Completed
3 | 12 |  |  | MobileApp -View map with pinned location(with location tracking) | 2 | 1 | 2 | Completed
3 | 13 |  | - | MobileApp - Sequence Diagrams | 0.5 | 0.5 | 0.5 | Completed
3 | 14 |  |  | WebApp - Sequence Diagram | 1 | 1 | 1 | To Be Done
3 | 15 |  |  | User Testing Preparation | 1.5 | 2 | 1.5 | Completed
3 | 16 |  |  | Acceptance Preparation | 3 | 3 | 3 | Completed
B
4 | 3 |  |  | WebApp - Monitor and manage Leaderboard | 0.5 | 0.5 | 0.5 | Completed
4 | 5 |  |  | WebApp - Monitor and manage Mission Submission | 1 | 1 | 1 | Completed
4 | 6 |  |  | WebApp - Monitor Trail Duration | 1.5 | 1.5 | 1.5 | Completed
4 | 7 |  | Admin Upload Module Backend | WebApp - Upload Multimedia (Images and Videos) | 2.5 | 2.5 | 2.5 | Completed
4 | 8 |  |  | WebApp - View Uploads | 2 | 2 | 2 | Completed
4 | 11 |  |  | WebApp - Monitor and manage Leaderboard | 1 | 1 | 1 | Completed
4 | 13 |  |  | WebApp - Monitor and manage Mission Submission | 1.5 | 1.5 | 1.5 | Completed
4 | 14 |  |  | WebApp - Monitor Trail Duration | 1 | 1 | 1 | Completed
4 | 15 |  | Admin Upload Module Frontend | WebApp - Upload Multimedia (Images and Videos) | 0.5 | 0.5 | 0.5 | Completed
4 | 16 |  |  | WebApp - View Uploads | 1.5 | 1.5 | 1.5 | Completed
4 | 17 | Android | User Trail Module (Frontend) | MobileApp - View Activity Feed | 1.5 | 1.5 | 1.5 | Completed
4 | 18 |  |  | MobileApp - View Leaderboard | 1 | 1 | 1 | Completed
4 | 19 |  | User Trail Module (Backend) | MobileApp - View Activity Feed | 2 | 2 | 2 | Completed
4 | 20 |  |  | MobileApp - View Leaderboard | 1 | 1 | 1 | Completed
5 | 7 |  | Hotspot Module (Backend) | WebApp - Add/Edit/Remove Hotspot Location | 0.5 | 0.5 | 0.5 | Completed
5 | 8 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 0.5 | 0.5 | 0.5 | Completed
5 | 9 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 0.5 | 0.5 | 0.5 | Completed
5 | 10 |  | Hotspot Module (Frontend) | WebApp - Add/Edit/Remove Hotspot Location | 1 | 1 | 1 | Completed
5 | 11 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 1 | 1 | 1 | Completed
5 | 12 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 1.5 | 1.5 | 1.5 | Completed
5 | 13 | IOS | App Account Module (Backend) | MobileApp - Login | 4 | 4 | 4 | Completed
5 | 14 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3 | Completed
5 | 15 |  | App Account Module (Frontend) | MobileApp - Login | 4 | 4 | 4 | Completed
5 | 16 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3 | Completed
6 | 7 |  | Narrative Module (Backend) | WebApp - Add/Edit/Remove Text/Story | 1.25 | 1.25 | 1.25 | Completed
6 | 8 |  |  | WebApp - Attach photos or videos to Narrative | 2 | 2 | 2 | Completed
6 | 9 |  | Narrative Module (Frontend) | WebApp - Add/Edit/Remove Text/Story | 1 | 1 | 1 | Completed
6 | 10 |  |  | WebApp - Attach photos or videos to Narrative | 2.5 | 2.5 | 2.5 | Completed
6 | 11 | Nodejs | Complete Mission Module (Backend) | MobileApp - Drag and Drop | 2 | 2 | 2 | Completed
6 | 12 |  |  | MobileApp - CrossWord | 1.5 | 1.5 | 1.5 | Completed
6 | 13 | Android | Complete Mission Module (Frontend) | MobileApp - Drag and Drop | 1 | 1 | 1 | Completed
6 | 14 |  |  | MobileApp - CrossWord | 2.5 | 2.5 | 2.5 | Completed
6 | 15 | IOS | User Trail Module (Backend) | Connect to Trail | 0.5 | 0.5 | 0.5 | Completed
6 | 16 |  |  | View Narrative | 2 | 2 | 2 | Completed
6 | 17 |  |  | Complete Missions(Quiz, Wefie) | 0.5 | 0.5 | 0.5 | Completed
6 | 18 |  |  | View Past Submissions | 1.5 | 1.5 | 1.5 | Completed
6 | 19 |  |  | Upload Submissions | 1 | 1 | 1 | Completed
6 | 20 |  |  | View map with pinned location(with location tracking) | 1.5 | 1.5 | 1.5 | Completed
6 | 21 |  | User Trail Module (Frontend) | Connect to Trail | 1 | 1 | 1 | Completed
6 | 22 |  |  | View Narrative | 2.5 | 2.5 | 2.5 | Completed
6 | 23 |  |  | Complete Missions(Quiz, Wefie) | 1 | 1 | 1 | Completed
6 | 25 |  |  | Upload Submissions | 1.5 | 1.5 | 1.5 | Completed
6 | 26 |  |  | View map with pinned location(with location tracking) | 1 | 1 | 1 | Completed
7 | 7 |  | Mission Module (Backend) | WebApp - Add/Edit/Remove mission description | 1 | 1 | 1 | Completed
7 | 8 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 | 2 | 2 | Completed
7 | 12 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 0.5 | 0.5 | 0.5 | Completed
7 | 13 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 0.5 | 0.5 | 0.5 | Completed
7 | 14 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 0.5 | 0.5 | 0.5 | Completed
7 | 16 |  |  | WebApp - Add/Edit/Remove Groups | 0.5 | 0.5 | 0.5 | Completed
7 | 23 | Nodejs | Mission Module (Backend) | MobileApp - Complete missions - Word Search - Anagram - Drawing | 2.5 | 2.5 | 2.5 | Completed
7 | 26 |  |  | View Leaderboard | 1 | 1 | 1 | Completed
7 | 28 |  |  | View Leaderboard | 1 | 1 | 1 | Completed
7 | 29 | Others | - | User Testing Preparation |  |  |  | In Progress
8 | 1 | Web App | Admin Trail Monitoring Module (Backend) | WebApp - Monitor Groups' Progress | 0.5 | 0.5 | 0.5 | Completed
8 | 2 |  |  | WebApp - Monitor and Manage Leaderboard | 2 | 2 | 2 | Completed
8 | 3 |  |  | WebApp - Monitor and Manage Mission Submission | 1.5 | 1.5 | 1.5 | Completed
8 | 4 |  | Admin Trail Monitoring Module (Front end) | WebApp - Monitor Groups' Progress | 1 | 1 | 0.5 | Completed
8 | 5 |  |  | WebApp - Monitor and Manage Leaderboard | 2.5 | 2.5 | 2.5 | Completed
8 | 6 |  |  | WebApp - Monitor and Manage Mission Submission | 1 | 1 | 1 | Completed
8 | 11 | Android | Complete Mission Module (Backend) | MobileApp - Complete missions - Anagram - Drawing | 2 | 2 | 2 | Completed
8 | 12 |  | Complete Mission Module (Frontend) | MobileApp - Complete missions - Anagram - Drawing | 2 | 2 | 2 | Completed
9 | 5 |  | Mission Module (Backend) | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 | 2 | 2 | Completed
9 | 6 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 | 0 | 2 | To Be Done
9 | 7 |  | Admin Trail Creation Module (Backend) | WebApp - Add/Edit/Remove Mission to trail map | 1 | 1 | 1 | Completed
9 | 8 |  |  | WebApp - Add/Edit/Remove Participants | 1 | 1 | 1 | Completed
9 | 9 |  |  | WebApp - Add/Edit/Remove Groups | 1 | 1 | 1 | Completed
9 | 13 | Android | Mission Module (Backend) | MobileApp - Complete missions - Word Search | 2 | 2 | 2 | Completed
9 | 14 |  | Mission Module (Frontend) | MobileApp - Complete missions - Word Search | 2 | 2 | 2 | Completed
9 | 15 | IOS | User Trail Module (Back end) | View Activity Feed | 1 | 1 | 1 | Completed
9 | 16 |  | User Trail Module (Frontend) | View Activity Feed | 1 | 1 | 1 | Completed
9 | 17 |  | Complete Mission Module (Backend) | MobileApp - Complete missions - Drag & Drop - Anagram | 3 | 3 | 3 | Completed
9 | 18 |  | Complete Mission Module (Frontend) | MobileApp - Complete missions - Drag & Drop - Anagram | 2 | 2 | 2 | Completed
10 | 1 | Web App** | Admin Trail Monitoring Module (Front end) | WebApp - Monitor Groups' Location | 1 | 1 | 1 | Completed
10 | 2 |  |  | WebApp - Monitor Trail Duration | 1 | 1 | 1 | Completed
10 | 5 |  | Mission Module (Backend) | WebApp - Add/Edit/Remove mission type: - Drag & Drop | 2 | 2 | 2 | Completed
10 | 6 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission type: - Drag & Drop | 2 | 2 | 2 | Completed
10 | 7 |  | Admin Trail Creation Module (Frontend) | WebApp - Add/Edit/Remove Mission to trail map | 1 | 1 | 1 | Completed
10 | 8 |  |  | WebApp - Add/Edit/Remove Participants | 1 | 1 | 1 | Completed
10 | 9 |  |  | WebApp - Add/Edit/Remove Groups | 1 | 1 | 1 | Completed
10 | 10 | Android | Notification Module (Backend) | MobileApp - View Notification | 2 | 2 | 2 | Completed
10 | 11 |  |  | MobileApp - Receive Notification | 1.5 | 1.5 | 1.5 | Completed
10 | 12 |  | Notification Module (Frontend) | MobileApp - View Notification | 1.5 | 1.5 | 1.5 | Completed
10 | 13 |  |  | MobileApp - Receive Notification | 2 | 2 | 2 | Completed
10 | 14 |  | Deployment | Prep for deployment |  |  |  | Completed
10 | 15 | IOS | Complete Mission Module (Backend) | MobileApp - Complete missions - Word Search - Drawing | 2 | 2 | 2 | Completed
10 | 16 |  | Complete Mission Module (Frontend) | MobileApp - Complete missions - Word Search - Drawing | 2 | 2 | 2 | Completed
10 | 17 |  | Deployment | Prep for deployment |  |  |  | Completed
|  |  | Admin Trail Monitoring Module (Back end) | WebApp - Monitor and Manage Activity Feed | 2 | 2 | 2 | Completed
|  |  | Admin Trail Monitoring Module (Front end) | WebApp - Monitor and Manage Activity Feed | 1.5 | 1.5 | 1.5 | Completed
11 | 1 | Web App | Notification Module (Backend) | WebApp - Announcer Feature | 2.5 | 2.5 | 2.5 | Completed
11 | 2 |  |  | WebApp - Reminder Feature | 2 | 2 | 2 | Completed
11 | 3 |  | Mission Module (Backend) | WebApp - Add/Edit/Delete missions - Word Search - Anagram - Drawing - Crossword | 1 | 1 | 1 | Completed
11 | 4 |  | Mission Module (Frontend) | WebApp - Add/Edit/Delete missions - Word Search - Anagram - Drawing - Crossword | 1 | 1 | 1 | Completed
11 | 5 |  | Notification Module (Frontend) | WebApp - Announcer Feature | 1 | 1 | 1 | Completed
11 | 6 |  |  | WebApp - Reminder Feature | 1 | 1 | 1 | Completed
| 11 | Android | Usability Module (Backend) | MobileApp - User Help Page | 3 | 3 | 3 | Completed
11 | 12 |  | Usability Module (Frontend) | MobileApp - User Help Page | 3 | 3 | 3 | Completed
11 | 13 | IOS | Notification Module (Backend) | MobileApp - View Notification | 1.5 | 1.5 | 1.5 | Completed
11 | 14 |  |  | MobileApp - Receive Notification | 2 | 2 | 2 | Completed
11 | 16 |  | Usability Module (Backend) | MobileApp - User Help Page | 3 | 3 | 3 | Completed
11 | 17 |  | Notification Module (Frontend) | MobileApp - View Notification |  |  |  | Completed
11 | 18 |  |  | MobileApp - Receive Notification | 2 | 2 | 2 | Completed
11 | 20 |  | Usability Module (Frontend) | MobileApp - User Help Page | 3 | 3 | 3 | Completed
11 | 21 | Others | - | USER TESTING PREPARATION |  |  |  | Completed
11 | 22 | Others | - | MID TERM PREPARATION |  |  |  | Completed
11 | 23 | Others | - | LIVE TRAIL PREPARATION |  |  |  | Completed
11 | 24 | Others | - | SPONSOR UAT |  |  |  | Completed
12 | 1 | Web App | Usability Module (Backend) | WebApp - Admin Help Page | 3 | 3 | 3 | Completed
12 | 2 |  | Usability Module (Frontend) | WebApp - Admin Help Page | 3 | 3 | 3 | Completed
12 | 3 | Others | - | UI/UX IMPROVEMENTS |  |  |  | Completed
12 | 4 | Others | - | LIVE TRAIL PREPARATION |  |  |  | Completed
12 | 5 | Others | - | OPTIMIZATION |  |  |  | Completed
12 | 6 | Others | - | DOCUMENTATION |  |  |  | Completed
13 | 5 | Web App | Data Analytcis (Back end) | WebApp - Record Trail Data | 3 | 3 | 3 | Completed
13 | 6 |  |  | WebApp - Display Summary Report of Past Data | 2 | 2 | 2 | Completed
13 | 7 |  | Data Analytcis (Front end) | WebApp - Record Trail Data | 4 | 4 | 4 | Completed
13 | 8 |  |  | WebApp - Display Summary Report of Past Data | 3 | 3 | 3 | Completed
13 | 9 | Others | - | UI/UX IMPROVEMENTS |  |  |  | Completed
13 | 10 | Others | - | POSTER PREPARATION |  |  |  | Completed
14 | 1 | Others | - | UI Improvement (Webapp, MobileApp)
14 | 2 | Others | - | FINAL PRESENTATION PREPARATION
14 | 3 | Others | - | SPONSOR UAT 2
15 | 1 |  | - | Preparation for Final Presentation

## Metrics(NEW)
Product Burndown
Sprint | Estimated Story Points | Actual Story Points Completed | Story Points Remaining
0 | 273.75 | 0 | 273.75
1 | 241.75 | 32 | 241.75
2 | 217.25 | 24.5 | 217.25
3 | 186.75 | 29.5 | 187.75
4 | 159.75 | 18.5 | 169.25
5 | 140.75 | 19 | 150.25
6 | 112 | 27.75 | 122.5
7 | 89.5 | 9.5 | 113
8 | 85.5 | 12 | 101
9 | 67.5 | 16 | 85
10 | 47.5 | 20 | 65
11 | 24.5 | 41.5 | 23.5
12 | 18.5 | 3 | 20.5
13 | 6.5 | 12 | 8.5
14 | 6.5 | 0 | 8.5
15 | 6.5 | 0 | 8.5
Sprint | Story Points Completed
0 | 0
1 | 32
2 | 24.5
3 | 29.5
4 | 18.5
5 | 19
6 | 27.75
7 | 9.5
8 | 12
9 | 16
10 | 20
11 | 41.5
12 | 3
13 | 12
14 | 0
15 | 0
Average | 0
Rolling Avg. | 18.8333