## Project Schedule v1
Date Created: | 2012-10-29
| SEPT | OCTOBER |  |  | NOVEMBER |  |  |  |  | DECEMBER |  |  |  | JANUARY |  |  |  | FEBRUARY |  |  |  |  | MARCH |  |  |  | APRIL
WEEK | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Conceptualization
Iteration 0: Project Initiation
Iteration 1: Identify Business Needs
Proposal Submission (26/10/2012)
Iteration 3: Solutioning
Development
Iteration 4: Prototyping
Acceptance (06/11/2012)
Iteration 5: Account
Iteration 6: Profile
Release 0.1
Iteration 7: Manage Tasks
Iteration 8: Manage Task Review
Iteration 9: Mobile(Tasks)
Release 0.2
Iteration 10: Manage Questions
Iteration 11: Mobile(Questions)
Release 0.3
Iteration 12: Search
Iteration 13: Manage Volunteer Records
Release 0.4
Iteration 14: User Testing
Mid Term Feedback
Iteration 15: Statistics
Release 0.5
Iteration 16: User Testing 2
Feedback
Iteration 17: User Acceptance Test
Iteration 18: Improvements
Final Presentation
Iteraton 18: Handover
Poster Day