## Schedule Metric
Iteration 1: 20/05/2013 to 26/05/2013 (7 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Gather user requirements | 1 day | 2013-05-20 | 2013-05-20 | 1 day | 2013-05-20 | 2013-05-20 | 100 percent
Research on requirements
Market Research | 6 days | 2013-05-21 | 2013-05-26 | 6 days | 2013-05-21 | 2013-05-26 | 100 percent
Define goals | 1 day | 2013-05-22 | 2013-05-22 | 1 day | 2013-05-22 | 2013-05-22 | 100 percent
Define priorities
Define project scope
Allocate roles and responsibilities
Develop schedule | 4 days | 2013-05-23 | 2013-05-26 | 4 days | 2013-05-23 | 2013-05-26 | 100 percent
Proposal write-up
Research on technology
Schedule Metric: | [7 days (planned) / 7 days (actual)] x 100 = 100 %
Iteration 2: 27/05/2013 to 09/06/2013 (14 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Define milestones | 1 day | 2013-05-27 | 2013-05-27 | 1 day | 2013-05-27 | 2013-05-27 | 100 percent
Define deliverables
Use case diagram
Use case Scenario
Account management | 4 days | 2013-05-28 | 2013-05-31 | 4 days | 2013-05-28 | 2013-05-31 | 100 percent
Content Management
Comic Management
Purchase Management
Search Management
Social Interaction Management
Video Management
confirmation | 1 day | 2013-05-31 | 2013-05-31 | 1 day | 2013-05-31 | 2013-05-31 | 100 percent
System Sequence Diagram
Account management | 2 days | 2013-06-01 | 2013-06-02 | 2 days | 2013-06-01 | 2013-06-02 | 100 percent
Content Management
Comic Management
Purchase Management
Search Management
Social Interaction Management
Video Management
confirmation | 1 day | 2013-06-03 | 2013-06-03 | 1 day | 2013-06-03 | 2013-06-03 | 100 percent
Sequence Diagram
Account management | 2 days | 2013-06-04 | 2013-06-05 | 2 days | 2013-06-04 | 2013-06-05 | 100 percent
Content Management
Comic Management
Purchase Management
Search Management
Social Interaction Management
Video Management
confirmation | 1 day | 2013-06-06 | 2013-06-06 | 1 day | 2013-06-06 | 2013-06-06 | 100 percent
Class diagram | 2 days | 2013-06-07 | 2013-06-08 | 2 days | 2013-06-07 | 2013-06-08 | 100 percent
ER Diagram | 1 day | 2013-06-09 | 2013-06-09 | 1 day | 2013-06-09 | 2013-06-09 | 100 percent
Proposal write-up | 7 days | 2013-06-03 | 2013-06-09 | 7 days | 2013-06-03 | 2013-06-09 | 100 percent
Schedule Metric: | [14 days (planned) / days (actual)] x 100 = 100 %
Iteration 4: 24/06/2013 to 12/07/2013 (19 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Setup database | 1 day | 2013-06-24 | 2013-06-24 | 1 day | 2013-06-25 | 2013-06-25 | 100 percent
Website layout | 1 day | 2013-06-25 | 2013-06-25 | 1 day | 2013-06-27 | 2013-06-27 | 100 percent
Account Management
Admin - Login/Logout | 2 days | 2013-06-26 | 2013-06-27 | 1 day | 2013-06-28 | 2013-06-28 | 66.7 percent
Admin - Create admin |  |  |  | 2 days | 2013-06-29 | 2013-06-30
Admin - Delete admin | 2 days | 2013-06-28 | 2013-06-29 | 1 day | 2013-07-02 | 2013-07-02 | 66.7 percent
Admin - Edit admin |  |  |  | 2 days | 2013-07-04 | 2013-07-05
Customer - Login/Logout | 2 days | 2013-06-24 | 2013-06-25 | 8 days | 2013-06-29 | 2013-07-06 | 25 percent
Integration | 2 days | 2013-06-30 | 2013-07-01 | 2 days | 2013-07-07 | 2013-07-08 | 100 percent
Testing | 1 day | 2013-07-02 | 2013-07-02 | 1 day | 2013-07-09 | 2013-07-09 | 100 percent
Debugging - Admin | 3 days | 2013-07-03 | 2013-07-05 | 3 days | 2013-07-10 | 2013-07-12 | 100 percent
Debugging - App
Buffer | 2 days | 2013-07-06 | 2013-07-07 | Used up
Schedule Metric: | [14 days (planned) / 19 days (actual)] x 100 = 73.7 %
Action Plan For Iteration 5: | 1. The team did not drop any functions for Iteration 5
2. "Admin - Edit Comic Details" Pushed to Iteration 6