## living_integrated_network_20130
Id | Story | Labels | Iteration | Iteration Start | Iteration End | Story Type | Estimate | Current State | Created at | Accepted at | Deadline | Requested By | Owned By | Description | URL | Comment | Comment | Task | Task Status | Task | Task Status | Task | Task Status
38853889 | Establish goals and rules |  | 1 | Aug 21, 2012 | Sep 3, 2012 | chore |  | accepted | Nov 2, 2012 | Aug 27, 2012 |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38853889
38854147 | Gather Requirements from client |  | 1 | Aug 21, 2012 | Sep 3, 2012 | chore |  | accepted | Nov 2, 2012 | Aug 30, 2012 |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38854147
38854155 | Develop project schedule |  | 1 | Aug 21, 2012 | Sep 3, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 2, 2012 |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38854155
38853899 | Create KPI |  | 1 | Aug 21, 2012 | Sep 3, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 3, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38853899
38854145 | Allocate roles and responsibilities |  | 1 | Aug 21, 2012 | Sep 3, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 3, 2012 |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38854145
38854755 | Analyse Client Requirements |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 6, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38854755
38854775 | User persona |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 9, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38854775
38854793 | User journey |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 9, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38854793
38854777 | Environmental scans |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 9, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38854777
38854759 | Finalise on requirements |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 10, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38854759
38854843 | Brainstorm on features we want to implement, how to implement, technology used and platforms |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 10, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38854843
38855021 | Shortlist feasible features |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 10, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855021
38855033 | Create use case and scenario for FBS |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 16, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855033
38855133 | Create schedule metric, bug metric and change log |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 16, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855133
38855089 | Create Sequence Diagram for FBS |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 16, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855089
38855159 | Create online mockup set 1 |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 17, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855159
38855173 | Create proposal draft |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 17, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855173
38855193 | Assess project schedule |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 17, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855193
38855201 | Assess requirements |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 17, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855201
38855213 | Team feedback and assessments |  | 2 | Sep 4, 2012 | Sep 17, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 17, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855213
38855887 | Assess system designs and make improvements |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 18, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855887
38855115 | Create test plan |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 20, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855115
38855067 | Create Class diagram for FBS |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 20, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855067
38855807 | Evaluate Online Mockup 1 with client |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 20, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855807
38855747 | Facility Booking System FSD |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 23, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855747
38855769 | Augmented reality research |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 23, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855769
38855779 | Database research |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 23, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855779
38855783 | Create use case and scenario for Admin and Special Functionalities |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 24, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855783
38855793 | Create Sequence Diagram for Admin and Special Functionalities |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 24, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855793
38855751 | FSD Creation |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 26, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855751
38855825 | Create Online Mockup set 2 |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 26, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855825
38855835 | Create UI design PSDs set 1 |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 26, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855835
38855761 | User Stories creation |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 27, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855761
38855845 | Evaluate Online Mockup 2 with client |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 27, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855845
38855853 | Evaluate UI Design PSDs set 1 |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 27, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855853
38855799 | Create Class diagram for Admin and special functionalities |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Sep 30, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855799
38855765 | Port user stories to Pivotal tracker and rate difficulty |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Oct 1, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855765
38855865 | Edit proposal |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Oct 1, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855865
38855871 | Assess project schedule |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Oct 1, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855871
38855881 | Assess requirements |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Oct 1, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855881
38855897 | Team Feedback and assessments |  | 3 | Sep 18, 2012 | Oct 1, 2012 | chore |  | accepted | Nov 2, 2012 | Oct 1, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38855897
38914021 | Develop test case |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 3, 2012 | Oct 2, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38914021
37022909 | Admin Log in and log out of account | administrative, general | 4 | Oct 2, 2012 | Oct 15, 2012 | feature | 1 | accepted | Oct 2, 2012 | Oct 14, 2012 |  | Xiangyang Peh | Jocelyn | As an admin, I want to be able to log in and out so i can access the LIN backend | http://www.pivotaltracker.com/story/show/37022909 | must flag user as an admin in his/her cookie (Xiangyang Peh - Oct 2, 2012)
36839755 | Administrator views admin page | administrative | 4 | Oct 2, 2012 | Oct 15, 2012 | feature | 1 | accepted | Sep 28, 2012 | Oct 14, 2012 |  | Jocelyn | Jocelyn | As an admin, I want to be able to view admin page so that I can do my admin duties | http://www.pivotaltracker.com/story/show/36839755
36840295 | Admin creates new LIN account | administrative | 4 | Oct 2, 2012 | Oct 15, 2012 | feature | 2 | accepted | Sep 28, 2012 | Oct 14, 2012 |  | Shamus | Jocelyn | As an admin user I need to be able to create a new LIN account So that when new people move In i can create new accounts for them | http://www.pivotaltracker.com/story/show/36840295
36832251 | User applies for new LIN account | general | 4 | Oct 2, 2012 | Oct 15, 2012 | feature | 2 | accepted | Sep 28, 2012 | Oct 14, 2012 |  | Xiangyang Peh | Jocelyn | As a resident of Beacon Heights, i want to create accounts for my family so they can use the LIN system under their own name | http://www.pivotaltracker.com/story/show/36832251
36840249 | Admin edits LIN user's account | administrative | 4 | Oct 2, 2012 | Oct 15, 2012 | feature | 2 | accepted | Sep 28, 2012 | Oct 14, 2012 |  | Shamus | Jocelyn | As an Admin user I need to be able to edit a LIN account So that the most up to date information will always be in the system. | http://www.pivotaltracker.com/story/show/36840249
38924975 | Test System |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38924975
38924979 | Debug System |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38924979
38924989 | Edit proposal |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38924989
38924991 | Assess Project Schedule |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38924991
38924993 | Assess requirements |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38924993
38925005 | Assess system requirements and make improvements |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925005
38925011 | Team feedback and assessments |  | 4 | Oct 2, 2012 | Oct 15, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 15, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925011
38925033 | Develop Test Case |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 16, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925033
36840345 | Admin Deletes LIN account | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Sep 28, 2012 | Oct 19, 2012 |  | Shamus | Jocelyn | As an admin user I need to be able to delete a LIN account So that residents moving out will no longer have access to LIN | http://www.pivotaltracker.com/story/show/36840345
36840253 | Administrator can view & Filter a list of all users | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Sep 28, 2012 | Oct 24, 2012 |  | Xiangyang Peh | Jonathan Seetoh | As an administrator, I want to be able to view a list of registered users So I can handle help requests and manage my users | http://www.pivotaltracker.com/story/show/36840253
36103973 | User Log in | general | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Sep 15, 2012 | Oct 29, 2012 |  | Xiangyang Peh | Jonathan Seetoh | As a user, I want to log in to the platform so I can access the LIN's features | http://www.pivotaltracker.com/story/show/36103973 | Must check how to verify that a user is a real condo member (Xiangyang Peh - Sep 15, 2012)
36834195 | Administrator creates facility | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 3 | accepted | Sep 28, 2012 | Oct 29, 2012 |  | Jonathan Seetoh | Jonathan Seetoh | As an administrator I want to be able to add a facility to the system So that condo residents can book the facility online. | http://www.pivotaltracker.com/story/show/36834195
37022621 | Admin views new LIN account applications |  | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Oct 2, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/37022621
37022653 | Admin user Approves pending LIN account | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Oct 2, 2012 | Oct 29, 2012 |  | Shamus | Jocelyn | As an admin user I need to be able to approve pending LIN accounts | http://www.pivotaltracker.com/story/show/37022653
37022765 | Admin is notified of accounts pending approval | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Oct 2, 2012 | Oct 29, 2012 |  | Jonathan Seetoh | Jocelyn | As an administrator I want to be notified if someone applies for a LIN acc So that i dont have to keep checking if there are new applicants | http://www.pivotaltracker.com/story/show/37022765
36834353 | Administrator can view/edit facility | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 2 | accepted | Sep 28, 2012 | Oct 29, 2012 |  | Jonathan Seetoh |  | As an administrator I want to be able to view all the facilities i have So that i can see the facilities and edit them if necessary. | http://www.pivotaltracker.com/story/show/36834353
36834441 | Administrator can delete a facility | administrative | 5 | Oct 16, 2012 | Oct 29, 2012 | feature | 1 | accepted | Sep 28, 2012 | Oct 29, 2012 |  | Jonathan Seetoh |  | As an administrator, i want to be able to delete a facility from the system So that if a facility is not in used anymore, it can be reflected in the system | http://www.pivotaltracker.com/story/show/36834441
38925037 | Test System |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925037
38925041 | Debug System |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925041
38925045 | Edit proposal |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925045
38925049 | Assess project schedule |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925049
38925051 | Assess requirements |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925051
38925053 | Assess system designs and make improvements |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925053
38925055 | Team feedback and assessments |  | 5 | Oct 16, 2012 | Oct 29, 2012 | chore |  | accepted | Nov 4, 2012 | Oct 29, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925055
38925109 | Acceptance Preparation |  | 6 | Oct 30, 2012 | Dec 10, 2012 | chore |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925109
38925503 | LIN 1.0 |  | 6 | Oct 30, 2012 | Dec 10, 2012 | release |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925503
38925473 | Acceptance Presentation |  | 6 | Oct 30, 2012 | Dec 10, 2012 | release |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925473
38925111 | Assess project schedule |  | 6 | Oct 30, 2012 | Dec 10, 2012 | chore |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925111
38925115 | Assess requirements |  | 6 | Oct 30, 2012 | Dec 10, 2012 | chore |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925115
38925121 | Assess requirements |  | 6 | Oct 30, 2012 | Dec 10, 2012 | chore |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925121
38925123 | Assess system design and make improvements |  | 6 | Oct 30, 2012 | Dec 10, 2012 | chore |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925123
38925125 | Team feedback and assessments |  | 6 | Oct 30, 2012 | Dec 10, 2012 | chore |  | accepted | Nov 4, 2012 | Nov 7, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/38925125
36832015 | User makes booking | facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 2 | accepted | Sep 28, 2012 | Dec 13, 2012 |  | KEVIN QUAH LIAN SHEN QUAH | Jocelyn | As a user I want to make a booking on a facility So that I will be able to reserve the space for myself | http://www.pivotaltracker.com/story/show/36832015 |  |  | User must be able to select a facility in the FBS | not completed | User must be able to select a date in the FBS | not completed | User must be able to select time in the FBS | not completed
36837131 | Admin must be able to track facility booking payments | administrative, facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 2 | accepted | Sep 28, 2012 | Dec 13, 2012 |  | Fayanne Foo | Jocelyn | As an Admin I need to be able to track payments made by the residents on their facility booking So that I can verify if the payment has been made | http://www.pivotaltracker.com/story/show/36837131
41004561 | Admin can delete booking |  | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 1 | accepted | Dec 11, 2012 | Dec 13, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/41004561
41031449 | Admin can update payment details |  | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 2 | accepted | Dec 11, 2012 | Dec 13, 2012 |  | Jocelyn | Jocelyn |  | http://www.pivotaltracker.com/story/show/41031449
36832197 | User views all of a facility's bookings | facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 3 | accepted | Sep 28, 2012 | Dec 23, 2012 |  | KEVIN QUAH LIAN SHEN QUAH | Fayanne Foo | As a user I want to view a facility's bookings So that I can see which facilities are available for booking | http://www.pivotaltracker.com/story/show/36832197 |  |  | Create booking page | not completed
36832137 | User deletes booking | facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 1 | accepted | Sep 28, 2012 | Dec 23, 2012 |  | KEVIN QUAH LIAN SHEN QUAH | Jocelyn | As a user I want to delete my booking So that I don't waste money booking a facility I don't need | http://www.pivotaltracker.com/story/show/36832137
40993817 | Admin can add and edit booking | administrative, facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 2 | accepted | Dec 10, 2012 | Dec 23, 2012 |  | Jocelyn | Jocelyn | Front end UI copied to back end. Modified to allow input of username/housing unit | http://www.pivotaltracker.com/story/show/40993817
40993511 | Admin can create new rules for a Facility | administrative, facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 3 | accepted | Dec 10, 2012 | Dec 23, 2012 |  | Shamus | Jocelyn |  | http://www.pivotaltracker.com/story/show/40993511
40993933 | Admin CRUD Facility Type | administrative, facility booking system | 7 | Dec 11, 2012 | Dec 24, 2012 | feature | 3 | accepted | Dec 10, 2012 | Dec 23, 2012 |  | Shamus | Jocelyn |  | http://www.pivotaltracker.com/story/show/40993933
38925481 | User Acceptance Test 1 |  | 8 | Dec 25, 2012 | Jan 7, 2013 | release |  | accepted | Nov 4, 2012 | Jan 7, 2013 | Dec 29, 2012 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925481
38925507 | LIN 1.1 |  | 8 | Dec 25, 2012 | Jan 7, 2013 | release |  | accepted | Nov 4, 2012 | Jan 7, 2013 | Jan 5, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925507
36837803 | Admin can upload and delete pdf forms | administrative, resource system | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As an admin, I want to be able to upload and delete pdf forms so that the forms online are the latest copies | http://www.pivotaltracker.com/story/show/36837803
36837379 | Admin uploads the PDF resident handbook in the resources | administrative, resource system | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As an admin, I want to edit the resident handbook in the resources so that I can update it with the latest rules and regulations | http://www.pivotaltracker.com/story/show/36837379
36833623 | User checks out the condo rules and regulation online | resource system | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As a user, I want to check out the Condo rules and regulation online so that I can easily find out what they are instead of trying to find a copy that was given to me. | http://www.pivotaltracker.com/story/show/36833623
36834111 | User saves a copy of the resources (resident handbook and pdf forms) | resource system | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As a user, I want to be able to save a copy of the resources so that I can have a soft copy in my computer. | http://www.pivotaltracker.com/story/show/36834111
36834007 | User prints out resources (resident handbook and pdf forms) | resource system | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As a user, I want to be able to print out resources so that I have a hard copy of it instead of a soft copy. | http://www.pivotaltracker.com/story/show/36834007
37307221 | Admin can upload and edit services details (like nearby amenities) | services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 2 | accepted | Oct 6, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As an admin, I want to edit the services details so that I can keep them updated | http://www.pivotaltracker.com/story/show/37307221
36832311 | User views services | services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Fayanne Foo | Jocelyn | As a user I need to be able to view nearby amenities and services so that I am able to obtain the contact details of these entities. | http://www.pivotaltracker.com/story/show/36832311
37020321 | Admin uploads a form template | administrative, services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 3 | accepted | Oct 2, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As an admin, I want to be able to create an online form so that users can submit new forms | http://www.pivotaltracker.com/story/show/37020321
37020379 | Admin can edit online forms | administrative, services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 2 | accepted | Oct 2, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As an admin, i want to be able to edit online forms to update them | http://www.pivotaltracker.com/story/show/37020379
36832885 | User submits administrative form online | services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 2 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Fayanne Foo | Jocelyn | As a user, I need to be able fill up the administrative forms and submit them online so that I do not need to head down physically to the managing office | http://www.pivotaltracker.com/story/show/36832885
37020269 | Admin views and search/filter all submitted forms | administrative | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 2 | accepted | Oct 2, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As an admin, I want to be able to view all submitted forms | http://www.pivotaltracker.com/story/show/37020269
37020277 | Admin changes form status | administrative | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Oct 2, 2012 | Jan 21, 2013 |  | Shamus | Jocelyn | as an Admin user I need to be able to change the status of the form To allow different admin users to know the status of the form (handled/in progress) | http://www.pivotaltracker.com/story/show/37020277
36835955 | Admin save and export user submitted form | administrative, services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Fayanne Foo | Jocelyn | As an Admin, I need to be able to save and export the user submitted forms so that I will be able to keep a separate record of these forms | http://www.pivotaltracker.com/story/show/36835955
36835147 | Users can have quick access to the downloadable forms when they are on the online forms page and vice versa | resource system, services | 9 | Jan 8, 2013 | Jan 21, 2013 | feature | 1 | accepted | Sep 28, 2012 | Jan 21, 2013 |  | Jocelyn | Jocelyn | As a user, I want to have quick access to the online version of the forms when I am on the PDF version and vice versa, so that I can quickly access the pages I want when I change my mind. | http://www.pivotaltracker.com/story/show/36835147
38925515 | User Testing 2 (Admin) |  | 10 | Jan 22, 2013 | Feb 4, 2013 | release |  | accepted | Nov 4, 2012 | Jan 31, 2013 | Feb 1, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925515
36835953 | User creates profile | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 3 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | KEVIN QUAH LIAN SHEN QUAH | Jocelyn | As a user I want to create a profile So that I can properly introduce myself to the other members of the community | http://www.pivotaltracker.com/story/show/36835953 | MA approves creation of profile (Shamus - Sep 28, 2012)
36836419 | User uploads profile picture | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | KEVIN QUAH LIAN SHEN QUAH | Jocelyn | As a user I want to upload a profile picture So that I can show my pretty face to the world | http://www.pivotaltracker.com/story/show/36836419
36835981 | User edits profile | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | KEVIN QUAH LIAN SHEN QUAH | Jocelyn | As a user I want to update my profile with more details So that I can keep my profile updated and fill in details otherwise missing from Facebook integration | http://www.pivotaltracker.com/story/show/36835981
36832427 | User views Wall | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 3 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Xiangyang Peh | Jocelyn | As a user, i want to be able to view the Condo Wall so that i can see the latest happenings in the condo | http://www.pivotaltracker.com/story/show/36832427 | This include coding the UI for the wall (Shamus - Sep 28, 2012)
36833047 | User or admin makes a post on wall | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 2 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Xiangyang Peh | Jocelyn | As a user, I want to be able to post on the condo wall So I can share updates with my friends and neighbours | http://www.pivotaltracker.com/story/show/36833047
36834969 | User views community's members | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 2 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Xiangyang Peh | Jocelyn | As a user, I want to look at a list of people using LIN so I can discover new friends | http://www.pivotaltracker.com/story/show/36834969
36837185 | User searches for other community members | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Xiangyang Peh | Jocelyn | As a user, I want to search for other other users so i can look for friends and neighbouts | http://www.pivotaltracker.com/story/show/36837185
37022479 | User adds a friend | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Oct 2, 2012 | Feb 3, 2013 |  | Shamus | Jocelyn | As a user I need to be able to add friends So that i can invite them to my AWESOME events | http://www.pivotaltracker.com/story/show/37022479
36835759 | User can submit an enquiry or feedback | contact us | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 2 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Jocelyn | Jocelyn | As a user, I want to be able to submit an enquiry or feedback online so that I can easily contact the admin personnel if I need to | http://www.pivotaltracker.com/story/show/36835759
36834957 | Admin view user submitted feedback forms | administrative, contact us | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Fayanne Foo | Jocelyn | As an admin, I need to be able to view the responses submitted by the residents, so that I will be able to act upon the response. | http://www.pivotaltracker.com/story/show/36834957
36834445 | User tags friends in post | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Sep 28, 2012 | Feb 3, 2013 |  | Xiangyang Peh | Jocelyn | As a user, I want to tag my beacon heights friends in my post. So my friends will be informed of my updates | http://www.pivotaltracker.com/story/show/36834445
37306391 | User likes a post on the wall | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Oct 6, 2012 | Feb 3, 2013 |  | Jocelyn | Jocelyn | As a User, I want to like posts on the wall so that I can show that I like the post | http://www.pivotaltracker.com/story/show/37306391
37306401 | User flags shoutout/request for help on the wall as inappropriate | community system | 10 | Jan 22, 2013 | Feb 4, 2013 | feature | 1 | accepted | Oct 6, 2012 | Feb 3, 2013 |  | Jocelyn | Jocelyn | As a user I need to be able to flag a shoutout/request for help as in appropriate | http://www.pivotaltracker.com/story/show/37306401
44437347 | User Testing 3 (SMU) |  | 11 | Feb 5, 2013 | Feb 18, 2013 | release |  | accepted | Feb 13, 2013 | Feb 7, 2013 | Feb 8, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/44437347
36835093 | User views events timeline | event system | 11 | Feb 5, 2013 | Feb 18, 2013 | feature | 3 | accepted | Sep 28, 2012 | Feb 18, 2013 |  | Shamus | Jocelyn | As a user I need to be able to jump to a certain date in the events timeline | http://www.pivotaltracker.com/story/show/36835093
36832431 | User creates an event | event system | 11 | Feb 5, 2013 | Feb 18, 2013 | feature | 2 | accepted | Sep 28, 2012 | Feb 18, 2013 |  | Shamus | Jocelyn | As a User I want to create an event(online) So that inform my friends about my event(Actual) | http://www.pivotaltracker.com/story/show/36832431
36833437 | User change event details | event system | 11 | Feb 5, 2013 | Feb 18, 2013 | feature | 1 | accepted | Sep 28, 2012 | Feb 18, 2013 |  | Shamus | Jocelyn | As a user who created an event I need to be able to change the details of the event so that i can inform attendees of any changes in the event | http://www.pivotaltracker.com/story/show/36833437
44437375 | User Testing 4 (Residents) |  | 12 | Feb 19, 2013 | Mar 4, 2013 | release |  | accepted | Feb 13, 2013 | Feb 24, 2013 | Feb 15, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/44437375
38925513 | LIN 1.2 |  | 12 | Feb 19, 2013 | Mar 4, 2013 | release |  | accepted | Nov 4, 2012 | Feb 24, 2013 | Feb 15, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925513
36832667 | User cancels event | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user I need to cancel a event that i have created so that when something crops up, i have the ability to change my mind. | http://www.pivotaltracker.com/story/show/36832667
37021095 | User views Event Wall | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 2 | unstarted | Oct 2, 2012 |  |  | Fayanne Foo |  | As a User, I need to be able to view the wall/page of different events So that I can find out more details and join in the event | http://www.pivotaltracker.com/story/show/37021095
36832873 | User invites friends to events | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user I want to invite friends to my events so that i do not have to manually invite them | http://www.pivotaltracker.com/story/show/36832873
36833717 | User RSVPs to an event | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | as a user i need to be able to indicate that I will be attending an event | http://www.pivotaltracker.com/story/show/36833717
36832433 | User tags facility booking to event | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user I want to tag a facility to my event So that my attendees will know where my events are going to be held at. | http://www.pivotaltracker.com/story/show/36832433
38925641 | Mid Term Presentation |  | 12 | Feb 19, 2013 | Mar 4, 2013 | release |  | unstarted | Nov 4, 2012 |  | Feb 26, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925641
36833185 | User join events | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user i want to be able to join an event that I was invited to | http://www.pivotaltracker.com/story/show/36833185
36833679 | User likes an event | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | as a user i need to be able to like an event | http://www.pivotaltracker.com/story/show/36833679
36834429 | User flags an event as inapprorpiate | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user I need to be able to flag an event on the event wall as inappropriate. | http://www.pivotaltracker.com/story/show/36834429
36835281 | User flags shoutout/request for help in event page as inappropriate | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user I need to be able to flag a shoutout/request for help as in appropriate | http://www.pivotaltracker.com/story/show/36835281
36835713 | MCST/admin uploads banner for featured event | administrative, event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As an Admin user/MCST I need to be able to upload banners for featured events | http://www.pivotaltracker.com/story/show/36835713
36833247 | User makes post on event wall | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | as a user i need to be able to make a post on the events wall so that i can voice out my opinions, make comments, RSVP etc. | http://www.pivotaltracker.com/story/show/36833247
36833521 | User filters events | event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user I need to be able to fiter through the events list so that i can differentiate between condo-wide events and and my events | http://www.pivotaltracker.com/story/show/36833521
36835787 | Admin user features a user created event | administrative, event system | 12 | Feb 19, 2013 | Mar 4, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | Shamus | Jocelyn | As an admin user I need to be able to feature user created event | http://www.pivotaltracker.com/story/show/36835787
36834095 | User attaches event to post | community system | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | Xiangyang Peh |  | As a user posting on a wall, I want to attach an event i created to my post so i can provide event information easily on my post | http://www.pivotaltracker.com/story/show/36834095
36832259 | User makes payment for booking online | facility booking system | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH | Jocelyn | As a user I want to make payments for bookings online So that I don't waste time physically making bookings | http://www.pivotaltracker.com/story/show/36832259 | zooz.com (Xiangyang Peh - Sep 28, 2012) | paypal.com (Xiangyang Peh - Sep 28, 2012)
36836035 | User links Facebook to profile | community system | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a user I want to link my Facebook account to my profile So that I can save time not entering details into the profile, and be able to use Facebook features from within the app. | http://www.pivotaltracker.com/story/show/36836035
36837925 | User view Admin announcements via Facebook app | facebook app | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user via the facebook app I need to be able to view admin announcements | http://www.pivotaltracker.com/story/show/36837925
36837721 | User view events via FB App | facebook app | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 3 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user through the facebook app I need to be able to view an event in LIN | http://www.pivotaltracker.com/story/show/36837721
36837373 | User responds to a Request for help through the FB App | facebook app | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | Shamus |  | As a user through the facebook app I need to be able to respond to a request for help (clicking on it should take me back to LIN's condo wall) | http://www.pivotaltracker.com/story/show/36837373
36832369 | User books taxi | services | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 3 | unstarted | Sep 28, 2012 |  |  | Fayanne Foo |  | As a user, I need to be able to input my location details and arrival time so that I am able to book a taxi | http://www.pivotaltracker.com/story/show/36832369
38925681 | LIN 1.3 |  | 13 | Mar 5, 2013 | Mar 18, 2013 | release |  | unstarted | Nov 4, 2012 |  | Mar 19, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925681
36834127 | Admin views facility usage report | administrative, analytics, facility booking system | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 3 | unstarted | Sep 28, 2012 |  |  | Fayanne Foo |  | As an admin, I need to be able to view usage reports so that I am able to keep track of the usage of the facilities | http://www.pivotaltracker.com/story/show/36834127
36832325 | Manager views most recently used | analytics, facility booking system | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 1 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a manager I want to view the most recently used facilities So that I can figure out which facilities are likely to need maintenance | http://www.pivotaltracker.com/story/show/36832325
36832361 | Manager views most frequently used facilities | analytics, facility booking system | 13 | Mar 5, 2013 | Mar 18, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a manager I want to be able to view the most frequently used facilities So that I will be able to judge which are the most overloaded facilities | http://www.pivotaltracker.com/story/show/36832361
36832453 | Manager views revenue generated from facilities | analytics, facility booking system | 14 | Mar 19, 2013 | Apr 1, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a manager I want to be able to view the revenue generated form facilities So that I am able to implement better pricing policies for high revenue facilities | http://www.pivotaltracker.com/story/show/36832453
36832413 | Manager views peak hour usage of facilities | analytics, facility booking system | 14 | Mar 19, 2013 | Apr 1, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a manager I want to be able to view the peak hour usage of facilities So that I am able to better manage the demand for facilities and implement policies accordingly | http://www.pivotaltracker.com/story/show/36832413
36832475 | Manager views usage/time graph | analytics, facility booking system | 14 | Mar 19, 2013 | Apr 1, 2013 | feature | 2 | unstarted | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a manager I want to be able to view a usage/time graph So that I can plan for future facility bookings | http://www.pivotaltracker.com/story/show/36832475
38925701 | User Testing 5 (SMU) |  | 14 | Mar 19, 2013 | Apr 1, 2013 | release |  | unstarted | Nov 4, 2012 |  | Mar 20, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925701
38925671 | User Testing 6 (Residents) |  | 14 | Mar 19, 2013 | Apr 1, 2013 | release |  | unstarted | Nov 4, 2012 |  | Mar 25, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925671
38925719 | LIN 1.4 |  | 14 | Mar 19, 2013 | Apr 1, 2013 | release |  | unstarted | Nov 4, 2012 |  | Apr 12, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925719
38925705 | Final Presentation |  | 14 | Mar 19, 2013 | Apr 1, 2013 | release |  | unstarted | Nov 4, 2012 |  | Apr 15, 2013 | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925705
43718897 | Admin sends email to all residents |  |  |  |  | feature |  | unscheduled | Feb 3, 2013 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/43718897
43718895 | Disclaimer or instructions on each page |  |  |  |  | feature |  | unscheduled | Feb 3, 2013 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/43718895
43718893 | Email reminder for payment, then if they do not pay, the system will auto delete the system | facility booking system |  |  |  | feature |  | unscheduled | Feb 3, 2013 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/43718893
36834109 | User invites more people to event(after creation) | event system |  |  |  | feature | 1 | unscheduled | Sep 28, 2012 |  |  | Shamus |  | As a creator of and event I need to be able to invite more people to my event | http://www.pivotaltracker.com/story/show/36834109
39289127 | Seems that sometimes DB cannot be access via hosted app. |  |  |  |  | bug |  | unscheduled | Nov 9, 2012 |  |  | Shamus |  | needs more testing to replicate. Apparently only after tunneling can we log in. | http://www.pivotaltracker.com/story/show/39289127
39121769 | If user is not found during login, should return to login page with informative message |  |  |  |  | bug |  | unscheduled | Nov 7, 2012 |  |  | Shamus |  |  | http://www.pivotaltracker.com/story/show/39121769
38611359 | User able to spam enter when registering and it will create multiple applications |  |  |  |  | bug |  | unscheduled | Oct 29, 2012 |  |  | Shamus |  |  | http://www.pivotaltracker.com/story/show/38611359
36834487 | Admin post latest event on event wall | administrative, event system |  |  |  | feature | 1 | unscheduled | Sep 28, 2012 |  |  | Fayanne Foo |  | As an admin I want to be able to add events on the event wall so that I am able to invite all residents to the event | http://www.pivotaltracker.com/story/show/36834487
38925413 | User can use NFC to launch app |  |  |  |  | feature | 3 | unscheduled | Nov 4, 2012 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925413
38925359 | User can use NFC to make a booking |  |  |  |  | feature | 2 | unscheduled | Nov 4, 2012 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/38925359
36832277 | Managing Agent edits bookings | facility booking system |  |  |  | feature | 2 | unscheduled | Sep 28, 2012 |  |  | KEVIN QUAH LIAN SHEN QUAH |  | As a manager I want to edit facility bookings So that I can troubleshoot user systems | http://www.pivotaltracker.com/story/show/36832277
39131323 | Developer can create new instance of application |  |  |  |  | feature | 3 | unscheduled | Nov 7, 2012 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/39131323
39131573 | Developer can view newly created instance of application |  |  |  |  | feature | 2 | unscheduled | Nov 7, 2012 |  |  | Jocelyn |  |  | http://www.pivotaltracker.com/story/show/39131573
36834419 | User emails a soft copy of the resources (handbook and pdf forms) to email addresses | resource system |  |  |  | feature | 1 | unscheduled | Sep 28, 2012 |  |  | Jocelyn | Jocelyn | As a user, I want to be able to email a soft copy of the resources so that I will have a soft copy of it with me. | http://www.pivotaltracker.com/story/show/36834419
36837005 | Admin can save and export enquiries and feedback | administrative, contact us |  |  |  | feature | 2 | unscheduled | Sep 28, 2012 |  |  | Jocelyn |  | As an admin, I want to save and export enquiries and feedback so that I can keep them for records purposes | http://www.pivotaltracker.com/story/show/36837005