**Minutes 10**

|  |  |
| --- | --- |
| Date: | 18/06/2013 |
| Time: | 7 pm |
| Venue: | SOB GSR 2-10 |
| Attendees | Nur Hazirah Binte Zainal AbidinPriya PathakRoohiya DudekulaSaloni RawatSaraniya Elengovan |
| Agenda | 1. Proposal
2. Schedule
3. Scope
 |
| Topics discussed | 1. **Discussed changes in proposal as advised by prof**
2. **New scope**
	1. Core
		1. Account Management Module
			* Log In / Log Out (Admin & Customer)
			* Create admin account (Admin)
			* Delete admin account (Admin)
			* Change admin password (Admin)
			* Delete user account (Customer)
		2. Content Management Module
			* Upload comic via admin website (Admin)
			* Delete comic from database (Admin)
			* Edit comic details (Title, author, volume, issue, genre, synopsis) via admin website
		3. Comic Management Module
			* View comic on app (Customer)
			* Delete comic from app (Customer)
	2. Secondary
		1. Purchase Management Module
			* View purchase details via admin website (Admin)
			* Make payment (Customer)
			* Enter purchase details for payment (Customer)
			* QR (Customer)
			* View notification (Customer)
		2. Search Management Module
			* Search (by title or author) via admin website (Admin)
			* Search (by title, author or free/not) in app (Customer)
	3. Tertiary
		1. Social Interaction Management Module
			* Like (Customer)
		2. Video Management Module
			* Upload video via admin website (Admin)
			* Delete video via admin website (Admin)
			* View video in app (Customer)
	4. Wish List
		1. User able to log in without plug in
		2. Voice navigation / Voice search
		3. Comment, flag Comment (Customer) and delete flagged comments via admin website (Admin)
		4. Analytics
3. **New schedule**
	1. Iteration 1
		1. Date: 20/05 to 26/05
		2. Task: Define project scope, gather user requirements, research on various requirements and technologies to be used, define goals and priorities
	2. Iteration 2
		1. Date: 27/05 to 09/06
		2. Task: Prepare project documentation for milestones, deliverables and proposal, ER diagram, use case scenario and diagram, SD and SSD.
	3. Iteration 3
		1. Date: 10/06 to 23/06
		2. Task: Project initiation, defining the parameters for schedule and bug metric, mock up for admin website and paper prototype for app
	4. Iteration 4
		1. Date: 24/06 to 05/07
		2. Buffer: 06/07 to 07/07
		3. Task: Set up database, development of UI for website and application, account management module (login, logout, create admin account, delete admin account and, delete user account)
	5. Iteration 5
		1. Date: 08/07 to 08/08
		2. Buffer: 09/07 to 20/08
		3. Milestone – Acceptance: 20/08
		4. Task: Content management module (upload comic, edit comic details), comic management module (view comic) and purchase management module (enter purchase details, make payment)
	6. Iteration 6
		1. Date: 21/08 to 03/09
		2. Buffer: 04/09 to 05/09
		3. Milestone – UAT 1
		4. Task: Content management module (delete comic from database), comic management module (delete comic from app), search management (Search in admin website and app)
	7. Iteration 7
		1. Date: 06/09 to 14/09
		2. Buffer: 15/09 to 16/09
		3. Task: Video management module (upload video and view video) and purchase management module (QR)
	8. Iteration 8
		1. Date: 17/09 to 26/09
		2. Buffer: 27/09 to 29/09
		3. Milestone – Mid Term: 30/09 to 09/10
		4. Task: Purchase management module (View notification, view purchase details via admin website) and social interaction module (like)
	9. Buffer
		1. Date: 10/10 to 23/10
		2. Milestone – UAT 2
	10. Iteration 9
		1. Date: 24/10 to 24/11
		2. Milestone – Poster: 12/11
		3. Milestone – Finals: 26/11 to 3/12
		4. Task: Go live (Google play), documentations for “Go live” process and admin guide
 |
| To do  | 1. Ask client if they are okay if the app can’t come down from Google Play.
2. Inform client QR is 3rd party integration
3. Inform client that for video it has to be YouTube embedded.
4. Let client know that if customer clicks buy we can’t take number of time viewed comic details.
5. Ask Saraniya to ask supervisor about acceptance dates!!!
6. Update official scope
7. Update official schedule
 |
| Next Agenda |  |

Prepared by, Vetted by,

Priya