## Bug log
S/N | Milestone | Owner | Description | Impact level | Score | Version Found | Resolved | Version Resolved | Iteration Found | Iteration Resolved | Total | [7 empty] | Yes
1 | A | Weikiat | Front end (Team photo has links to .html instead of .php) | Cosmetic/Trivial | 0 | UAT 1 | Yes | 70 |  |  | Number of bugs | Resolved | Unresolved | Score |  |  |  | Cosmetic/Trivial | No
2 | A | Weikiat | Add photo (Photo name as primary key... When delete, all similar photo names deleted) | Major | 5 | UAT 1 | Yes | 60 | 4 | 5 | Num of Logs | Resolved | Not Resolved | Score
3 | A | Weikiat | Session Time out.. (Timed out even though actions are still being done) | Minor | 3 | UAT 1 | Yes | 67 | 4 | 5 | 79 | 79 | 0 | 0
4 | A | Weikiat | Connection (Close connection) | Minor | 3 | UAT 1 | Yes | 62 | 4 | 5
5 | A | Junfan | Traffic Management (detailed crashed when no initial details is added) | Major | 5 | UAT 1 | Yes | 93 | 4 | 5
6 | A | Weikiat | Team photo should be the link | Cosmetic/Trivial | 0 | UAT 1 | Yes | 70
7 | A | Weikiat | Client would like to have the dept as tab, the team head will be shown -- refer to photo. To combine the tabs layout with the square layout. | Cosmetic/Trivial | 0 | UAT 1 | Yes | 70
8 | A | Weikiat | Headings for side navigation for back end | Cosmetic/Trivial | 0 | UAT 1 | Yes | 65
9 | A | Weikiat | ACL - if granted, show deny button if denied, show grant button | Cosmetic/Trivial | 0 | UAT 1 | Yes | 60
10 | A | Weikiat | Pjt Mgt - If projects has same name, edits will apply to both projects | Minor | 3 | UAT 1 | Yes | 60 | 4 | 5 |  |  |  |  | Iteration | Date Start | Date End
11 | A | Weikiat | Pjt Mgt - Pjt name should be displayed on front end for each pjt | Cosmetic/Trivial | 0 | UAT 1 | Yes | 70 |  |  | 5 | 0 |  |  | 5 | 2011-07-22 | 2011-08-12
12 | A | Weikiat | Each pjt should have a photo gallery | Cosmetic/Trivial | 0 | UAT 1 | Yes | 70 |  |  | 6 | 0 |  |  | 6 | 2011-08-12 | 2011-09-02
13 | A | Junfan | Naming of select db should be changed | Cosmetic/Trivial | 0 | UAT 1 | Yes | 70 |  |  | 7 | 0 |  |  | 7 | 2011-09-02 | 2011-09-27
14 | A | Junfan | pdf only generates one column. Needs more | Minor | 3 | UAT 1 | Yes | 48 | 4 | 4 |  |  |  |  | 8 | 2011-09-29 | 2011-10-15
15 | A | Junfan | Search function for student list or autocomplete | Cosmetic/Trivial | 0 | UAT 1 | Yes | 112 | [6 empty] | 9 | 2011-10-17 | 2011-10-26
16 | A | Junfan | Catch error if name field in csv is blank. | Minor | 3 | UAT 1 | Yes | 296 | 4 | 8 |  |  |  |  | 10 | 2011-10-27 | 2011-11-11
17 | A | Junfan | System should allow Re-enter into station | Minor | 3 | UAT 1 | Yes | 296 | 4 | 8 |  |  |  |  | 11 | 2011-11-11 | 2011-11-29
18 | B | Junfan | Centralise the blackboard in traffic mgt | Cosmetic/Trivial | 0 | 50 | Yes | 112
19 | B | Junfan | Public is able to delete user without having to log in | Major | 5 | 52 | Yes | 70 | 4 | 5
20 | B | Junfan | creation of me db causes 'The connection to the server was reset while the page was loading.' db is created but tables are not | Major | 5 | 52 | Yes | 112 | 4 | 6
21 | B | Weikiat | Link the user to acl mgt | Minor | 3 | 78 | Yes | 115 | 5 | 5
22 | B | Weikiat | What we do page dynamic resolution issue | Cosmetic/Trivial | 0 | 78 | Yes | 115
23 | B | Weikiat | Search all for all searching functions (photo) | Cosmetic/Trivial | 0 | 78 | Yes | 115
24 | B | Junfan | QR generation page has timeout error, generation not complete | Major | 5 | 78 | Yes | 112 | 5 | 5
25 | B | Junfan | Traffic Management -- UI issue when screen resolution changes | Cosmetic/Trivial | 0 | 78 | Yes | 112
26 | B | Junfan | Traffic Management -- provide icon for back to overview link | Cosmetic/Trivial | 0 | 78 | Yes | 361 | 5
27 | B | Junfan | Traffic Management -- Add in time in station for station overview | Cosmetic/Trivial | 0 | 78 | Yes | 112
28 | B | ALL | Main page for report and traffic to have select implementation | Cosmetic/Trivial | 0 | 78 | Yes | 101
30 | B | Auch | Next button to be standardise | Cosmetic/Trivial | 0 | 78 | Yes |  |  | 2011-10-27
31 | B | Auch | Set max 2 digit for option based score | Cosmetic/Trivial | 0 | 78 | Yes |  |  | 2011-10-27
32 | B | Auch | Create new css for a default table definition | Cosmetic/Trivial | 0 | 78 | Yes |  |  | 2011-10-27
33 | B | Auch | Missed the fieldset closing for assign_weight.php | Major | 5 | 78 | Yes | 81 | 5 | 5
34 | B | Auch | Auto addition of % to display in total% | Cosmetic/Trivial | 0 | 78 | Yes |  |  | 2011-09-30
35 | B | Auch | Description of range to be changed to [from ¦ to ] | Minor | 3 | 78 | Yes | 86 | 5 | 5
37 | B | Auch | Change the layout of Birt report viewer | Minor | 3 | 78 | Yes | 86 | 5 | 5
38 | B | Auch | Change font of report to tahoma | Cosmetic/Trivial | 0 | 78 | Yes | 100
39 | B | Jinghui | Enter bug login page | Cosmetic/Trivial | 0 | 82 | Yes | 112
40 | B | Jinghui | Radio button should be icons instead | Minor | 3 | 82 | Yes | 112 | 5 | 5
41 | B | Jinghui | If connection has error it should be handled | Major | 5 | 82 | Yes | 112 | 5 | 5
42 | B | Jinghui | Manual input has to sync to BackEnd | Minor | 3 | 82 | Yes | 297 | 5 | 8
43 | B | Auch | Modify the terms used in parameter search -- Add in search based on class | Improvements | 0 | 78 | Yes | 299 | 5 | 2011-10-12
44 | B | Jinghui | Limit to 10 students in station instead of 8 | Cosmetic/Trivial | 0 | 82 | Yes
45 | B | Jinghui | Tracking of amount from station to station | Major | 5 | 82 | Yes | 112 | 6 | 5
46 | B | Jinghui | Have the prompt message to be visible | Cosmetic/Trivial | 0 | 82 | Yes | 112
47 | B | Jinghui | Comment box to be moved down and have the radio button up for openended | Cosmetic/Trivial | 0 | 82 | Yes | 112
48 | B | Jinghui | portrait view better for supermarket | Cosmetic/Trivial | 0 | 82 | Yes | 112
49 | B | Jinghui | Popup message should appear at centre of page | Cosmetic/Trivial | 0 | 82 | Yes | 112
50 | B | Jinghui | Input field for user name and password should be single-lined | Cosmetic/Trivial | 0 | 82 | Yes | 112
51 | B | Jinghui | Prevent accidental clicking of Back button | Cosmetic/Trivial | 0 | 82 | Yes | 112
52 | C | Jinghui | Master resend button | Improvements | 0 | 123 | Yes | 297 | 6
53 | C | Jinghui | Cut off wireless functions | Improvements | 0 | 123 | Yes | 297 | 6
54 | C | Junfan | Header issue with deployment on YDC server | Major | 5 | 124 | Yes | 136 | 7 | 6
55 | C | Jinghui | Supermarket module crashed | Show Stopper | 10 | 130 | Yes | 230 | 7 | 7
56 | C | Auch | Difficult to input node dollar range during config | Cosmetic/Trivial | 0 | 130 | Yes | 143 | 7
57 | C | Auch | No validation for score in node dollar config | Minor | 3 | 130 | Yes | 147 | 7 | 7
58 | C | Junfan | Maze config- previously saved MCQ questions not showing | Minor | 3 | 180 | Yes | 211 | 7 | 7
59 | C | Junfan | Maze config- Delete Implementation cause data loss | Major | 5 | 180 | Yes | 211 | 7 | 7
60 | C | Weikiat | No indication of session timeout | Cosmetic/Trivial | 0 | 204 | Yes | 247 | 7
61 | C | Weikiat | Back end main headers not in sequence (OTA should be placed in Administration | Cosmetic/Trivial | 0 | 204 | Yes | 229 | 7
63 | C | Junfan | Validate maximum of 10 stations to be added in station config | Minor | 3 | 204 | Yes | 211 | 7 | 7
64 | C | Junfan | Button link to config for supermarket | Cosmetic/Trivial | 0 | 204 | Yes | 245 | 7
65 | C | Junfan | Check/Uncheck module image should be of the same size | Improvements | 0 | 204 | Yes | 309 | 7 | 2011-10-16
66 | C | Junfan | Hyperlink Cross/Tick images to module config | Cosmetic/Trivial | 0 | 204 | Yes | 211 | 7
68 | C | Junfan | Traffic image should be grey scale if no students in station | Cosmetic/Trivial | 0 | 204 | Yes | 228 | 7
69 | C | Junfan | Dynamic refresh for traffic management | Cosmetic/Trivial | 0 | 204 | Yes | 296 | 7 | 2011-10-12
70 | C | Junfan | Validation of 10 stations to be shown in mgt portal | Improvements | 0 | 204 | Yes | 390 | 7
71 | C | Auch | Un-configurable boxes in report config is not distinguishable | Minor | 3 | 204 | Yes | 217 | 7 | 7
72 | C | Auch | Category without modules will have error in assign weightage | Major | 5 | 204 | Yes | 213 | 7 | 7
73 | C | Jinghui | Login too slow (Separate downloading button from login) | Major | 5 | 204 | Yes | 230 | 7 | 7
74 | C | Jinghui | Cannot add new students when there are lesser than 10 students | Major | 5 | 204 | Yes | 230 | 7 | 7
75 | C | Auch | Supermarket config is recog as done if there is no 0 values of score | Minor | 3 | 210 | Yes | 284 | 7 | 8
79 | D | Junfan | Default setting for nd and comments in maze config | Minor | 3 | 229 | Yes | 296 | 8 | 8
80 | D | Junfan | Unable to dynamically insert rows for scenarioconfig in maze config | Minor | 3 | 229 | Yes | 385 | 8 | 11
81 | D | Jinghui | Error for alarm countdown function | Minor | 3 | 297 | Yes | 389 | 9 | 2015-11-01
82 | D | Weikiat | Validation for Instant Messenger | Minor | 3 | 314 | Yes | 315 | 9 | 2011-10-17
83 | D | Jinghui | Error for name when users goes back from notes to profile page | Minor | 3 | 297 | Yes | 363 | 9 | 2015-11-01
84 | D | Junfan | Delete implementation affeects report config | Minor | 3 | 229 | Yes | 378 | 8 | 10
85 | D | Junfan | typing error in maze configuration | Minor | 3 | 229 | Yes | 373 | 8 | 10
86 | D | Jinghui | Unable to send to multiple station for IM | Major | 5 | 356 | Yes | 398 | 10
87 |  |  |  |  | 0
88 |  |  |  |  | 0
89 |  |  |  |  | 0
90 |  |  |  |  | 0
91 |  |  |  |  | 0
92 |  |  |  |  | 0
93 |  |  |  |  | 0
94 |  |  |  |  | 0
95 |  |  |  |  | 0
96 |  |  |  |  | 0
97 |  |  |  |  | 0
98 |  |  |  |  | 0
99 |  |  |  |  | 0
100 |  |  |  |  | 0
101 |  |  |  |  | 0
102 |  |  |  |  | 0
103 |  |  |  |  | 0
104 |  |  |  |  | 0
105 |  |  |  |  | 0
106 |  |  |  |  | 0
107 |  |  |  |  | 0
108 |  |  |  |  | 0
109 |  |  |  |  | 0
110 |  |  |  |  | 0
111 |  |  |  |  | 0
112 |  |  |  |  | 0
113 |  |  |  |  | 0
114 |  |  |  |  | 0
115 |  |  |  |  | 0
116 |  |  |  |  | 0
117 |  |  |  |  | 0
118 |  |  |  |  | 0
119 |  |  |  |  | 0
120 |  |  |  |  | 0
121 |  |  |  |  | 0
122 |  |  |  |  | 0
123 |  |  |  |  | 0
124 |  |  |  |  | 0
125 |  |  |  |  | 0
126 |  |  |  |  | 0
127 |  |  |  |  | 0
128 |  |  |  |  | 0
129 |  |  |  |  | 0
130 |  |  |  |  | 0
131 |  |  |  |  | 0
132 |  |  |  |  | 0
133 |  |  |  |  | 0
134 |  |  |  |  | 0
135 |  |  |  |  | 0
136 |  |  |  |  | 0
137 |  |  |  |  | 0
138 |  |  |  |  | 0
139 |  |  |  |  | 0
140 |  |  |  |  | 0
141 |  |  |  |  | 0
142 |  |  |  |  | 0
143 |  |  |  |  | 0
144 |  |  |  |  | 0
145 |  |  |  |  | 0
146 |  |  |  |  | 0
147 |  |  |  |  | 0
148 |  |  |  |  | 0
149 |  |  |  |  | 0