## Schedule
TIME | EVENT/PARTICIPANT |  | I/C | COMMENTS
0800 | Team Breakfast |  | everyone!
0830 | Meet At SIS |  | Kevin
0900 | Print Stuffs |  | Sherrie
0930 | Integration Testing |  | Sherrie
1000 | Move over to Empact |  | All
1030 | Team Briefing |  | Kevin
1100 | Preparation |  | Sherrie
1130 | Setup |  | Development team
1200 | Peter Yang (Empact A) | Yan Shuo (Empact B) | Kevin/Waimun
1230 | Tony Yin (testuser1) | Ethan (testuser2) | Kevin/Waimun
1300 | Lunch Break | Lunch Break
1330 | Shahrin (Empact A) | Nicholas Ong (testuser3) | Kevin/Jervenne
1400 | Keong (testuser4) | Angela (Empact B) | Kevin/Jervenne
1430 | Cynthia Wong (testuser5) |  | Jervenne/Waimun
1500 | Anna Himmanen (testuser7) | Hock Seng (testuser8) | Jervenne/Waimun
1530 | Jun Wei (testuser9) | Kat (testuser10) | Jervenee/Waimun
1600 | Katrin Andrew (testuser23) | Li Wen (testuser11) | Kevin
1630 | Frank Lee (testuser12) | Ashwin (testuser22) | Waimun
1700 | Clarice (testuser13) | Julianna (testuser14) | Cancelled
1730 | Paul (testuser15) | Lastrina (testuser16) | Cancelled
1800 | Xiao Ming (testuser17) | Johann Pacher (testuser6) | Waimun
1830 | Chuen Lam (testuser18) |  | Kevin
1900 | Sheng Yunzhou (testuser19) | Sophee (Empact B / testuser20) | Waimun
1930 | Jabel Tay (testuser21)
2000 | Debrief |  | Kevin
2030 | Pack up |  | everyone!

## Logistics
item | unit | source | comments
extenstion wire | 3 |  | inclusive of 1 standby
laptop | 5
video cam | 3 |  | inclusive of 1 standby
video cam charger
test plan
questionnaire hardcopy
stapler
TO PRINT
feedback form (volunteer) | google docs
feedback form (empact) | google docs
Test plan (volunteer) | drop box
Test plan (empact) | drop box
observation forms | dropbox
execution plan

## Participants details
Name | Contact | Comments

## Links
Feedack form (volunteer)
https://docs.google.com/spreadsheet/viewform?formkey=dGFaNm1yV2x3V0NRcHk5UDhGbFpqQ2c6MQ
Results
https://docs.google.com/spreadsheet/ccc?key=0AuLeuwqZi7r9dGcxbl9ITjdrYWhXU3REOExCbGVJc3c#gid=0
Feedback form (Empact)
Results