## Sheet1
Planned Schedule |  | Actual Schedule |  | Remarks
Modules | Duration | Modules | Duration | Variation (Days) | Status
Iteration 1 - Inception Phase
Define main roles & responsibilities | 1Jul - 1Jul | Define main roles & responsibilities |  |  | 100%
Set team expectations & goals | 1Jul - 1Jul | Set team expectations & goals |  |  | 100%
Risk management plan | 1Jul - 2Jul | Risk management plan |  |  | 100%
Define Metrics | 1Jul - 2Jul | Define Metrics |  |  | 100%
Define rough project schedule | 1Jul - 2Jul | Define rough project schedule |  |  | 100%
Project Management Planning and Requirements Gathering
Iteration 2 - Elaboration 1 Phase
Facebook App Database Connectivity | 16 Jul - 16 Jul | Facebook App Database Connectivity | 16 Jul - 16 Jul | 0 | 100%
Syncing Facebook and B1G1 account | 21 Jul - 22 Jul | Syncing Facebook and B1G1 account | 21 Jul - 22 Jul | 0 | 100%
Facebook App Permissions for Wall post/Information | 17 Jul - 18 Jul | Facebook App Permissions for Wall post/Information | 17 Jul - 18 Jul | 0 | 100%
B1G1 World Database Connectivity | 16 Jul - 17 Jul | B1G1 World Database Connectivity | 16 Jul - 17 Jul | 0 | 100%
Google map implementation | 16 Jul - 17 Jul | Google map implementation | 17 Jul - 17 Jul | 0 | 100%
Geocoding for latitude/longtitude of address | 18 Jul - 19 Jul | Geocoding for latitude/longtitude of address | 19 Jul - 19 Jul | 0 | 100%
Plotting of entities on map | 18 Jul - 20 Jul | Plotting of entities on map | 20 Jul - 20 Jul | 0 | 100%
Animation framework for displaying a single entity | 20Jul - 22 Jul | Animation framework for displaying a single entity | 22 Jul - 22 Jul | 0 | 100%
B1G1 World Widget implementation framework | 20Jul - 22 Jul | B1G1 World Widget implementation framework | 22 Jul - 22 Jul | 0 | 100%
Draft interface layout (Prototype for B1G1 World, Widget and Facebook) | 16Jul - 22 Jul | Draft interface layout (Prototype for B1G1 World, Widget and Facebook) | 16 Jul - 20 Jul | 2 | 100%
Database Deployment | 16Jul - 18 Jul | Database Deployment | 18 Jul - 18 Jul
Milestone : Project Accptance Report and Presentation (5 Aug 2010)
Iteration 3 - Elaboration 2 Phase
XML Structure Standardization for plotting markers on map | 13Aug - 13Aug | XML Structure Standardization for plotting markers on map | 13Aug - 13Aug | 0 | 100%
XML Structure Standardization for details for a particular marker | 13Aug - 14Aug | XML Structure Standardization for details for a particular marker | 13Aug - 14Aug | 0 | 100%
XML Structure Standardization for relationships for a particular marker | 13Aug - 15Aug | XML Structure Standardization for relationships for a particular marker | 13Aug - 15Aug | 0 | 100%
Populating geocode data | 13Aug - 15Aug | Populating geocode data | 13Aug - 16Aug | 1 | 100%
B1G1 World Layout | 14Aug - 19Aug | B1G1 World Layout | 14Aug - 20Aug | 1 | 100%
Individual entities' icons | 15Aug - 19Aug | Individual entities' icons | 15Aug - 19Aug | 0 | 100%
Automated Wallpost Notifications Framework | 13Aug - 19Aug | Automated Wallpost Notifications Framework | 13Aug - 19Aug | 0 | 100%
Facebook application layout | 13Aug - 19Aug | Facebook application layout | 13Aug - 19Aug | 0 | 100%
Iteration 4 - Construction 1 Phase
Filter: By Regions | 2Sept - 4Sept | Filter: By Regions | 2Sept - 5Sept | 1 | 100%
Filter: Projects that the member gives | 2Sept - 4Sept | Filter: Projects that the member gives | 2Sept - 4Sept | 3 | 100%
Filter: Projects that the worthy cause member has | 2Sept - 7Sept | Filter: Projects that the worthy cause member has | 2Sept - 11Sept | 4 | 100%
Filter: Members and Worthy Cause Member that the project has | 2Sept - 9Sept | Filter: Members and Worthy Cause Member that the project has | 2Sept - 10Sept | 1 | 100%
Filter: Leverage of an individual member | 2Sept - 9Sept | Filter: Leverage of an individual member | 2Sept - 13Sept | 4 | 100%
Details Layout for individual entities | 2Sept - 6Sept | Details Layout for individual entities | 2Sept - 6Sept | 0 | 100%
Giving Information Layout for B1G1 World | 2Sept - 9Sept | Giving Information Layout for B1G1 World | 2Sept - 10Sept | 1 | 100%
Facebook like function | 2Sept - 4Sept | Facebook like function | 2Sept - 6Sept | 2 | 100%
Facebook share function | 8Sept - 13Sept | Facebook share function | 8Sept - 16Sept | 3 | 100%
Facebook invite function | 6Sept - 13Sept | Facebook invite function | 6Sept - 16Sept | 3 | 100%
Wall post function (for contribution by companies) | 4Sept - 9Sept | Wall post function (for contribution by companies) | 4Sept - 9Sept | 0 | 100%
Causes Listing Page | 9Sept - 15Sept | Causes Listing Page | 9Sept - 16Sept | 1 | 100%
Individual Cause Page | 16Sept - 20Sept | Individual Cause Page | 16Sept - 20Sept | 0 | 100%
Facebook Analytics - Retriving Number of Likes Cron Job | 5Sept - 11Sept | Facebook Analytics - Retriving Number of Likes Cron Job | 5Sept - 11Sept | 0 | 100%
Main Page and Feedback Page (UI) | 2Sept - 8Sept | Main Page and Feedback Page (UI) | 2Sept - 9Sept | 1 | 100%
Causes Listing and Individual Cause Page Layout | 2Sept - 8Sept | Causes Listing and Individual Cause Page Layout | 2Sept - 9Sept | 1 | 100%
Milestone : Midterm Review and Presentation (28 Sep 2010)
Milestone : User-Accpetance Test 1
Iteration 5- Construction 2 Phase
Filter: Favorite Giving | 4Oct -8Oct | - | Function Dropped | Combined into Filter: Leverage for individual | 0%
Filter: Keyword Search | 3Oct -8Oct | Filter: Keyword Search | 3Oct -12Oct | 1 | 100%
Recommendation Module | 8Oct - 17Oct | Recommendation Module | 8Oct - 17Oct | 0 | 100%
Geocoding control panel | 3Oct - 11Oct | Geocoding control panel | 3Oct - 13Oct | 2 | 100%
Recommendation List | 6Oct - 21Oct | Recommendation List | 6Oct - 23Oct | 2 | 100%
Login/Logout Function | 6Oct - 8Oct | Login/Logout Function | 6Oct - 8Oct | 0 | 100%
B1G1 World Widget with AddThis | 4Oct - 8Oct | B1G1 World Widget with AddThis | 4Oct - 8Oct | 0 | 100%
Did You Know function | 4Oct - 8Oct | Did You Know function | 4Oct - 8Oct | 0 | 100%
B1G1 World Widget | 2Oct - 8Oct | B1G1 World Generic Widget | 2Oct - 11Oct | B1G! World Widget Split into Two | 100%
|  | B1G1 World Customized Widget | 2Oct - 11Oct | Modules | 100%
Milestone : Poster Submission
Milestone : User-Accpetance Test 2
Milestone : Heuristic Evaluation
Iteration 6 - Transition Phase
Debugging | 14Nov - 16Nov | Debugging |  |  | 100%
Final Deployment | 17Nov - 18Nov | Final Deployment |  |  | 100%
Final Testing of Complete System | 19Nov - 21Nov | Final Testing of Complete System |  |  | 100%
User Manual + Documentation | 17Nov - 21Nov | User Manual + Documentation |  |  | 100%
Prepare Presentation Slides | 17Nov - 21Nov | Prepare Presentation Slides |  |  | 100%