## Schedule
SPRINT NO | Task ID |  | MODULE | DESCRIPTION | ESTIMATED TIME TAKEN | HOURS SPENT ACTUAL | STORY POINTS | STATUS
1 | 1 |  | - | Finalize Project Scope | 2 | 1.5 | 2 | Completed
1 | 2 |  |  | Use Case Diagram | 2 | 2 | 2 | Completed
1 | 3 |  |  | ER Diagram | 2 | 3 | 2 | Completed
1 | 4 |  |  | As-Is Diagram | 0.5 | 0.5 | 0.5 | Completed
1 | 5 |  |  | To-Be Diagram | 1 | 1.5 | 1 | Completed
1 | 6 |  |  | Navigation Diagram - Web App | 3.5 | 5 | 3.5 | Completed
1 | 7 |  |  | Navigation Diagram - Mobile App | 4 | 3.5 | 4 | Completed
1 | 8 |  |  | Lo-Fi Wireframing - Admin Web App | 5 | 6 | 5 | Completed
1 | 9 |  |  | Lo-Fi Wireframing - Mobile App | 6 | 6 | 6 | Completed
1 | 10 |  |  | Technical Research-React Native | 3 | 5 | 3 | Completed
1 | 11 |  |  | Technical Research-Nodejs | 3 | 4 | 3 | Completed
2 | 1 | Web App | Web Admin Module (Backend) | WebApp - Login/Logout | 2 |  | 2 | To Be Done
2 | 2 |  |  | WebApp - Change Password | 1 |  | 1 | To Be Done
2 | 3 |  | Web Admin Module (Frontend) | WebApp - Login/Logout | 2 |  | 2 | To Be Done
2 | 4 |  |  | WebApp - Change Password | 1 |  | 1 | To Be Done
2 | 5 | Nodejs | App Account Module (Backend) | MobileApp - Login | 4 |  | 4 | To Be Done
2 | 6 |  |  | MobileApp - Auto-Login (Session) | 3 |  | 3 | To Be Done
2 | 5 | Android | App Account Module (Frontend) | MobileApp - Login | 4 |  | 4 | To Be Done
2 | 6 |  |  | MobileApp - Auto-Login (Session) | 3 |  | 3 | To Be Done
2 | 5 | IOS | App Account Module (Frontend) | MobileApp - Login | 4 |  | 4 | To Be Done
2 | 6 |  |  | MobileApp - Auto-Login (Session) | 3 |  | 3 | To Be Done
2 | 15 |  | - | Scenario | 1 |  | 1 | To Be Done
2 | 16 |  |  | Persona | 1 |  | 1 | To Be Done
2 | 17 |  |  | Git and Viroreact set-up | 0.5 |  | 0.5 | To Be Done
2 | 18 |  |  | Proposal Preparation | 2 |  | 2 | To Be Done
3 | 1 | Android | User Trail Module (Frontend) | View Trail Info | X |  | X | To Be Done
3 | 2 |  |  | Connect to Trail | 0.5 |  | 0.5 | To Be Done
3 | 3 |  |  | View Narrative | 1 |  | 1 | To Be Done
3 | 4 |  |  | Complete Missions(Quiz, Wefie) | 2 |  | 2 | To Be Done
3 | 5 |  |  | View Participants | 0.5 |  | 0.5 | To Be Done
3 | 6 |  |  | View Past Submissions | 4 |  | 4 | To Be Done
3 | 7 |  |  | Upload Submissions | 1 |  | 1 | To Be Done
3 | 8 |  |  | View map with pinned location(with location tracking) | 3.5 |  | 3.5 | To Be Done
3 | 9 | Nodejs | User Trail Module (Backend) | View Trail Info | X |  | X | To Be Done
3 | 10 |  |  | Connect to Trail | 1 |  | 1 | To Be Done
3 | 11 |  |  | View Narrative | 0.5 |  | 0.5 | To Be Done
3 | 12 |  |  | Complete Missions(Quiz, Wefie) | 2 |  | 2 | To Be Done
3 | 13 |  |  | View Participants | 0.75 |  | 0.75 | To Be Done
3 | 14 |  |  | View Past Submissions | 4 |  | 4 | To Be Done
3 | 15 |  |  | Upload Submissions | 3 |  | 3 | To Be Done
3 | 16 |  |  | View map with pinned location(with location tracking) | 2 |  | 2 | To Be Done
3 | 25 | IOS | User Trail Module (Frontend) | View Trail Info | X |  | X | To Be Done
3 | 26 |  |  | Connect to Trail | 0.5 |  | 0.5 | To Be Done
3 | 27 |  |  | View Narrative | 1 |  | 1 | To Be Done
3 | 28 |  |  | Complete Missions(Quiz, Wefie) | 2 |  | 2 | To Be Done
3 | 29 |  |  | View Participants | 0.5 |  | 0.5 | To Be Done
3 | 30 |  |  | View Past Submissions | 4 |  | 4 | To Be Done
3 | 31 |  |  | Upload Submissions | 1 |  | 1 | To Be Done
3 | 32 |  |  | View map with pinned location(with location tracking) | 3.5 |  | 3.5 | To Be Done
3 | 33 |  | - | Hi-Fi Wireframing design for admin WebApp |  |  |  | To Be Done
3 | 34 |  |  | MobileApp - Sequence Diagrams | 2 |  | 2 | To Be Done
3 | 35 |  |  | User Testing Preparation | 1.5 |  | 1.5 | To Be Done
3 | 36 |  |  | Acceptance Preparation | 3 |  | 3 | To Be Done
4 | 1 | WebApp | Admin Trail Monitoring Module (Backend) | WebApp - Monitor Groups' Progress | 0.5 |  | 0.5
4 | 2 |  |  | WebApp - Monitor Groups' Location | 2 |  | 2
4 | 3 |  |  | WebApp - Monitor and manage Leaderboard | 0.5 |  | 0.5
4 | 4 |  |  | WebApp - Monitor and manage Activity Feed | 1.5 |  | 1.5
4 | 5 |  |  | WebApp - Monitor and manage Mission Submission | 1 |  | 1
4 | 6 |  |  | WebApp - Monitor Trail Duration | 1.5 |  | 1.5
4 | 7 |  | Admin Upload Module Backend | WebApp - Upload Multimedia (Images and Videos) | 2.5 |  | 2.5
4 | 8 |  |  | WebApp - View Uploads | 2 |  | 2
4 | 9 |  | Admin Trail Monitoring Module Frontend | WebApp - Monitor Groups' Progress | 1 |  | 1
4 | 10 |  |  | WebApp - Monitor Groups' Location | 2.5 |  | 2.5
4 | 11 |  |  | WebApp - Monitor and manage Leaderboard | 1 |  | 1
4 | 12 |  |  | WebApp - Monitor and manage Activity Feed | 1 |  | 1
4 | 13 |  |  | WebApp - Monitor and manage Mission Submission | 1.5 |  | 1.5
4 | 14 |  |  | WebApp - Monitor Trail Duration | 1 |  | 1
4 | 15 |  | Admin Upload Module Frontend | WebApp - Upload Multimedia (Images and Videos) | 0.5 |  | 0.5
4 | 16 |  |  | WebApp - View Uploads | 1.5 |  | 1.5
4 | 17 | Android | User Trail Module (Frontend) | MobileApp - View Activity Feed | 1.5 |  | 1.5
4 | 18 |  |  | MobileApp - View Leaderboard | 1 |  | 1
4 | 19 | IOS | User Trail Module (Frontend) | MobileApp - View Activity Feed | 2 |  | 2
4 | 20 |  |  | MobileApp - View Leaderboard | 1 |  | 1
4 | 21 |  | - | Hi-Fi Wireframing Design for Mobile App | 5 |  | 5
5 | 1 | Web App | Hotspot Module (Backend) | WebApp - Add/Edit/Remove Hotspot Location | 0.5 |  | 0.5
5 | 2 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 0.5 |  | 0.5
5 | 3 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 0.5 |  | 0.5
5 | 4 |  | Hotspot Module (Frontend) | WebApp - Add/Edit/Remove Hotspot Location | 1 |  | 1
5 | 5 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 1 |  | 1
5 | 6 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 1.5 |  | 1.5
5 | 7 |  | Admin AR Game Module (Backend) | WebApp - Implement Mini AR Game (6 Types) | 20 |  | 20
5 | 8 |  |  | WebApp - Admin Preview AR Game | 20 |  | 20
5 | 9 |  | Admin AR Game Module (Frontend) | WebApp - Implement Mini AR Game (6 Types) | 20 |  | 20
5 | 10 |  |  | WebApp - Admin Preview AR Game | 20 |  | 20
6 | 1 | Web App | Narrative Module (Backend) | WebApp - Add/Edit/Remove Text/Story | 1.25 |  | 1.25
6 | 2 |  |  | WebApp - Attach photos or videos to Narrative | 2 |  | 2
6 | 3 |  | Narrative Module (Frontend) | WebApp - Add/Edit/Remove Text/Story | 1 |  | 1
6 | 4 |  |  | WebApp - Attach photos or videos to Narrative | 2.5 |  | 2.5
6 | 5 | Nodejs | User AR Game Module (Backend) | MobileApp - Activate AR based on hotspot location | 2 |  | 2
6 | 6 |  |  | MobileApp - Play AR game which reveals Narrative | 1.5 |  | 1.5
6 | 7 | Android | User AR Game Module (Frontend) | MobileApp - Activate AR based on hotspot location | 1 |  | 1
6 | 8 |  |  | MobileApp - Play AR game which reveals Narrative | 2.5 |  | 2.5
6 | 9 | IOS | User AR Game Module (Frontend) | MobileApp - Activate AR based on hotspot location | 1 |  | 1
6 | 10 |  |  | MobileApp - Play AR game which reveals Narrative | 2.5 |  | 2.5
6 | 11 | Nodejs | AR Tutorial Module (Backend) | MobileApp - Introductory Video | 3 |  | 3
6 | 12 |  |  | MobileApp - Introductory AR Game Interaction | 1.5 |  | 1.5
6 | 13 | Android | AR Tutorial Module (Frontend) | MobileApp - Introductory Video | 2.5 |  | 2.5
6 | 14 |  |  | MobileApp - Introductory AR Game Interaction | 3 |  | 3
6 | 15 | IOS | AR Tutorial Module (Frontend) | MobileApp - Introductory Video | 2.5 |  | 2.5
6 | 16 |  |  | MobileApp - Introductory AR Game Interaction | 3 |  | 3
7 | 1 | Web App | Mission Module (Backend) | WebApp - Add/Edit/Remove mission description | 1 |  | 1
7 | 2 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Video - Drag & Drop - Match 3 | 2 |  | 2
7 | 3 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission description | 1.5 |  | 1.5
7 | 4 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Video - Drag & Drop - Match 3 | 2 |  | 2
7 | 5 |  | Admin Trail Creation Module (Backend) | WebApp - Add Trail Info | X |  | X
7 | 6 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 0.5 |  | 0.5
7 | 7 |  |  | WebApp - Add/Edit/Remove AR game to trail map | 0.5 |  | 0.5
7 | 8 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 0.5 |  | 0.5
7 | 9 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 0.5 |  | 0.5
7 | 10 |  |  | WebApp - Add/Edit/Remove Participants | X |  | X
7 | 11 |  |  | WebApp - Add/Edit/Remove Groups | 0.5 |  | 0.5
7 | 12 |  | Admin Trail Creation Module (Frontend) | WebApp - Add Trail Info | X |  | X
7 | 13 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 1 |  | 1
7 | 14 |  |  | WebApp - Add/Edit/Remove AR game to trail map | 1 |  | 1
7 | 15 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 1 |  | 1
7 | 16 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 1 |  | 1
7 | 17 |  |  | WebApp - Add/Edit/Remove Participants | X |  | X
7 | 18 |  |  | WebApp - Add/Edit/Remove Groups | 1 |  | 1
7 | 19 | Nodejs | Mission Module (Backend) | MobileApp - Complete missions (Video, Drag & Drop, Match 3) | 2.5 |  | 2.5
7 | 20 | Android | Mission Module (Frontend) | MobileApp - Complete missions (Video, Drag & Drop, Match 3) | 2 |  | 2
7 | 21 | IOS | Mission Module (Frontend) | MobileApp - Complete missions (Video, Drag & Drop, Match 3) | 2 |  | 2
8 | 1 | Web App | Notification Module (Backend) | WebApp - Announcer Feature | 2.5 |  | 2.5
8 | 2 |  |  | WebApp - Reminder Feature | 2 |  | 2
8 | 3 |  | Feedback Module (Backend) | WebApp - Collate and generate feedback report | .1.5 |  | .1.5
8 | 4 |  | Notification Module (Frontend) | WebApp - Announcer Feature | 1 |  | 1
8 | 5 |  |  | WebApp - Reminder Feature | 1 |  | 1
8 | 6 |  | Feedback Module (Frontend) | WebApp - Collate and generate feedback report | 2 |  | 2
8 | 7 | Nodejs | Notification Module (Backend) | MobileApp - View Notification | 2 |  | 2
8 | 8 |  |  | MobileApp - Receive Notification | 1.5 |  | 1.5
8 | 9 |  | Feedback Module (Backend) | MobileApp - Feedback form submission | 1 |  | 1
8 | 10 | Android | Notification Module (Frontend) | MobileApp - View Notification | 1.5 |  | 1.5
8 | 11 |  |  | MobileApp - Receive Notification | 2 |  | 2
8 | 12 |  | Feedback Module (Frontend) | MobileApp - Feedback form submission | 1.5 |  | 1.5
8 | 13 | IOS | Notification Module (Frontend) | MobileApp - View Notification | 1.5 |  | 1.5
8 | 14 |  |  | MobileApp - Receive Notification | 2 |  | 2
8 | 15 |  | Feedback Module (Frontend) | MobileApp - Feedback form submission | 1.5 |  | 1.5
9 | 1 | Web App | Data Analytics (Backend) | WebApp - Record Trail data | 1 |  | 1
9 | 2 |  |  | WebApp - Display summary report of past data on trail | 1 |  | 1
9 | 3 |  | Data Analytics (Frontend) | WebApp - Record Trail data | 2 |  | 2
9 | 4 |  |  | WebApp - Display summary report of past data on trail | 3 |  | 3
9 | 5 |  | Automation Module (Backend) | WebApp - Automated assignment of participants to groups based on criteria | 3 |  | 3
9 | 6 |  |  | WebApp - Automated assignment of missions to trails | 3 |  | 3
9 | 7 |  | Automation Module (Frontend) | WebApp - Automated assignment of participants to groups based on criteria | 1 |  | 1
9 | 8 |  |  | WebApp - Automated assignment of missions to trails | 1 |  | 1
10 | 1 | Web App | Usability Module (Backend) | WebApp - Admin Help Page | 3 |  | 3
10 | 2 |  | Usability Module (Frontend) | WebApp - Admin Help Page | 3 |  | 3
10 | 3 | Nodejs | Usability Module (Backend) | MobileApp - User Help Page | 3 |  | 3
10 | 4 | Android | Usability Module (Frontend) | MobileApp - User Help Page | 3 |  | 3
10 | 5 | IOS | Usability Module (Frontend)) | MobileApp - User Help Page | 3 |  | 3
10 | 6 |  | - | User Testing Preparation | 3 |  | 3
10 | 7 |  | - | MidTerm Preparation | 4 |  | 4
11 | 1 | Web App | Additional AR Game (Backend) | WebApp - Add/Edit/Remove Mini Hotspots | 1 |  | 1
11 | 2 |  |  | WebApp - Add/Edit/Remove Narrative to mini hotspot | 1 |  | 1
11 | 3 |  | Additional AR Game (Frontend) | WebApp - Add/Edit/Remove Mini Hotspots | 1.5 |  | 1.5
11 | 4 |  |  | WebApp - Add/Edit/Remove Narrative to mini hotspot | 1.5 |  | 1.5
12 | 1 | Web App | Additional Trail Modes (Backend) | WebApp - Additional Trail Modes | 1 |  | 1
12 | 2 |  | Additional Trail Modes (Frontend) | WebApp - Additional Trail Modes | 2 |  | 2
12 | 3 | Nodejs | Additional AR implementation (Backend) | MobileApp - Add any additional AR implementation | 3 |  | 3
12 | 4 | Android | Additional AR implementation (Frontend) | MobileApp - Add any additional AR implementation | 5 |  | 5
12 | 5 | IOS | Additional AR implementation (Frontend) | MobileApp - Add any additional AR implementation | 5 |  | 5
13 | 1 |  | - | UI Improvement (Webapp, MobileApp) | 10 |  | 10
13 | 2 |  | - | POSTER PREPARATION | 5 |  | 5
14 | 1 |  | - | Documentation Review | 3 |  | 3
14 | 2 |  | - | Preparation for Project Handover | 4 |  | 4
14 | 3 |  | - | FINAL PRESENTATION PREPARATION | 5 |  | 5
15 | 1 |  | - | Preparation for Final Presentation | 4 |  | 4

## Metrics
Product Burndown
Sprint | Estimated Story Points | Actual Story Points Completed | Story Points Remaining
0 | 390.5 | 0 | 390.5
1 | 358.5 | 32 | 358.5
2 | 327 | 0 | 358.5
3 | 282.25 | 0 | 358.5
4 | 250.25 | 0 | 358.5
5 | 165.25 | 0 | 358.5
6 | 132.5 | 0 | 358.5
7 | 112 | 0 | 358.5
8 | 89 | 0 | 358.5
9 | 74 | 0 | 358.5
10 | 52 | 0 | 358.5
11 | 47 | 0 | 358.5
12 | 31 | 0 | 358.5
13 | 16 | 0 | 358.5
14 | 4 | 0 | 358.5
15 | 0 | 0 | 358.5
Sprint | Story Points Completed
0 | 0
1 | 32
2 | 0
3 | 0
4 | 0
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
Average | 2
Rolling Avg. | 10.6667
Number of Bugs
Iteration No. | Low | High | Critical | Bug Metric Score
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 |  |  |  | 0
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0