## Sheet1
Sprint | Date | Type | Change Request | Issued By | Change Description | Decision | Action Taken | Status of Request
2 | 2016-06-09 | Scopes | Maintenance of the existing system | Sponsor | Sponsor would like the team to do support for the website | Reject | This task is out the team's project scope, but team helped sponsors' freelancer developers to troubleshoot the errors | Closed
3 | 2016-06-27 | Schedule | Shift Admin Login & Log out to sprint 4 | Team | Team was familarising themselves with new coding language such as Python | Accept | PM assigned the incompleted tasks as an immediate tasks to complete in Sprint 4 | Closed
4 | 2016-06-30 | Functionality | Integrate the QR code feature that freelancer had created with Hook Coffee's application that Team had ceated | Sponsor | After scanning the QR code, the sticker will be printed out and transaction will take place. As this is part of processing order that Team had implemented, therefore is is a high-priority to schedule the Integration of QR Code as a task in next sprint | Accept | PM assigned the 'Integration with QR code' as a task in Sprint 5 | Closed
6 | 2016-07-26 | Schedule | Allocate this sprint's coding tasks to the next sprint | Team | Team wants to focus on catering to the points raised by the testers (UAT) to ensure that system has a more intuitive interface | Accept | PM re-schedule the coding tasks to the next sprint. This sprint is mainly focused on improving the application based on UAT's feedback | Closed
6 | 2016-08-02 | Stakeholder Management | Team discussed with sponsors to come out with a communication protocol between Team, IPMAN and Freelancer developers | Team | Team found out that conflicts arise during integration as IPMAN and developer team simultaneously commit to the same test server. | Accept | Team came out with a communication protocol. Team will liaise with the developer team through Trello and Slack. | Closed
6 | 2016-08-02 | Scopes | Sponsor wants an extra option to 'include backlog' to view the number of all backlog orders to be packed till today | Sponsor | Sponsors wants to the the option to view the backlog orders so that he can continue to pack those orders that he had not completed | Accept | Team accepted this change as this is necessary for his business workflow to continue. PM assigned this to Sprint 8 | Closed
7 | 2016-08-21 | Schedule | Shifted Automated clustering of customers For Email Marketing Campaign to Sprint 11 | Team | The feature of Smart Marketing tracking information and analysis of users churn rate have to be completed so that we can collect meaningful data to do the automated clustering of customers | Accept | PM shift the task to Sprint 11 which is to be implemented after the completion of smart marketing campaign | Closed
8 | 2016-08-23 | Scopes | Remove good-to-have functions (FacebookBot & Recommend the amount of coffee to roast) | Team | It is because Team would like to focus on dahboard graph, smart martketing, analysis and inventory system which would provide more value to sponsors | Accept | Team had discussed with sponsors and sponsors had also agreed. Sponsors also proposed to add in the customers' lifetime value & users' churn rate to be shown in the dashboard graph. | Closed
9 | 2016-09-13 | Scopes | Add in the feature 'Print Address' per customer in the customer's page | Sponsor | Sponsors wants to have the option to be able to print out the address for each customer so that he can print out the address sticker if he accidentally tore the stickers after processing customers' orders | Accept | Team decided to implement the change as it was a feature that was completed Sprint 8 so it does not takes up much time to implement this feature as this only affects the front-end. Thus, PM assigned this task in the current sprint, Sprint 9. | Closed
9 | 2016-09-13 | Scopes | Add 'new sign-ups' feature in the Dashboard Summary Page. Remove 'top-k coffee type' feature | Sponsor | Sponsor would like to know the number of customers who sign up from yesterday. | Accept | PM assigned new task to know the number of 'new sign-ups' and remove the 'top-k coffee type' feature. | Closed
9 | 2016-09-13 | Scopes | Integrate Intercomm logic which freelancer's developer had implemented our application | Sponsor | Team have to integrate the intercomm because it affects the Smart marketing, dashboard and analysis modules | Accept | PM assigned the Intercomm integration as a task to be completed in Sprint 10 as it is high priority | Closed
10 | 2016-09-20 | Methodology | Change in methodology in the deployment | Team | As Team IPMAN was building our changes on top of our current sprint work, thus there were incomplete features which can cause a lot of issues if we were to deploy immediately as we have not tested all the features. With a new branch for deployment, team IPMAN would be able to resolve the bugs and deploy immediately. | Accept | Team added another branch for deployment, so in total there are 2 branches now. | Closed