## Login & Logout
S/N | Functionalities | Description | Test Inputs | Pre-Conditions | Test Procedure | Exepected Result | Actual Result | Pass/Fail | Tested in Sprint | Remarks
1 | Login | Successful user login with valid credentials. | 01. Username: User1 02. Password: 1234 | Nil | 01. User types in username. 02. User types in password. 03. User clicks on "Let's Go!" button. | 01. System to redirect user to home page upon successful login. | 01. System redirected user to home page upon successful login. | Pass | 10 | Nil
2 | Login | Unsuccessful user login with empty fields (all). (Validation) | Nil | Nil | 01. User clicks on "Let's Go!" button. | 01. System to display message "Please fill out this field" for username textbox only. 02. System to not redirect user to home page. | 01. System displayed message "Please fill out this field" for username textbox only. 02. System does not redirect user to home page. | Pass | 10 | Nil
3 | Login | Unsuccessful user login with one empty field. (Validation) | 01. Username: User1 | Nil | 01. User types in username. 02. User clicks on "Let's Go!" button. | 01. System to display message "Please fill out this field" for password textbox only. 02. System to not redirect user to home page. | 01. System displayed message "Please fill out this field" for password textbox only. 02. System does not redirect user to home page. | Pass | 10 | Nil
4 | Login | Unsuccessful user login with one empty field. (Validation) | 01. Password: 1234 | Nil | 01. User types in password. 02. User clicks on "Let's Go!" button. | 01. System to display message "Please fill out this field" for username textbox only. 02. System to not redirect user to home page. | 01. System displayed message "Please fill out this field" for username textbox only. 02. System does not redirect user to home page. | Pass | 10 | Nil
5 | Login | Unsuccessful user login with valid username and invalid password. (Validation) | 01. Username: User1 02. Password: 0000 | Nil | 01. User types in username. 02. User types in password. 03. User clicks on "Let's Go!" button. | 01. System to display message "Invalid username/password." 02. System to not redirect user to home page. | 01. System displayed message "Invalid username/password." 02. System does not redirect user to home page. | Pass | 10 | Nil
6 | Login | Test max characters limits with white spaces. | 01. Username: "!#$!!!DF#11234FD.." 02. Password: "!#$!!!DF#11234FD.." | Nil | 01. User types in username. 02. User types in password. 03. User clicks on "Let's Go!" button. | 01. System to display message "Please enter a valid username/password!" 02. System to not redirect user to home page. | 01. System to display message "Please enter a valid username / password!" 02. System to not redirect user to home page. | Pass | 10 | Can inprove this part by limiting the input characters.
7 | Logout | Successful user logout. | Nil | 01. User is logged into system. | 01. User clicks dropdown list. 02. User clicks "Log Out" button. | 01. System to redirect user to login page. | 01. System redirected user to login page. | Pass | 10 | Nil

## Knowledge Challenge
S/N | Functionalities | Description | Test inputs | Pre-Conditions | Test Procedure | Exepected Result | Actual Result | Pass/Fail | Tested in sprint | Remarks
1 | Knowledge Challenge (Suggest Question) | Suggest question for voting of questions. | 01. Question: How tall is Michael Jordan? 02. Answer 1: 1.7m 03. Answer 2: 1.8m 04. Answer 3: 1.9m | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Suggest Question" image. 03. User types in question. 04. User types in answer 1. 05. User types in answer 2. 06. User types in answer 3. 07. User clicks "Suggest Now!" button. | 01. System to display success message "The question was successfully added!". | 01. System displayed success message "The question was successfully added!". | Pass | 10 | Nil
2 | Knowledge Challenge (Suggest Question) | Self-suggested question will not appear for voting by oneself. | Nil | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Vote Answer" image. | 01. System to not display suggested question. | 01. System did not display suggested question. | Pass | 10 | Nil
3 | Knowledge Challenge (Suggest Question) | Suggest questions validations. | Nil | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Suggest Question" image. 03. User clicks Suggest Now!" button. | 01. System to display error message "Please fill out this field" for the question textarea. | 01. System displayed error message "Please fill out this field" for the question textarea. | Pass | 10 | Nil
4 | Knowledge Challenge (Suggest Question) | Suggested questions from Test Case 1 to be visible for voting by user. | Nil | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Vote Answer" image. | 01. System to display suggested questions from Test Case 1. | 01. System displayed suggested questions from Test Case 1. | Pass | 10 | Extremely long questions and answers distort the display in Vote Answer page.
5 | Knowledge Challenge (Suggest Question) | Test max characters limits. | 01. Question: "!@#!@%!Acv.22123…" 02. Answer 1: "!@#!@%!Acv.22123…" 03. Answer 2: "!@#!@%!Acv.22123…" 04. Answer 3: "!@#!@%!Acv.22123…" | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Suggest Question" image. 03. User types in question until max limit. 04. User types in answer 1 until max limit. 05. User types in answer 2 until max limit. 06. User types in answer 3 until max limit. 07. User clicks "Suggest Now!" button. | 01. System to display success message "The question was successfully added!". | 01. System displayed success message "The question was successfully added!". | Pass | 10 | Nil
6 | Knowledge Challenge (Vote Answer) | Voting for an answer for suggested question. | Nil | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Vote Answer" image. 03. User clicks "Vote Now!" button. 04. User clicks 1st option. | 01. System to display success message "Your vote has been captured!". 02. System to display voting results in percentage. | 01. System displayed success message "Your vote has been captured!". 02. System displayed voting results in percentage. | Pass | 10 | Extremely long questions and answers distort the display in Vote Answer page and relative pages.
7 | Knowledge Challenge (Send Challenge) 1-to-1 | Sending easy difficulty individual challenge to another user. | 01. Title: One-on-One Challenge 02. Opponent: User1 | 1. User is logged into system. 2. There are 3 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Individual Challenge". 04. User clicks "Easy" (3 questions). 05. User types in challenge title. 06. User clicks "Select Questions" button. 07. User selects 3 questions (radio buttons). 08. User clicks "Add to Challenge" button. 09. User clicks "Choose a User" dropdown list. 10. User clicks selects opponent. 11. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed success message "You have successfully sent a challenge". | Pass | 10 | It will be better to exclude oneself from the "Choose a User" dropdown list. It can select more than 3 questions. Should automatically prevent checking of more than 3 questions. There is a typo-error for the "Choose User" tab. It should be called "Choose User".
8 | Knowledge Challenge (Send Challenge) 1-to-1 | Sending medium difficulty individual challenge to another user. | 01. Title: One-on-One Challenge 02. Opponent: User1 | 1. User is logged into system. 2. There are 6 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Individual Challenge". 04. User clicks "Medium" (6 questions). 05. User types in challenge title. 06. User clicks "Select Questions" button. 07. User selects 6 questions (radio buttons). 08. User clicks "Add to Challenge" button. 09. User clicks "Choose a User" dropdown list. 10. User clicks selects opponent. 11. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed success message "You have successfully sent a challenge". | Pass | 10 | It will be better to exclude oneself from the "Choose a User" dropdown list. It can select more than 3 questions. Should automatically prevent checking of more than 3 questions. There is a typo-error for the "Choose User" tab. It should be called "Choose User".
9 | Knowledge Challenge (Send Challenge) 1-to-1 | Sending hard difficulty individual challenge to another user. | 01. Title: One-on-One Challenge 02. Opponent: User1 | 1. User is logged into system. 2. There are 9 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Individual Challenge". 04. User clicks "Hard" (9 questions). 05. User types in challenge title. 06. User clicks "Select Questions" button. 07. User selects 9 questions (radio buttons). 08. User clicks "Add to Challenge" button. 09. User clicks "Choose a User" dropdown list. 10. User clicks selects opponent. 11. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed success message "You have successfully sent a challenge". | Pass | 10 | It will be better to exclude oneself from the "Choose a User" dropdown list. It can select more than 3 questions. Should automatically prevent checking of more than 3 questions. There is a typo-error for the "Choose User" tab. It should be called "Choose User".
10 | Knowledge Challenge (Send Challenge) 1-to-1 | Test max characters limits with white spaces. | 01. Title: "!#$!!!DF#11234FD.." 02. Opponent: User1 | 1. User is logged into system. 2. There are 3 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Individual Challenge". 04. User clicks "Easy" (3 questions). 05. User clicks "Select Questions" button. 06. User selects 3 questions (radio buttons). 07. User clicks "Add to Challenge" button. 08. User clicks "Choose a User" dropdown list. 09. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed "Bad Request. Your browser sent a request that this server could not understand". | Fail | 10 | Nil
11 | Knowledge Challenge (Send Challenge) 1-to-Many | Sending easy difficulty individual challenge to another group. | 01. Title: One-on-Many Challenge 02. Opponent: Tanjong Katong School | 1. User is logged into system. 2. There are 3 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Easy" (3 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 3 questions (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed success message "You have successfully sent a challenge". | Pass | 10 | Own school should be automatically omitted.
12 | Knowledge Challenge (Send Challenge) 1-to-Many | Sending medium difficulty individual challenge to another group. | 01. Title: One-on-Many Challenge 02. Opponent: Tanjong Katong School | 1. User is logged into system. 2. There are 6 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Medium" (6 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 6 questions (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed success message "You have successfully sent a challenge". | Pass | 10 | Upon pressing the "back" button on browser, and clicks on "Send Challenge" button again, it will cause two challenges to be sent to the opponent group.
13 | Knowledge Challenge (Send Challenge) 1-to-Many | Sending hard difficulty individual challenge to another group. | 01. Title: One-on-Many Challenge 02. Opponent: Tanjong Katong School | 1. User is logged into system. 2. There are 9 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Hard" (9 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 9 questions (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System displayed success message "You have successfully sent a challenge". | Pass | 10 | Upon pressing the "back" button on browser, and clicks on "Send Challenge" button again, it will cause two challenges to be sent to the opponent group.
14 | Knowledge Challenge (Send Challenge) 1-to-Many | Test max characters limits with white spaces. | 01. Title: "!#$!!!DF#11234FD.." 02. Opponent: Tanjong Katong School | 1. User is logged into system. 2. There are 3 questions available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Easy" (3 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 3 questions (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System to display success message "You have successfully sent a challenge". | Pass | 10 | Nil
15 | Knowledge Challenge (Send Challenge) Many-to-Many | Start new easy difficulty collaborative challenge to another group. | 01. Title: Many-on-Many Challenge 02. Opponent: Broadrick Secondary School | 1. User is logged into system. 2. There is 1 question available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Easy" (1 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 1 question (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully formed part of a school challenge". | 01. System displayed success message "You have successfully formed part of a school challenge". | Pass | 10 | Nil
16 | Knowledge Challenge (Send Challenge) Many-to-Many | Start new medium difficulty collaborative challenge to another group. | 01. Title: Many-on-Many Challenge 02. Opponent: Broadrick Secondary School | 1. User is logged into system. 2. There is 1 question available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Easy" (1 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 1 question (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully formed part of a school challenge". | 01. System displayed success message "You have successfully formed part of a school challenge". | Pass | 10 | Nil
17 | Knowledge Challenge (Send Challenge) Many-to-Many | Start new hard difficulty collaborative challenge to another group. | 01. Title: Many-on-Many Challenge 02. Opponent: Broadrick Secondary School | 1. User is logged into system. 2. There is 1 question available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Easy" (1 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 1 question (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully formed part of a school challenge". | 01. System displayed success message "You have successfully formed part of a school challenge". | Pass | 10 | User extremely likely to choose 3 questions. Can consider changing it to radio button if user is merely choosing one question.
18 | Knowledge Challenge (Send Challenge) Many-to-Many | Take part in forming a challenge. | Nil | 1. User is logged into system. 2. There is 1 question available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Form School Challenge". 05. User clicks "Form Challenge" (1 questions). 06. User clicks "Select Questions" button. 07. User selects 1 question (check boxes). 08. User clicks "Form Challenge" button. | 01. System to display success message "You have successfully formed a challenge!". | 01. System displayed success message "You have successfully formed a challenge!". | Pass | 10 | "Forming School Challenge" and "Start New Challenge" seems like the same thing.
19 | Knowledge Challenge (Send Challenge) Many-to-Many | Test max characters limits with white spaces. | 01. Title: "!#$!!!DF#11234FD.." 02. Opponent: Broadrick Secondary School | 1. User is logged into system. 2. There is 1 question available. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Send Challenge" image. 03. User clicks "Collaborative Challenge". 04. User clicks "Start New Challenge". 05. User clicks "Easy" (1 questions). 06. User types challenge title. 07. User clicks "Select Questions" button. 08. User selects 1 question (check boxes). 09. User clicks "Add to Challenge" button. 10. User clicks on "Choose School" tab. 11. User clicks on "Choose School" dropdown list. 12. User clicks on opponent school. 13. User clicks "Send Challenge" button. | 01. System to display success message "You have successfully sent a challenge". | 01. System to display success message "You have successfully sent a challenge". | Pass | 10 | Nil
20 | Knowledge Challenge (Accept Challenge) "Your Challenge" | User to accept individual challenge from another user, and answers questions. (Correct answers) | Nil | 1. User is logged into system. 2. There is an individual challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "Accept" from "Your Challenge". 04. User clicks correct answer for 1st question. 05. User clicks correct answer for 2nd question. 06. User clicks correct answer for 3rd question. | 01. System to display challenge results - Questions - Status Status to display all questions are answered correctly. | 01. System displayed challenge results - Questions - Status Status displayed all questions are answered correctly. | Pass | 10 | Nil
21 | Knowledge Challenge (Accept Challenge) "Your Challenge" | User to accept individual challenge from another user, and answers questions. (Incorrect answers) | Nil | 1. User is logged into system. 2. There is an individual challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "Accept" from "Your Challenge". 04. User clicks wrong answer for 1st question. 05. User clicks wrong answer for 2nd question. 06. User clicks wrong answer for 3rd question. | 01. System to display challenge results - Questions - Status Status to display all questions are answered incorrectly. Links are provided to post the incorrectly answered question in Little Desk. | 01. System displayed challenge results - Questions - Status Status displayed all questions are answered wrongly. Links provided are unable to post to Little Desk with "CakePHP: the rapid development php framework". | Fail | 10 | Nil
22 | Knowledge Challenge (Accept Challenge) "Your Challenge" | User to view another challenge after completing an individual challenge. | Nil | 1. User is logged into system. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "Accept" from "Your Challenge". 04. User clicks any answer for 1st question. 05. User clicks any answer for 2nd question. 06. User clicks any answer for 3rd question. 07. User clicks on "Another Challenge?" button. | 01. System to display Knowledge Challenge Arena page. 02. System to display all challenges. | 01. System displayed Knowledge Challenge Arena page. 02. System displayed all challenges. | Pass | 10 | This page can only be accessible after completing a challenge. Instead of having this page, user can be redirected to the Knowledge Challenge accept challenge page.
23 | Knowledge Challenge (Accept Challenge) "Your Class Challenge" | User to accept class challenge, and answers questions. (Correct answers) | Nil | 1. User is logged into system. 2. There is a class challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My Class Challenge" button. 03. User clicks "Accept" challenge. 04. User clicks correct answer for 1st question. 05. User clicks correct answer for 2nd question. 06. User clicks correct answer for 3rd question. | 01. System to display challenge results - Questions - Status Status to display all questions are answered correctly. | 01. System displayed challenge results - Questions - Status Status displayed all questions are answered correctly. | Pass | 10 | Nil
24 | Knowledge Challenge (Accept Challenge) "Your Class Challenge" | User to accept class challenge (Incorrect answers) | Nil | 1. User is logged into system. 2. There is a class challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My Class Challenge" button. 03. User clicks "Accept" challenge. 04. User clicks wrong answer for 1st question. 05. User clicks wrong answer for 2nd question. 06. User clicks wrong answer for 3rd question. | 01. System to display challenge results - Questions - Status Status to display all questions are answered incorrectly. Links are provided to post the incorrectly answered question in Little Desk. | 01. System displayed challenge results - Questions - Status Status displayed all questions are answered wrongly. Links provided are unable to post to Little Desk with "CakePHP: the rapid development php framework". | Fail | 10 | Nil
25 | Knowledge Challenge (Accept Challenge) "Your Class Challenge" | User to access all challenges after completing class challenge. | Nil | 1. User is logged into system. 2. There is a class challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My Class Challenge" button. 03. User clicks "Accept" challenge. 04. User clicks wrong answer for 1st question. 05. User clicks wrong answer for 2nd question. 06. User clicks wrong answer for 3rd question. 07. User clicks on "Another Challenge?" button. | 01. System to display Knowledge Challenge Arena page. 02. System to display all challenges. | 01. System displayed Knowledge Challenge Arena page. 02. System displayed all challenges. | Pass | 10 | It leads to the "individual" challenge page. Maybe the user can be directed back to the class challenges instead since he or she had just completed the class challenge.
26 | Knowledge Challenge (Accept Challenge) "Your School Challenge" | User to accept school challenge (Correct answers) | Nil | 1. User is logged into system. 2. There is a school challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My School Challenge" button. 03. User clicks "Accept" challenge. 04. User clicks correct answer for 1st question. 05. User clicks correct answer for 2nd question. 06. User clicks correct answer for 3rd question. | 01. System to display challenge results - Questions - Status Status to display all questions are answered correctly. | 01. System displayed challenge results - Questions - Status Status displayed all questions are answered correctly. | Pass | 10 | Nil
27 | Knowledge Challenge (Accept Challenge) "Your School Challenge" | User to accept school challenge (Incorrect answers) | Nil | 1. User is logged into system. 2. There is a school challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My School Challenge" button. 03. User clicks "Accept" challenge. 04. User clicks wrong answer for 1st question. 05. User clicks wrong answer for 2nd question. 06. User clicks wrong answer for 3rd question. | 01. System to display challenge results - Questions - Status Status to display all questions are answered incorrectly. Links are provided to post the incorrectly answered question in HelpDesk. | 01. System displayed challenge results - Questions - Status Status displayed all questions are answered wrongly. Links provided are unable to post to Little Desk with "CakePHP: the rapid development php framework". | Fail | 10 | Some links can lead the user to Little Desk. However, some causes error.
28 | Knowledge Challenge (Accept Challenge) "Your School Challenge" | User to access all challenges after completing school challenge. | Nil | 1. User is logged into system. 2. There is a school challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My School Challenge" button. 03. User clicks "Accept" challenge. 04. User clicks wrong answer for 1st question. 05. User clicks wrong answer for 2nd question. 06. User clicks wrong answer for 3rd question. 07. User clicks on "Another Challenge?" button. | 01. System to display Knowledge Challenge Arena page. 02. System to display all challenges. | 01. System displayed Knowledge Challenge Arena page. 02. System displayed all challenges. | Pass | 10 | Nil
29 | Knowledge Challenge (Challenge Status) Individual Challenge to user | Viewing challenge sent from another user to user. | Nil | 1. User is logged into system. 2. There is an existing challenge sent from another user to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Challenge Status". | 01. System to display challenge status sent from another user to user. | 01. System displayed challenge status sent from another user to user. | Pass | 10 | Nil
30 | Knowledge Challenge (Challenge Status) Class Challenge to user | Viewing challenge sent from another class to user. | Nil | 1. User is logged into system. 2. There is an existing challenge sent from another user to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Challenge Status". 03. User clicks "My Class Challenge". | 01. System to display challenge status sent from another class to user. | 01. System displayed challenge status sent from another class to user. | Pass | 10 | Nil
31 | Knowledge Challenge (Challenge Status) School Challenge to user | Viewing challenge sent from another school to user. | Nil | 1. User is logged into system. 2. There is an existing challenge sent from another user to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Challenge Status". 03. User clicks "My School Challenge". | 01. System to display challenge status sent from another school to user. | 01. System displayed challenge status sent from another school to user. | Pass | 10 | Nil
32 | Knowledge Challenge (Challenge Status) Individual Challenge to others | Viewing challenge sent from user to another user. | Nil | 1. User is logged into system. 2. There is an existing challenge sent from another user to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Challenge Status". 03. User clicks "Challenge to others" | 01. System to display challenge status sent from user to another user. | 01. System displayed challenge status sent from user to another user. | Pass | 10 | Nil
33 | Knowledge Challenge (Challenge Status) Class Challenge to others | Viewing challenge sent from class to another user. | Nil | 1. User is logged into system. 2. There is an existing challenge sent from another user to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Challenge Status". 03. User clicks "Challenge to others". 04. User clicks "My Class Challenge". | 01. System to display challenge status sent from class to another user. | 01. System displayed challenge status sent from class to another user. | Pass | 10 | Nil
34 | Knowledge Challenge (Challenge Status) School Challenge to others | Viewing challenge sent from another school to user. | Nil | 1. User is logged into system. 2. There is an existing challenge sent from another user to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Challenge Status". 03. User clicks "Challenge to others". 04. User clicks "My School Challenge". | 01. System to display challenge status sent from another school to user. | 01. System displayed challenge status sent from school to another user. | Pass | 10 | Nil
35 | Knowledge Challenge (Reject Challenge) Individual Challenge | User to reject individual challenge. | Nil | 1. User is logged into system. 2. There is an individual challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "Reject" button. 04. User clicks "Ok" button. | 01. System to not display the rejected challenge anymore. | 01. System does not display the rejected challenge anymore. | Pass | 10 | Nil
36 | Knowledge Challenge (Reject Challenge) Class Challenge | User to reject class challenge. | Nil | 1. User is logged into system. 2. There is a class challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My Class Challenge" button. 04. User clicks "Reject". 05. User clicks "Ok" button. | 01. System to not display the rejected challenge anymore. | 01. System does not display the rejected challenge anymore. | Pass | 10 | Nil
37 | Knowledge Challenge (Reject Challenge) School Challenge | User to reject school challenge. | Nil | 1. User is logged into system. 2. There is a class challenge sent to user. | 01. User clicks "Knowledge Challenge" tab. 02. User clicks "Accept Challenge" dropdown list. 03. User clicks "My School Challenge" button. 04. User clicks "Reject". 05. User clicks "Ok" button. | 01. System to not display the rejected challenge anymore. | 01. System does not display the rejected challenge anymore. | Pass | 10 | Nil

## Little Desk
S/N | Functionalities | Description | Test inputs | Pre-Conditions | Test Procedure | Exepected Result | Actual Result | Pass/Fail | Tested in sprint | Remarks
1 | Little Desk | Posting a question in Little Desk. | 01. Question: Why birds fly when we try to approach them? | 01. User is logged into system. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "Animals" category. 03. User types in question. 04. User clicks "Ask Now!". | 01. System to display successful message "You have successfully posted a question!". 02. System to display question asked directly below the question asking bar. | 01. System displayed successful message "You have successfully posted a question!". 02. System displayed question asked directly below the question asking bar. | Pass | 10 | Nil
2 | Little Desk | Posting a question in Little Desk. (Validation) | Nil | 01. User is logged into system. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "Animals" category. 03. User clicks "Ask Now!". | 01. System to display error message "Please write something before asking". | 01. System displayed error message "Please write something before asking". | Pass | 10 | Nil
3 | Little Desk | Searching for a question. (Question posted before) | 01. Search keyword: Bird | 01. User is logged into system. 02. A question related to "bird" has been asked. | 01. User clicks "Little Desk" navigation bar. 02. User clicks search bar textbox. 03. User types in search keyword in search bar. 04. User clicks "Search Now!" button. | 01. System to display search results based on "bird" keyword. | 01. System displayed search results based on "bird" keyword. | Pass | 10 | When "bird" keyword is typed into the search bar twice, it does not return bird result at all. Search refinement can be done.
4 | Little Desk | Searching for a question. (Question not posted before) | 01. Search keyword: Dinosaur | 01. User is logged into system. 02. A question related to "dinosaur" has not been asked. | 01. User clicks "Little Desk" navigation bar. 02. User clicks search bar textbox. 03. User types in search keyword in search bar. 04. User clicks "Search Now!" button. | 01. System to display message "No results found!". | 01. System displayed message "No results found!". | Pass | 10 | Nil
5 | Little Desk | Searching for a question. (Empty search) | Nil | 01. User is logged into system. 02. A question has been asked. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "Search Now!" button. | 01. System to display all questions results. | 01. System displayed all questions results. | Pass | 10 | Nil
6 | Little Desk | Answering a question. | 01. Answer: The birds are afraid that you may attack them. | 01. User is logged into system. 02. A question has been asked. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "Animals" category. 03. User clicks on question. 04. User clicks on answer textbox. 05. User types in answer. 06. User clicks "Reply Now!". | 01. System to display message "Replied successfully! Thank you!". 02. System to display replied answer to question. | 01. System displayed message "Replied successfully! Thank you!". 02. System displayed replied answer to question. | Pass | 10 | Nil
7 | Little Desk | Liking a question (Like). | Nil | 01. User is logged into system. 02. A question has been asked. | 01. User clicks "Little Desk" navigation bar. 02. User clicks animal category. 03. User clicks on a question. 04. User clicks "Like" button. | 01. System to turn "Like" button into "Liked" wording. | 01. System turned "Like" button into "Liked" wording. | Pass | 10 | The question should be able to "un-like" after "like".
8 | Little Desk | Adding a collaborator. | Nil | 01. User is logged into system. 02. A question has been asked. 03. User has at least one friend. | 01. User clicks "Little Desk" navigation bar. 02. User clicks animal category. 03. User clicks on a question. 04. User clicks on "Invite your friends!" dropdown list. 05. User clicks on friend. 06. User clicks on "Invite Now!" button. | 01. System to display message "You have successfully invited Michael as collaborator!". 02. System to display "Michael" button in "Fellow Collaborators". | 01. System displayed message "You have successfully invited Michael as collaborator!". 02. System displayed "Michael" button in "Fellow Collaborators". | Pass | 10 | Nil
9 | Little Desk | Removing a collaborator. | Nil | 01. User is logged into system. 02. A question has been asked. 03. Question has at least one collaborator. | 01. User clicks "Little Desk" navigation bar. 02. User clicks animal category. 03. User clicks on a question. 04. User clicks on a collaborator dropdown list. 05. User clicks "Remove". | 01. System to display message "You have successfully removed Michael as a collaborator!". 02. System to not display "Michael" button in "Fellow Collaborators". | 01. System displayed message "You have successfully removed Michael as a collaborator!". 02. System does not display "Michael" button in "Fellow Collaborators". | Pass | 10 | Nil
10 | Little Desk | Viewing question asked by user. (My Questions) | Nil | 01. User is logged into system. 02. A question has been asked by user. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "My Questions". | 01. System to display questions asked by user. | 01. System displayed questions asked by user. | Pass | 10 | Nil
11 | Little Desk | Viewing question asked by another user. (Tutee's Questions) | Nil | 01. User is logged into system. 02. A question has been asked by another user and assigned user as tutee. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "My Friend's Question". | 01. System to display questions assigned to user. | 01. System displayed questions assigned to user. | Pass | 10 | Nil
12 | Little Desk | Getting a random question asked by another user. | Nil | 01. User is logged into system. 02. A question has been asked by another user. | 01. User clicks "Little Desk" navigation bar. 02. User clicks "Get a Random Question". | 01. System to redirect user to a question asked by another user. | 01. System redirected user to a question asked by another user. | Pass | 10 | Nil

## Little Classroom
S/N | Functionalities | Description | Test inputs | Pre-Conditions | Test Procedure | Exepected Result | Actual Result | Pass/Fail | Tested in sprint | Remarks
1 | Create Classroom | User creates a classroom. | 01. Classroom Title: Animal Title | 01. User is logged into the system. | 01. User clicks on "Little Classroom" tab. 02. User clicks on "Create Lesson" button. 03. User clicks on "Animal" category. 04. User types the classroom title into textarea. 05. User clicks on "Create" button. | 01. System to display classroom page. | 01. System displayed classroom page. | Pass | 10 | Nil
2 | Add New Chapter | User adds a new chapter to classroom. | 01. Chapter Title: Animal Chapter Title | 01. User is logged into the system. 02. A lesson has been created. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Add a New Chapter" button. 05. User types chapter title into textbox. 06. User clicks "Add Now!" button. | 01. System to display new chapter added. | 01. System displayed new chapter added. | Pass | 10 | Nil
3 | Add a New Paragraph | User adds a new paragraph to a chapter. | 01. Paragraph Content: Animal Introduction. | 01. User is logged into the system. 02. A lesson has been created. 03. A chapter has been added. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Add a new paragraph". 05. User selects a chapter from dropdown list. 06. User types in the paragraph. 07. User clicks "Add Now!" button. | 01. System to display the paragraph. | 01. System displayed the paragraph. | Pass | 10 | Nil
4 | Edit Paragraph | User edits content of a paragraph. | 01. Paragraph Content: New Animal Introduction. | 01. User is logged into the system. 02. A lesson has been created. 03. A chapter has been added. 04. A paragraph has been added. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "edit" button. 05. User types new paragraph content. 06. User clicks "Save!" button. | 01. System to display the newly edited paragraph. | 01. System displayed the newly edited paragraph. | Pass | 10 | Nil
5 | Delete Paragraph | User deletes paragraph. | Nil | 01. User is logged into the system. 02. A lesson has been created. 03. A chapter has been added. 04. A paragraph has been added. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "delete" button. 05. User clicks "Ok" button. | 01. System to not display the deleted paragraph. | 01. System does not display the deleted paragraph. | Pass | 10 | Nil
6 | Edit Chapter Title | User edits the chapter title. | Chapter Title: New Chapter Title | 01. User is logged into the system. 02. A lesson has been created. 03. A chapter has been added. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Edit Chapter Title" button. 05. User types chapter title into textbox. 05. User clicks "Saves!" button. | 01. System to display new edited chapter title. | 01. System displayed new edited chapter title. | Pass | 10 | Nil
7 | Delete Chapter | User deletes chapter. | Nil | 01. User is logged into the system. 02. A lesson has been created. 03. A chapter has been added. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Delete Chapter" button. 05. User selects chapter to delete from dropdown list. 06. User clicks "Delete Now!" button. | 01. System to not display the deleted chapter. | 01. System did not display the deleted chapter. | Pass | 10 | There is no confirmation message. If user accidentally deletes it. The content will be gone.
8 | View Collaborators | User views collaborator(s) for lesson. | Nil | 01. User is logged into the system. 02. A lesson has been created. 03. There are existing collaborators. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "View collaborators". | 01. User to be redirected back to Little Classroom collaborator page. 02. System to display all collaborators. | 01. User redirected back to Little Classroom collaborator page. 02. System displayed all collaborators. | Pass | 10 | Nil
9 | Add collaborator | User adds collaborator(s) for lesson. | Nil | 01. User is logged into the system. 02. A lesson has been created. 03. User has at least two friends. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "View collaborators". 05. User clicks dropdown list in "Invite an Editor". 06. User selects a friend "Zee". 07. User clicks "Invite Now!" button. 08. User clicks dropdown list in "Invite an Editor". 09. User selects a friend "Michael". 10. User clicks "Invite Now!" button. | 01. System to display both collaborators added. | 01. System displays only the second collaborator added. | Fail | 10 | First user cannot be added. Only the second user can be added.
10 | Delete Collaborator | User deletes collaborator(s) for lesson. | Nil | 01. User is logged into the system. 02. A lesson has been created. 03. User has at least two collaborators in lesson. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "View collaborators". 05. User clicks "delete" link for first collaborator. 06. User clicks "Ok" button. 07. User clicks "delete" link for second collaborator. 08. User clicks "Ok" button. | 01. System to not display both collaborators. | 01. System does not display both collaborators. | Pass | 10 | Nil
11 | Publish Classroom | User to publish classroom. | Nil | 01. User is logged into the system. 02. There is an existing un-published classroom. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Publish this classroom" button. 05. User clicks "Yes do it!" button. | 01. System to display success message "You have successfully published the classroom!". | 01. System displayed success message "You have successfully published the classroom!". | Pass | 10 | Nil
12 | Un-publish Classroom | User to un-publish classroom. | Nil | 01. User is logged into the system. 02. There is an existing published classroom. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Un-Publish this classroom" button. 05. User clicks "Yes do it!" button. | 01. System to display success message "You have successfully un-published the classroom!". | 01. System displayed success message "You have successfully un-published the classroom!". | Pass | 10 | Nil
13 | Delete Classroom | User to delete a classroom. | Nil | 01. User is logged into the system. 02. There is an existing classroom. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User clicks "Delete this Classroom". 05. User clicks "Throw it away!". | 01. User to be redirected back to Little Classroom. 02. System to display success message "Classroom has been deleted successfully". | 01. User redirected back to Little Classroom. 02. System displayed success message "Classroom has been deleted successfully". | Pass | 10 | Nil
14 | Search for Lesson (Available lesson) | User to search for lesson. | 01. Search Keyword: Animals | 01. User is logged into the system. 02. There is an existing classroom. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User types search keyword. 05. User clicks "Search Now!" button. | 01. System to display search results related to "animals". | 01. System displayed search results related to "animals". | Pass | 10 | Nil
15 | Search for Lesson (Unavailable lesson) | User to search for lesson. | 01. Search Keyword: ABC | 01. User is logged into the system. | 01. User clicks "Little Classroom" tab. 02. User clicks "My Classroom" dropdown list. 03. User clicks classroom title. 04. User types search keyword. 05. User clicks "Search Now!" button. | 01. System to display empty search results with message "No results". | 01. System displayed empty search results with message "No results". | Pass | 10 | Nil
16 | View other classrooms | User to view classrooms not created by user. | Nil | 01. User is logged into the system. 02. There is an existing other classroom. | 01. User clicks "Little Classroom" tab. 02. User clicks "Other classrooms" dropdown list. | 01. System to display all the other classrooms. | 01. System displayed all the other classrooms. | Pass | 10 | Nil
17 | View Random classroom | User to view random classroom | Nil | 01. User is logged into the system. 02. There is an existing other classroom. | 01. User clicks "Little Classroom" tab. 02. User clicks "Other classrooms" dropdown list. 03. User clicks "View a random lesson". | 01. System to display a lesson to user. | 01. System displayed a lesson to user. | Pass | 10 | Nil