## bug tracker
Bug Tracker
|  |  | Number of Forwarded bugs | 0
|  |  | Number of In Progress bugs | 0
|  |  | Number of Outstanding bugs | 2
|  |  | Number of Unfixed Bugs | 2
|  |  | Number of Fixed Bugs | 42
Bug Id | Description | Type | Level of Difficulty (estimated) | Severity Index | Assigned To | Reported By | Time Reported (Iteration No.) | Deadline | Status | Fixed By | Time Fixed (Iteration No.) | Re-tested By
1 | Tweets in timeline constantly flashing | UI | 4 | 0.25 | Soe Thet Aung | Aung Myint Thein | 1 |  | Fixed | Soe Thet Aung | 5 | Khine Pwint Wah
2 | UI not compatible with various screen res. | UI | 3 | 0.1875 | Kyaw Moe Hein | Soe Thet Aung | 2 | 2011-08-10 | Fixed | Soe Thet Aung | 2 | Kyaw Moe Hein
3 | "Share" button overlap with 3D | UI | 1 | 0.0625 | Kyaw Moe Hein | Aung Myint Thein | 2 |  | Fixed | Kyaw Moe Hein | 3 | Khine Pwint Wah
4 | Gliding doesn't go to correct placemark | Logic | 4 | 1 | Kyaw Moe Hein | Kyaw Moe Hein | 2 |  | Fixed | Thandar Tun | 5 | Aung Myint Thein
5 | Can't get data from DB | Data (eg. DB) | 1 | 0.1875 | Thandar Tun | Soe Thet Aung | 3 | 2011-08-15 | Fixed | Thandar Tun | 3 | Soe Thet Aung
6 | No location tagged tweet appear in trend | Logic | 1 | 0.25 | Aung Myint Thein | Aung Myint Thein | 3 |  | Fixed | Aung Myint Thein | 3 | Soe Thet Aung
7 | Accordion effect doesn't work | UI | 4 | 0.25 | Soe Thet Aung | Kyaw Moe Hein | 4 |  | Fixed | Soe Thet Aung | 4 | Kyaw Moe Hein
8 | After clicking on LostnFound, tweet-updates in all trends become lost and found tweets | Logic | 1 | 0.25 | Aung Myint Thein | Soe Thet Aung | 4 |  | Fixed | Aung Myint Thein | 4 | Soe Thet Aung
9 | Replacing placemarks in wrong places | Logic | 4 | 1 | Thandar Tun | Kyaw Moe Hein | 4 | 2011-09-22 | Fixed | Soe Thet Aung | 5 | Thandar Tun
10 | Tweet tagged with #sgSMU appear at SIS | Logic | 1 | 0.25 | Thandar Tun | Soe Thet Aung | 4 | 2011-09-23 | Fixed | Soe Thet Aung | 5 | Thandar Tun
11 | No. of trends greater than 5 | Syntax | 1 | 0.125 | Soe Thet Aung | Aung Myint Thein | 5 |  | Fixed | Aung Myint Thein | 5 | Aung Myint Thein
12 | Glide to each tweet has to hide the above levels. | Logic | 2 | 0.5 | Thandar Tun | Aung Myint Thein | 5 | 2011-09-24 | Fixed | Kyaw Moe Hein | 5 | Thandar Tun
13 | Glide to each tweet has to open the callout | Logic | 1 | 0.25 | Kyaw Moe Hein | Aung Myint Thein | 5 | 2011-09-24 | Fixed | Kyaw Moe Hein | 5 | Aung Myint Thein
14 | Trends need to check regular expression such as #01-12 | Logic | 3 | 0.75 | Phyo Wint Wint Tun | Aung Myint Thein | 5 | 2011-09-28 | Fixed | Phyo Wint Wint Tun | 5 | Aung Myint Thein
15 | Library walls showing strange texture | UI | 2 | 0.125 | Aung Myint Thein | Kyaw Moe Hein | 5 | 2011-09-20 | Fixed | Aung Myint Thein | 5 | Kyaw Moe Hein
16 | Trends and Lost n found tweets hasn't shown up in 3D model | Logic | 3 | 0.75 | Kyaw Moe Hein | Soe Thet Aung | 5 | 2011-09-28 | Fixed | Thandar Tun | 6 | Phyo Wint Wint Tun
17 | No scoll bar in tweet pop up box when required. | UI | 2 | 0.125 | Kyaw Moe Hein | Aung Myint Thein | 6 | 2011-09-28 | Fixed | Kyaw Moe Hein | 5 | Phyo Wint Wint Tun
18 | LostnFound not working at all | Logic | 4 | 1 | Aung Myint Thein | Khine Pwint Wah | 6 | 2011-10-17 | Fixed | Aung Myint Thein | 6 | Phyo Wint Wint Tun
19 | Sign in is not working | Logic | 3 | 0.75 | Phyo Wint Wint Tun | Khine Pwint Wah | 6 | 2011-10-17 | Fixed | Soe Thet Aung | 7 | Kyaw Moe Hein
20 | Though it is trend, it shows only one tweet | Logic | 3 | 0.75 | Soe Thet Aung | Thandar Tun | 6 | 2011-10-18 | Fixed | Soe Thet Aung | 8
21 | wrong tweet's bouncing | Logic | 2 | 0.5 | Thandar Tun | Phyo Wint Wint Tun | 7 |  | Fixed | Thandar Tun | 7 | Kyaw Moe Hein
22 | Case sensitive for location tag | Logic | 1 | 0.25 | Thandar Tun | Phyo Wint Wint Tun | 7 | 2011-10-18 | Fixed | Soe Thet Aung | 8 | Aung Myint Thein
23 | Remove first location tag | Logic | 3 | 0.75 | Phyo Wint Wint Tun | Aung Myint Thein | 7 |  | Fixed | Kyaw Moe Hein | 7 | Aung Myint Thein
24 | Close the popup after tweeted | UI | 2 | 0.125 | Phyo Wint Wint Tun | Aung Myint Thein | 7 |  | Fixed | Kyaw Moe Hein | 8 | Aung Myint Thein
25 | LostnFound reloading | UI | 1 | 0.0625 | Aung Myint Thein | Aung Myint Thein | 8 | 2011-11-30 | Fixed | Aung Myint Thein | 8 | Khine Pwint Wah
27 | Close slide panal after user switch the tabs between Timeline and trends | UI | 2 | 0.125 | Kyaw Moe Hein | Aung Myint Thein | 8 | 2011-11-11 | Fixed | Kyaw Moe Hein | 8 | Aung Myint Thein
28 | Clear option for tweet in model after tweeted and be ready for next tweet | Logic | 2 | 0.5 | Kyaw Moe Hein | Khine Pwint Wah | 8 | 2011-11-11 | Fixed | Kyaw Moe Hein | 8 | Phyo Wint Wint Tun
29 | priority level of the location doesn't work | Logic | 2 | 0.5 | Phyo Wint Wint Tun | Aung Myint Thein | 8 |  | Fixed | Phyo Wint Wint Tun | 8 | Thandar Tun
30 | in Trend page new tweets are not created in 3D model once it clicks | Logic | 2 | 0.5 | Thandar Tun | Aung Myint Thein | 8 | 2011-11-14 | Fixed | Kyaw Moe Hein | 8 | Aung Myint Thein
31 | once we open the tweet box, the previous location is set | Logic | 2 | 0.5 | Kyaw Moe Hein | Kyaw Moe Hein | 8 | 2011-11-14 | Fixed | Kyaw Moe Hein | 8 | Aung Myint Thein
32 | Some "Just now" don't get updated | UI | 2 | 0.125 | Soe Thet Aung | Soe Thet Aung | 8 | 2011-11-13 | Fixed | Soe Thet Aung | 8 | Soe Thet Aung
33 | Zoom too much when click on "Show in 3D" (Not a bug acutally, just to report) | UI | 1 | 0.0625 | Thandar Tun | Soe Thet Aung | 8 | 2011-11-13 | Outstanding
34 | Normal Tweeting shouldn't include the username like reply function (#sgSMU tag is not added in yet) | Logic | 2 | 0.5 | Kyaw Moe Hein | Phyo Wint Wint Tun | 8 | 2011-11-14 | Fixed | Kyaw Moe Hein | 8 | Aung Myint Thein
35 | Location filter error in LostnFound | Logic | 3 | 0.75 | Aung Myint Thein | Phyo Wint Wint Tun | 7 | 2011-11-14 | Fixed | Aung Myint Thein | 7 | Aung Myint Thein
36 | Trends - "Displaying Result" title is not showing in safari. | UI | 2 | 0.125 | Kyaw Moe Hein | Aung Myint Thein | 8 | 2011-11-14 | Outstanding
37 | Jquery String is together with the tweet. (?? Is causing the problem) | Logic | 3 | 0.75 | Kyaw Moe Hein | Thandar Tun | 8 | 2011-11-14 | Fixed | Aung Myint Thein | 8 | Soe Thet Aung
38 | After tweeting for Trend and reloading the application, only shows our tweets | Logic | 4 | 1 | Soe Thet Aung | Phyo Wint Wint Tun | 8 |  | Fixed | Soe Thet Aung
39 | if only one tweet in Trend then the 3D model doesn't show the placemark | Logic | 3 | 0.75 | Thandar Tun | Aung Myint Thein | 8 | 2011-11-14 | Fixed | Thandar Tun | 8 | Aung Myint Thein
40 | for location tag, we shouldn't allow the user to choose only level | Logic | 2 | 0.5 | Kyaw Moe Hein | Thandar Tun | 7 |  | Fixed | Kyaw Moe Hein | 7 | Aung Myint Thein
41 | for location tag can be chosen many times | Logic | 3 | 0.75 | Kyaw Moe Hein | Kyaw Moe Hein | 7 | 2011-11-14 | Fixed | Kyaw Moe Hein | 7 | Aung Myint Thein
42 | "wht on your mind" image is not appeared in google chrome | UI | 2 | 0.125 | Kyaw Moe Hein | Phyo Wint Wint Tun | 8 | 2011-11-14 | FIxed | Kyaw Moe Hein | 8 | Aung Myint Thein
43 | Click SMU on side navigation, "You r now at SOA" | Logic | 1 | 0.25 | Kyaw Moe Hein | Aung Myint Thein | 8 | 2011-11-14 | Fixed | Kyaw Moe Hein
44 | Bouncing in trends doesn't stop. | UI | 2 | 0.125 | Thandar Tun | Aung Myint Thein | 8 | 2011-11-14 | Fixed | Kyaw Moe Hein | 8 | Aung Myint Thein
46 | Geo point checking need to expand to 103.84 | Logic | 1 | 0.25 | Soe Thet Aung | Aung Myint Thein | 8 | 2011-11-14 | Fixed | Soe Thet Aung | 8
1 | by including photo feature to post the picture of the item | [5 empty] | Future feature
2 | 3D is moving around and it's quite attractive. If you can put into some music, it would be better. And as it is kinda social networking, it would be better to change the font. | [5 empty] | Future feature
[13 empty] | Bug Type | Value
[13 empty] | UI | 1
[13 empty] | Syntax | 2
[13 empty] | Data (eg. DB) | 3
[13 empty] | Logic | 4
Member
Aung Myint Thein
Khine Pwint Wah
Kyaw Moe Hein
Phyo Wint Wint Tun
Soe Thet Aung
Thandar Tun
Status
Fixed
Forwarded
In Progress
Outstanding