## Sheet1
S/N | Sprint | Issue/Change | Description | Suggested by | Hours spent on analysing the issue/brainstorm | Hours spent on to implement the changes | Total Hours to Recover
1 | 8 | Make changes to the Architectual diagram to explain Technical Complexity | Architectural diagram should show clearly the ownership of the codes | Supervisor | 3 | 2 | 5 | 8 | 4
2 | 8 | Brainstorm on how to provide Business Value for Sponsors | Team should aim to create value for the sponsors in ways that they didn’t have before | Supervisor | 2 | 2 | 4 | 9 | 1.3333
3 | 8 | Implement new metrics | Team currently have bug metrics and project metrics, but what are the other metrics that we can look at? | Supervisor | 3 | 2 | 5 | 10 | 1.6875
4 | 8 | Re-send function | Re-send orders were greyed as team originally thought that the logic was only active orders should be resent but team had changed it to shipped orders to be resent | Sponsors | 1 | 1 | 2
5 | 9 | Establish how Smart Marketing feature can create value for our sponsors | Supervisor wants Team IPMAN to brainstorm on the value provided for the sponsors and how it had impacted their business | Supervisor | 1 | 0.5 | 1.5
6 | 9 | Modify the Module Level Layer Diagram we have created | Supervisor highlighted that JSON views on the diagram should be changed to JSON as it was confusing with React Views | Supervisor | 0.5 | 0.5 | 1
7 | 9 | Improves on the presentation of the Architecture Diagram created by Team IPMAN | Supervisor suggested that we should illustrate how we have solved the duplicates of codes issues | Supervisor | 0.5 | 1 | 1.5
8 | 10 | Make changes to the explanation of HookCoffee's Business Process | Supervisor suggested that team should give paint a scenario to the audience with details so that it is more realistic | Supervisor | 1 | 1 | 2
9 | 10 | Make changes to the technical complexity with examples so that audience can follow through | Supervisor suggested us to include the screenshots of the various pages and keep our explanation simple | Supervisor | 0.5 | 1 | 1.5
10 | 10 | Choose a few highlights to present for the Project Management | Supervisor mentioned that we do not have time to present everything hence only choose to focus on 2-3 main points | Supervisor | 1 | 1 | 2
11 | 10 | Sponsor requested for a pop-up modal to appear after scanning the QR code for 'special gift' | The pop-up model only appears if the process code was entered instead of using the QR scanner. The issue was that the QR code field was not taken into account | Sponsors | 0.25 | 1 | 1.25