## Bug report
Iteration 5 Bug Metric
| (Total Score to be placed here) | 27
| Unresolved Score | 0
Defect ID | Defect Description | Steps to reproduce | Severity | Score | Status | Created by | Assigned to | Photo
1 | Pausing the podcast for the second time causes ReFokus to stop. | Start a session, play the podcast, pause, play and pause again. | Medium | 5 | Solved | Chan Jing Vin | Benjamin Chia
2 | When the timer between sessions count down to zero and the phone is in a sleep state, ReFokus stops. | Complete a session, stay on the timer screen and turn off the screen before waiting for the timer to hit zero. | Medium | 5 | Solved | Chan Jing Vin | Benjamin Chia
3 | Keyboard stays on the screen upon updating of password/email, disallowing the ability for users to see the confirmation status. | User resets email/password and clicks update. | Medium | 5 | Solved | Chan Jing Vin | Heng Kok Chin
4 | CSV is not able to print columns with the same question name. | User sets the same question name for a program and downloads the relevant CSV. | Medium | 5 | Solved | Chan Jing Vin | Yeo Cheng Fu
5 | Days since beginning of program is not changed, always reflects 1 | User starts a session. | Low | 1 | Solved | Chan Jing Vin | Benjamin Chia
6 | Unclear that users could scroll for the minutes in self practice. | User clicks self-practice in the hamburger menu. From here, the user attempts to change the timing in minutes for self practice. | Low | 1 | Solved | Chan Jing Vin | Gareth Shaun Ng
7 | Slider scale is not obvious to users. | User reaches the post survey and uses the slider. | Medium | 5 | Solved | Chan Jing Vin | Heng Kok Chin