## Dashboard Legend
Project Progress Dashboard Legend
|  | Stage | Level of Completion | Description | %
| Bank Teller Application | Back End | Developed Base Case | Back End Service (TIBCO Designer Project) success flow has been completed locally.
|  |  |  | Service can only receive correct inputs and returns correct outputs. | 12.5%
|  |  | Developed Error Flows | Back End Service (TIBCO Designer Project) error flows have been completed locally.
|  |  |  | Service can now receive any inputs and return both successful outputs and respective error codes. | 25%
|  |  | Deployed to Server | Back End Service (TIBCO Designer Project) has been deployed to SMU tBank’s Server and has been integrated with Service Mediation Layer.
|  |  |  | Service can now be accessed by any Retail Banking Channel. | 37.5%
|  |  | Integrated | Java classes have been created to allow Branch Teller Web Application User Interface to call the respective Back End Service(s).
New Service is integrated into TIBCO process
|  |  |  | Handover to front end team. | 50%
|  | UI | Developed Basic UI | A basic user interface has been created.
|  |  |  | Branch Teller Web Application is able to call locally deployed Back End Service(s). | 62.5%
|  |  | Developed Complete UI | User Interface with form validations has been completed.
|  |  |  | Branch Teller Web Application is able to call locally deployed Back End Service(s). | 75%
|  | Testing | Testing - Junit Testing | Functional Testing - Junit Testing | 87.5%
|  |  | Testing - HTMLUnit Testing | Functional Testing - HTMLUnit Testing | 100%
|  | Completed | Completed | Use Case is tested and completed. | 100%
|  |  | Level of Completion | Description | %
| Others |  | In Progress | Task is currently in progress, under development. | 25%
|  |  | Completed Locally | Task has been completed locally | 50%
|  |  | Deployed | Task has been completed locally and deployed | 75%
|  |  | Completed | Deliverables have been deployed in the server / executed throughout SMU tBank. | 100%
|  |  | Completed & Handed Over | Deliverables have been handed over if required | 100%
Start
Finish
Finish
Start

## Dashboard
Project Progress | updated 10 October 2013 | Legend: | Completed | Current Iteration 9 | Next Iteration 10 | Later
Branch Teller, Services & Integration | Branch Teller Use Cases | Services Involved | [8 empty] | % Complete | Remarks
| Login | - |  |  |  |  | Develop Basic UI | Develop Complete UI |  |  | 100%
| Party Create | Party Customer Create |  |  |  |  | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 100%
|  | MDM Customer Type Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 100%
| Party User PIN Create | Party Login Create |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI |  |  | 100%
|  | Party Login Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI |  |  | 100%
| Party Read & Update | Party Customer Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 100%
|  | Party Customer Update | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 100%
|  | Party Customer Read IC | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 100%
| Customer’s Accounts Dashboard | Account List Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
|  | Transaction History Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Account Deposit Create | Account Deposit Create | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | MDM Product Type Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | Product Parameters Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Manage Customer’s Deposit Accounts | Account List Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Account Deposit Read & Update | Account Deposit Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | Account Deposit Update | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | Product Parameters Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Account Loan Create | Account Loan Create | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | MDM Product Type Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | Product Parameters Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Manage Customer’s Loan Accounts | Account List Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Account Loan Read & Update | Account Loan Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | Account Loan Update | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 82.5%
|  | Product Parameters Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Transaction Deposit | Transaction Deposit | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Transaction Withdrawal | Transaction Withdrawal | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
|  | Transaction SMS Notification |  |  | Taking Over | Integrate |  |  |  |  | 100%
| Transaction History Read | Transaction History Read | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
| Payment Credit Transfer Bill Payment | Payment Credit Transfer Create | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
|  | MDM Billing Organization Read List |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
|  | Transaction SMS Notification |  |  | Taking Over | Integrate |  |  |  |  | 100%
| Payment Loan Repayment Full | Transaction _FullLoanRepayment_Create | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
|  | Product_LoanFullRepayment_Calculate |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
| Payment Loan Repayment Partial | Payment Loan Repayment Partial | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 75%
|  | Product_LoanPartialRepayment_Calculate |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
|  | Product_LoanInstallment_Calculate |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
| Direct Debit Authorization | Payment_DirectDebitAuthorization_Create |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
|  | Payment_DirectDebitAuthorization_Delete |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
|  | Payment_DirectDebitAuthorizationList_Read |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
|  | MDM Billing Organization Read List |  |  | Taking Over | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 25%
X-Factor (Credit Approval) | Credit Approval | Credit Approval | Develop Base Case | Develop Error Flows | Deploy to Server | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 0%
| Business Rules | [5 empty] | Develop | Develop UI (Guvnor) |  |  | 0%
X-Factor (Teaching Tool) | Modify Business Rules Parameters | [5 empty] | Develop | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 0%
| Generate Data Set | [5 empty] | Develop | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 0%
| Run Test | Credit Approval |  |  |  | Integrate | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 0%
| Display Test Results | [5 empty] | Develop Basic UI | Develop Complete UI | Testing - Junit | Testing - HTMLUnit | 0%
Others | Back End Systems & Miscellaneous
| Modify Common Data Model - Account |  | Modify | [7 empty] | 100%
| Modify Common Data Model - Transaction |  | Modify | [7 empty] | 100%
| Business Rules Management System Analysis |  | Analyse | [7 empty] | 100%
| Drools Server Local Setup |  | Setup | Deploy to Server | [6 empty] | 100%
| Drools Guvnor Rules Repository Local Setup |  | Setup | Deploy to Server | [6 empty] | 100%
| Sample Business Rules Set |  | Develop | Hand Over | [6 empty] | 100%
| Next Best Offer Service Prototype (TIBCO Designer Project) |  | Develop Base Case | Hand Over | [6 empty] | 100%
[9 empty] | Development Tasks Complete |  | 68.12%
|  | Tasks | 27 | 24 | 39 | 40 | 44 | 44 | 40 | 40 | 298
|  | Incomplete | 1 | 1 | 1 | 4 | 14 | 14 | 27 | 33 | 95
|  | Complete | [8 empty] | 203
|  | % Complete | [8 empty] | 68.12%

## Scope
Project Scope
Branch Teller Functionality
| Branch Teller Web Application | Functions | Description
1 | Branch Teller Web Application [For Branch Tellers] | Login | Branch teller and supervisor logs into the application
2 |  | Party Create | Users can enter in a new customer’s details to register with the bank
3 |  | Party User PIN Create | Users can create new login credentails for use in other Retail Banking Channels
4 |  | Party Read & Update | Users can retrieve and edit an existing customer’s details
5 |  | Customer’s Accounts Dashboard | Users can view brief summary of a customer’s deposit and loan accounts
6 |  | Account Deposit Create | Users can setup a new deposit account for a customer
7 |  | Manage Customer’s Deposit Accounts | Users can view a complete list of deposit accounts belonging to a customer
8 |  | Account Deposit Read & Update | Users can retrieve and edit details of an existing deposit account belonging to a customer | ›
9 |  | Account Loan Create | Users can submit a new loan request for a customer
10 |  | Manage Customer’s Loan Accounts | Users can view a complete list of loan accounts belonging to a customer
11 |  | Account Loan Read & Update | Users can retrieve and edit details of an existing loan belonging to a customer
12 |  | Transaction Deposit | Users help customers deposit money into a deposit account
13 |  | Transaction Withdrawal | Users help customers withdraw money from a deposit account
14 |  | Transaction History Read | Users view all monetary transactions of an existing account belonging to a customer
15 |  | Payment Credit Transfer Bill Payment | Users help customers transfer money from their deposit accounts to a registered organization
16 |  | Payment Loan Repayment Full | Users help customers repay a loan in full
17 |  | Payment Loan Repayment Partial | Users help customers partially repay a loan
18 |  | Direct Debit Authorization | Users help customers authorize any future monetary transfers to a registered organization
19 |  | Payment Standing Instruction | DROPPED: Users help customers manage standing instructions (i.e. Payments every 30 days)
20 |  | Manage Customer's Beneficiaries | DROPPED: User helps customers manage list of beneficiaries for transactions
21 | X-Factor (Credit Approval) [For Branch Tellers] | Credit Approval | Users run a loan application through a series of business rules to automatically determine loan approval
22 |  | Business Rules | Business rules engine that determines loan approval
23 |  | Upload Documents | Users help customers upload official documents to aid in the application of a loan
24 |  | Read Documents | Users retrieve uploaded official documents to view in the loan approval process
25 | X-Factor (Teaching Tool) [For Students & Teachers] | Modify Business Rules Parameters | Users can modify a threshold or parameter of an existing business rule
26 |  | Generate Data Set | Users can generate a number of profiles according to user-set parameters
27 |  | Run Test | Users can run generated profiles through the business rules to see Credit Approval process outcome
28 |  | Display Test Results | Users can view the Credit Approval process test run results
Services Catalogue
|  | Services (TIBCO Designer) | Description
1 | Built by Kungfu Panda | Party_Customer_Create | Service creates a new customer
2 |  | Party_Customer_Read | Service retrieves an existing customer’s profile
3 |  | Party_Customer_ ReadIC | Service searches for customer’s NRIC and returns customer’s profile
4 |  | Party_Customer_Update | Service updates customer’s profile
5 |  | Account_Deposit_Create | Service creates a new deposit account
6 |  | Account_Deposit_Read | Service retrieves deposit account details
7 |  | Account_Deposit_Update | Service updates deposit account details
8 |  | Account_Loan_Create | Service creates a new loan request
9 |  | Account_Loan_ Read | Service retrieves loan account details
10 |  | Account_Loan_Update | Service updates loan account details
11 |  | Party_AccountList_Read | Service retrieves a list of all deposit and loan accounts of a given customer
12 |  | Transaction_Deposit_Create | Service deposits money into a deposit account
13 |  | Transaction_Withdrawal_Create | Service withdraws money from a deposit account
14 |  | Transaction_History_Read | Service retrieves all transaction history of a given deposit or loan account
15 |  | Payment_CreditTransfer_Create | Service transfers money from one account to another account or a registered institution
16 |  | Transaction_LoanRepayment_Create | Service repays a loan in full
17 |  | Transaction_LoanRepayment_Partial_Create | Service repays a loan partially
18 |  | Credit Approval Assert | Service runs a loan application through a series of business rules and returns the outcome
1 | Developed by Others, Called by Kungfu Panda | Payment_DirectDebitAuthorization_Create | Service adds an account or a registered institution to a customer’s authorized list for future fund transfers
2 |  | Payment_DirectDebitAuthorization_Delete | Service removes an account or a registered institution from a customer's authorized list for future fund transfers
3 |  | Payment_DirectDebitAuthorizationList_Read | Service retrieves a list of accounts and registered institutions that are authorized by a customer for future fund transfers
4 |  | MDM_CustomerTypeList_Read | Service retrieves a list of all the various customer types
5 |  | MDM_ProductList_Read | Service retrieves a list of all the various product types
6 |  | Party_BillingOrgList_Read | Service retrieves a list of all registered institutions
7 |  | Product_Parameters_Read | Service retrieves the minimum balance of a given account type
8 |  | Transaction_SMS_Notification | Service sends SMS notification when transaction above withdrawal limit for Transaction Deposit and Transaction Withdrawal services
9 |  | Party_Login_Create | Service creates login credentials for customer for other retail banking channels (i.e. Internet Banking, ATM)
10 |  | Party_Login_Read | Service checks if customer has created login credentials for other retail banking channels
11 |  | Product_LoanRepayment_Calculate | Service calculates the amount incurred when doing a full loan repayment
12 |  | Product_LoanPartialRepayment_Calculate | Service calculates the amount incurred when doing a partial loan repayment
13 |  | Product_LoanInstallment_Calculate | Service calculates the new monthly loan installments and new maturity date after partial repayment
14 |  | Payment Standing Instruction Create | Dropped
15 |  | Payment Standing Instruction Read
16 |  | Payment Standing Instruction List Read
17 |  | Payment Standing Instruction Update
18 |  | Payment Standing Instruction Delete
19 |  | Payment Beneficiary List Read
20 |  | Payment Beneficiary Create
21 |  | Payment Beneficiary Delete
Functionality - Service Mapping
| Branch Teller Functions, Services & Integration | Branch Teller Functions | Services Involved
|  | Login | -
|  | Party Create | Party_Customer_Create
MDM_CustomerTypeList_Read
|  | Party User PIN Create | Party_Login_Create
Party_Login_Read
|  | Party Read & Update | Party_Customer_Read
Party_Customer_Update
Party_Customer_ ReadIC
|  | Customer’s Accounts Dashboard | Party_AccountList_Read
Transaction_History_Read
|  | Account Deposit Create | Account_Deposit_Create
MDM_ProductList_Read
Product_Parameters_Read
|  | Manage Customer’s Deposit Accounts | Party_AccountList_Read
|  | Account Deposit Read & Update | Account_Deposit_Read
Account_Deposit_Update
Product_Parameters_Read
|  | Account Loan Create | Account_Loan_Create
MDM_ProductList_Read
Product_Parameters_Read
|  | Manage Customer’s Loan Accounts | Party_AccountList_Read
|  | Account Loan Read & Update | Account_Loan_ Read
Account_Loan_Update
Product_Parameters_Read
|  | Transaction Deposit | Transaction_Deposit_Create
|  | Transaction Withdrawal | Transaction_Withdrawal_Create
Transaction_SMS_Notification
|  | Transaction History Read | Transaction_History_Read
|  | Payment Credit Transfer Bill Payment | Payment_CreditTransfer_Create
Party_BillingOrgList_Read
Transaction_SMS_Notification
|  | Payment Loan Repayment Full | Transaction_LoanRepayment_Create
Product_LoanRepayment_Calculate
|  | Payment Loan Repayment Partial | Transaction_LoanRepayment_Partial_Create
Product_LoanPartialRepayment_Calculate
Product_LoanInstallment_Calculate
|  | Direct Debit Authorization | Payment_DirectDebit_Create
Party_BillingOrgList_Read
| X-Factor (Credit Approval) | Credit Approval | Decision_CreditApproval_Assert
|  | Business Rules | -
|  | Upload Documents | -
|  | Read Documents | -
| X-Factor (Teaching Tool) | Modify Business Rules Parameters | -
|  | Generate Data Set | -
|  | Run Test | Decision_CreditApproval_Assert
|  | Display Test Results | -

## Schedule(Date)
FYP Kungfu Panda Project Schedule |  |  | Legend: | FYP Calendar | Week | Public Holidays | Milestone / Major Event
|  |  |  | PM & BA Tasks | Back End Tasks | Front End Tasks | Deadline Tasks
|  |  | Note: | FYP Wk Placeholders placed when planned start date coincides with date range
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1
FYP Wk 1 |  |  |  | 2013-04-29 | 2013-05-05 |  |  |  |  | Labour Day (1 May, Wed)
BRMS Drools Server | Install & Setup | Back End | Kevin | 2013-05-03 | 2013-05-03 | 2 | 2013-05-03 | 2013-05-03 | 2 | Surveying Business Rules Mgmt Systems (BRMS) Drools
SharePoint | Install & Learn | Back End | Yao Guang | 2013-05-05 | 2013-05-05 | 6 | 2013-05-05 | 2013-05-05 | 6 | Scope dropped (No. 1)
FYP Wk 2 |  |  |  | 2013-05-06 | 2013-05-12
BRMS Drools Server | Learn API | Back End | Kevin | 2013-05-11 | 2013-05-11 | 8 | 2013-05-11 | 2013-05-11 | 8 | Learning Drools Basic API
FYP Wk 3 |  |  |  | 2013-05-13 | 2013-05-19
BRMS Drools Server | Learn Administrative Console | Back End | Kevin | 2013-05-18 | 2013-05-18 | 6 | 2013-05-18 | 2013-05-18 | 6
BRMS Drools Rules Repository Guvnor | Learn | Back End | Kevin | 2013-05-19 | 2013-02-19 | 6 | 2013-05-19 | 2013-02-19 | 6
FYP Wk 4 |  |  |  | 2013-05-20 | 2013-05-26 |  |  |  |  | Vesak Day (24 May, Fri)
SharePoint | Learn Http Basic Authentication | Back End | Yao Guang | 2013-05-22 | 2013-05-22 | 3 | 2013-05-22 | 2013-05-22 | 3 | Scope dropped (No. 1)
TIBCO Environment | Install & Setup | Back End | Kevin, Yao Guang | 2013-05-25 | 2013-05-25 | 3 | 2013-05-25 | 2013-05-25 | 3
FYP Wk 5 |  |  |  | 2013-05-27 | 2013-06-02
Project Scope | Conceptualize Use Cases | PM & BA | Jon, Kevin, Yao Guang | 2013-06-02 | 2013-06-02 | 3 | 2013-06-02 | 2013-06-02 | 4 | SIS Level 3 Benches
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2
FYP Wk 6 |  |  |  | 2013-06-03 | 2013-06-09
TIBCO Environment | Setup | Back End | Kevin, Yao Guang | 2013-06-04 | 2013-06-04 | 5 | 2013-06-04 | 2013-06-04 | 5
Party Customer Create | Develop Base Case | Back End | Kevin, Yao Guang | 2013-06-05 | 2013-06-05 | 5 | 2013-06-05 | 2013-06-05 | 5 | Develop Party_Customer_Create / Configure Tibco Environment (Service Mediation, Logging, EMS, existing DBs)
Party Customer Create | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-06-06 | 2013-06-06 | 3 | 2013-06-06 | 2013-06-06 | 3 | Teamviewer
BRMS | Analyze | PM & BA | Kevin | 2013-06-08 | 2013-06-08 | 3 | 2013-06-08 | 2013-06-08 | 3 | Comparing different technologies recommended by Steven Nunez (Jess, Drools, FICO)
BRMS Drools Server & Rules Repository Guvnor | Setup | Back End | Kevin | 2013-06-08 | 2013-06-08 | 6 | 2013-06-08 | 2013-06-08 | 6 | Setup functional local deployment of Drools Server Endpoint and Guvnor REST Endpoints
BRMS Drools Server & Rules Repository Guvnor | Learn | Back End | Kevin | 2013-06-08 | 2013-06-08 | 3 | 2013-06-08 | 2013-06-08 | 3 | Testing Drools Endpoints to cater towards multiple Operations on same Endpoint (for different Rule sets and Domains)
FYP Wk 7 |  |  |  | 2013-06-10 | 2013-06-16
Party Customer Read | Develop Base Case | Back End | Yao Guang | 2013-06-10 | 2013-06-10 | 4 | 2013-06-10 | 2013-06-10 | 4 | Teamviewer
Party Customer Update | Develop Base Case | Back End | Kevin | 2013-06-10 | 2013-06-10 | 4 | 2013-06-10 | 2013-06-10 | 4
Party Customer Read | Develop Error Flows | Back End | Yao Guang | 2013-06-11 | 2013-06-11 | 2 | 2013-06-10 | 2013-06-10 | 2
Party Customer Update | Develop Error Flows | Back End | Kevin | 2013-06-11 | 2013-06-11 | 2 | 2013-06-10 | 2013-06-10 | 2
Account Create | Develop Base Case | Back End | Kevin, Yao Guang | 2013-06-12 | 2013-06-12 | 5 | 2013-06-12 | 2013-06-12 | 5 | Scope changed, add hours to Account Deposit Create (No. 5)
TIBCO Environment | Setup | Back End | Jon, Kevin, Yao Guang | 2013-06-16 | 2013-06-16 | 3 | 2013-06-16 | 2013-06-16 | 3 | Kevin & Yao Guang teach Jon
Proposal | Writing | PM & BA | Jon | 2013-06-14 | 2013-06-16 | 2 | 2013-06-14 | 2013-06-16 | 2
Project Scope | Define | PM & BA | Jon | 2013-06-14 | 2013-06-16 | 6 | 2013-06-14 | 2013-06-16 | 6
Wiki | Design Structure | PM & BA | Geraldine | 2013-06-14 | 2013-06-16 | 6 | 2013-06-14 | 2013-06-16 | 6
FYP Wk 8 |  |  |  | 2013-06-17 | 2013-06-23 |  |  |  |  | Proposal (20 June, Fri)
Account Create | Develop Base Case | Back End | Yao Guang | 2013-06-17 | 2013-06-17 | 4 | 2013-06-17 | 2013-06-17 | 4 | Scope changed, add hours to Account Deposit Create (No. 5)
Account Read | Develop Base Case | Back End | Yao Guang | 2013-06-19 | 2013-06-19 | 4 | 2013-06-19 | 2013-06-19 | 4 | Scope changed, add hours to Account Deposit Read (No. 5)
Account Update | Develop Base Case | Back End | Kevin | 2013-06-17 | 2013-06-21 | 12 | 2013-06-17 | 2013-06-21 | 12 | Scope changed, add hours to Account Deposit Update (No. 5)
Proposal | Revision | PM & BA | Jon | 2013-06-17 | 2013-06-20 | 6 | 2013-06-17 | 2013-06-20 | 10
Wiki | Update | PM & BA | Geraldine | 2013-06-17 | 2013-06-20 | 6 | 2013-06-17 | 2013-06-20 | 6
Proposal |  |  |  | 2013-06-20
BRMS Drools Server & Rules Repository Guvnor | Develop | Back End | Kevin | 2013-06-22 | 2013-06-22 | 4 | 2013-06-22 | 2013-06-22 | 4 | Develop Basic Framework for Drools Integration with Tibco Cross-Selling use case (Xml, parse, render interaction with drools REST endpoint), with test rule set
Next Best Offer | Develop Base Case | Back End | Kevin | 2013-06-22 | 2013-06-22 | 4 | 2013-06-22 | 2013-06-22 | 4
Buffer Time |  |  |  | 2013-06-23 | 2013-06-23 |  | 2013-06-23 | 2013-06-23
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3
FYP Wk 9 |  |  |  | 2013-06-24 | 2013-06-30
Account Deposit Create | Develop Base Case | Back End | Kevin, Yao Guang | 2013-06-24 | 2013-06-24 | 1 | 2013-06-24 | 2013-06-24 | 1
Account Deposit Read | Develop Base Case | Back End | Kevin, Yao Guang | 2013-06-25 | 2013-06-25 | 1 | 2013-06-25 | 2013-06-25 | 1
Account Deposit Update | Develop Base Case | Back End | Kevin, Yao Guang | 2013-06-26 | 2013-06-26 | 1 | 2013-06-26 | 2013-06-26 | 1
Account List Read | Develop Base Case | Back End | Kevin, Yao Guang | 2013-06-27 | 2013-06-30 | 2 | 2013-06-27 | 2013-06-30 | 2
Lo-Fi Prototype | Design | UI | James, Juntao | 2013-06-24 | 2013-06-25 | 2 | 2013-06-24 | 2013-06-25 | 2
Backbone JavaScript | Learn | UI | James, Juntao | 2013-06-26 | 2013-06-29 | 8 | 2013-06-26 | 2013-06-29 | 8
Bug Metrics | Develop | PM & BA | James | 2013-06-30 | 2013-06-30 | 2 | 2013-06-30 | 2013-06-30 | 2
PM Tools | Experiment & Analyse | PM & BA | Jon | 2013-06-24 | 2013-06-30 | 6 | 24 Jun, Mon | 30 Jun, Sun | 6
Project Scope | Define | PM & BA | Jon | 2013-06-24 | 2013-06-30 | 8 | 2013-06-24 | 2013-06-30 | 8
Schedule | Draft (v0.1) | PM & BA | Geraldine | 2013-06-24 | 2013-06-30 | 2 | 2013-06-24 | 2013-06-30 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-06-24 | 2013-06-30 | 8 | 2013-06-24 | 2013-06-30 | 8
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-06-30 | 2013-06-30 | 1 | 2013-06-30 | 2013-06-30 | 1
FYP Wk 10 |  |  |  | 2013-07-01 | 2013-07-07
Party Customer Create | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-01 | 2013-07-02 | 2 | 2013-07-01 | 2013-07-01 | 3
Party Customer Read | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-02 | 2013-07-03 | 2 | 2013-07-02 | 2013-07-02 | 2
Party Customer Update | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-03 | 2013-07-04 | 2 | 2013-07-03 | 2013-07-03 | 2
Account Deposit Create | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-04 | 2013-07-04 | 2 | 2013-07-04 | 2013-07-04 | 2 | Scope changed (No. 2)
Account Deposit Read | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-05 | 2013-07-05 | 2 | 2013-07-05 | 2013-07-05 | 2 | Scope changed (No. 2)
Account Deposit Update | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-06 | 2013-07-06 | 2 | 2013-07-06 | 2013-07-06 | 2 | Scope changed (No. 2)
Account List Read | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-07 | 2013-07-07 | 2 | 2013-07-07 | 2013-07-07 | 2 | Scope changed (No. 2)
Common Data Model - Transaction | Modify | Back End | Kevin, Yao Guang | 2013-07-06 | 2013-07-06 | 2 | 2013-07-06 | 2013-07-06 | 2 | Scope changed (No. 3)
Account Loan Create | Develop Base Case | Back End | Kevin, Yao Guang | 2013-07-04 | 2013-07-05 | 2 | 2013-07-08 | 2013-07-08 | 2
Account Loan Read | Develop Base Case | Back End | Kevin, Yao Guang | 2013-07-05 | 2013-07-06 | 2 | 2013-07-08 | 2013-07-08 | 2
Account Loan Update | Develop Base Case | Back End | Kevin, Yao Guang | 2013-07-06 | 2013-07-06 | 2 | 2013-07-08 | 2013-07-08 | 2
Lo-Fi Prototype | Revise | UI | James, Juntao | 2013-07-01 | 2013-07-06 | 2 | 2013-07-01 | 2013-07-07 | 2
Project Scope | Change Management | PM & BA | Jon | 2013-07-07 | 2013-07-07 | 4 | 2013-07-07 | 2013-07-07 | 4
Schedule | Draft (v0.2) | PM & BA | Geraldine | 2013-07-07 | 2013-07-07 | 2 | 2013-07-07 | 2013-07-07 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-07-07 | 2013-07-07 | 4 | 2013-07-07 | 2013-07-07 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-07-07 | 2013-07-07 | 1 | 2013-07-07 | 2013-07-07 | 1
Buffer Time |  |  |  | 2013-07-07 | 2013-07-07 |  | - | - |  | Buffer Time eaten by scope change
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4
FYP Wk 11 |  |  |  | 2013-07-08 | 2013-07-14
Party Customer Create | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-07-08 | 2013-07-11 | 4 | 2013-07-08 | 2013-07-11 | 4
Party Customer Create | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-12 | 2013-07-12 | 3 | Scope changed (No. 4)
Party Customer Read | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-12 | 2013-07-12 | 1 | Scope changed (No. 4)
Party Customer Update | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-12 | 2013-07-12 | 1 | Scope changed (No. 4)
Account Deposit Create | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-13 | 2013-07-13 | 1 | Scope changed (No. 4)
Account Deposit Read | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-13 | 2013-07-13 | 1 | Scope changed (No. 4)
Account Deposit Update | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-13 | 2013-07-13 | 1 | Scope changed (No. 4)
Account Loan Create | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-14 | 2013-07-14 | 1 | Scope changed (No. 4)
Account Loan Read | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-14 | 2013-07-14 | 1 | Scope changed (No. 4)
Account Loan Update | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-14 | 2013-07-14 | 1 | Scope changed (No. 4)
Account List Read | Modify Base Case | Back End | Kevin, Yao Guang | 2013-07-12 | 2013-07-12 | 1 | 2013-07-14 | 2013-07-14 | 1 | Scope changed (No. 4)
Account Deposit Create | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-13 | 2013-07-13 | 2 | 2013-07-13 | 2013-07-13 | 2
Account Deposit Read | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-13 | 2013-07-13 | 2 | 2013-07-13 | 2013-07-13 | 2
Account Deposit Update | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-13 | 2013-07-13 | 2 | 2013-07-13 | 2013-07-13 | 2
Account List Read | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-13 | 2013-07-13 | 2 | 2013-07-14 | 2013-07-14 | 2
Account Loan Create | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-14 | 2013-07-14 | 2 | 2013-07-14 | 2013-07-14 | 2
Account Loan Read | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-14 | 2013-07-14 | 2 | 2013-07-14 | 2013-07-14 | 2
Account Loan Update | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-07-14 | 2013-07-14 | 2 | 2013-07-14 | 2013-07-14 | 2
Project Scope | Change Management | PM & BA | Jon | 2013-07-08 | 2013-07-14 | 6 | 2013-07-08 | 2013-07-14 | 4
Schedule | Draft (v0.3) | PM & BA | Geraldine | 2013-07-14 | 2013-07-14 | 2 | 2013-07-07 | 2013-07-07 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-07-14 | 2013-07-14 | 4 | 2013-07-07 | 2013-07-07 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-07-14 | 2013-07-14 | 1 | 2013-07-14 | 2013-07-14 | 1
FYP Wk 12 |  |  |  | 2013-07-15 | 2013-07-21
Account Deposit Create | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-15 | 2013-07-15 | 1 | 2013-07-15 | 2013-07-15 | 1
Account Deposit Read | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-15 | 2013-07-16 | 1 | 2013-07-15 | 2013-07-16 | 1
Account Deposit Update | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-16 | 2013-07-16 | 1 | 2013-07-16 | 2013-07-16 | 1
Account List Read | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-16 | 2013-07-17 | 1 | 2013-07-16 | 2013-07-16 | 1
Account Loan Create | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-18 | 2013-07-18 | 1 | 2013-07-18 | 2013-07-18 | 1
Account Loan Read | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-18 | 2013-07-18 | 1 | 2013-07-18 | 2013-07-18 | 1
Account Loan Update | Deploy to Server | Back End | Kevin, Yao Guang | 2013-07-19 | 2013-07-19 | 1 | 2013-07-19 | 2013-07-19 | 1
Party Customer Create | Modify Integration Code | Back End | Kevin, Yao Guang | 2013-07-16 | 2013-07-19 | 2 | 2013-07-16 | 2013-07-19 | 2 | Scope changed (No. 4)
Party Customer Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-07-17 | 2013-07-21 | 3 | 2013-07-17 | 2013-07-21 | 3
Party Customer Update | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-07-19 | 2013-07-21 | 3 | 2013-07-19 | 2013-07-21 | 3
Login Use Case | Develop Basic UI | UI | James, Juntao | 2013-07-16 | 2013-07-19 | 1 | 2013-07-16 | 2013-07-16 | 1
Party Create Use Case - Party Customer Create | Develop Basic UI | UI | James, Juntao | 2013-07-16 | 2013-07-19 | 8 | 2013-07-16 | 2013-07-19 | 7
Party Read & Update Use Case - Party Customer Read | Develop Basic UI | UI | James, Juntao | 2013-07-20 | 1900-01-20 | 6 | 2013-07-20 | 1900-01-20 | 6
Party Read & Update Use Case - Party Customer Update | Develop Basic UI | UI | James, Juntao | 2013-07-20 | 1900-01-20 | 6 | 2013-07-20 | 1900-01-20 | 6
Login Use Case | Develop Complete UI | UI | James, Juntao | 2013-07-22 | 2013-07-22 | 1 | 2013-07-16 | 2013-07-16 | 1
Party Create Use Case - Party Customer Create | Develop Complete UI | UI | James, Juntao | 2013-07-22 | 2013-07-22 | 2 | 2013-07-22 | 2013-07-22 | 2
Party Read & Update Use Case - Party Customer Read | Develop Complete UI | UI | James, Juntao | 2013-07-22 | 2013-07-22 | 2 | 2013-07-22 | 2013-07-22 | 2
Party Read & Update Use Case - Party Customer Update | Develop Complete UI | UI | James, Juntao | 2013-07-22 | 2013-07-22 | 2 | 2013-07-22 | 2013-07-22 | 2
Project Scope | Change Management | PM & BA | Jon | 2013-07-15 | 2013-07-21 | 4 | 2013-07-15 | 2013-07-21 | 4
Schedule | Draft (v0.4) | PM & BA | Geraldine | 2013-07-15 | 2013-07-21 | 2 | 2013-07-15 | 2013-07-21 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-07-15 | 2013-07-21 | 4 | 2013-07-15 | 2013-07-21 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-07-21 | 2013-07-21 | 1 | 2013-07-21 | 2013-07-21 | 1
Party Customer Services Complete |  |  |  | 2013-07-21 |  |  | 2013-07-21
FYP Wk 13 |  |  |  | 2013-07-22 | 2013-07-28
Buffer Time |  |  |  | 2013-07-23 | 2013-07-27 |  |  |  |  | Most of Team Going for CSP Camp
Account Deposit Create | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-22 | 2013-07-22 | 1 | 2013-07-22 | 2013-07-22 | 1 | Scope changed (No. 5)
Account Deposit Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-22 | 2013-07-22 | 1 | 2013-07-22 | 2013-07-22 | 1 | Scope changed (No. 5)
Account Deposit Update | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-22 | 2013-07-22 | 1 | 2013-07-22 | 2013-07-22 | 1 | Scope changed (No. 5)
Account List Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-22 | 2013-07-22 | 1 | 2013-07-22 | 2013-07-22 | 1 | Scope changed (No. 5)
Account Loan Create | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-27 | 2013-07-27 | 1 | 2013-07-27 | 2013-07-27 | 1 | Scope changed (No. 5)
Account Loan Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-27 | 2013-07-27 | 1 | 2013-07-27 | 2013-07-27 | 1 | Scope changed (No. 5)
Account Loan Update | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 2013-07-27 | 2013-07-27 | 1 | 2013-07-27 | 2013-07-27 | 1 | Scope changed (No. 5)
Project Scope | Change Management | PM & BA | Jon | 2013-07-28 | 2013-07-28 | 4 | 2013-07-28 | 2013-07-28 | 4
Schedule | Draft (v0.5) | PM & BA | Geraldine | 2013-07-28 | 2013-07-28 | 2 | 2013-07-28 | 2013-07-28 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-07-28 | 2013-07-28 | 4 | 2013-07-28 | 2013-07-28 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-07-28 | 2013-07-28 | 1 | 2013-07-28 | 2013-07-28 | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5
FYP Wk 14 |  |  |  | 2013-07-29 | 2013-08-04
Account Deposit Create | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-01 | 2013-08-01 | 2 | 2013-08-01 | 2013-08-01 | 3
Account Deposit Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-02 | 2013-08-02 | 2 | 2013-08-02 | 2013-08-02 | 3
Account Deposit Update | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-02 | 2013-08-02 | 2 | 2013-08-02 | 2013-08-02 | 3
Account List Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-03 | 1900-02-06 | 2 | 2013-08-03 | 1900-02-06 | 3
Account Loan Create | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-03 | 2013-08-03 | 2 | 2013-08-03 | 2013-08-03 | 3
Account Loan Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-04 | 2013-08-04 | 2 | 2013-08-04 | 2013-08-04 | 3
Account Loan Update | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-04 | 2013-08-04 | 2 | 2013-08-04 | 2013-08-04 | 3
Account Deposit Create Use Case - Account Deposit Create | Develop Basic UI | UI | James | 2013-08-01 | 2013-08-01 | 3 | 2013-07-23 | 2013-08-01 | 3
Manage Customer's Deposit Accounts Use Case - Account List Read | Develop Basic UI | UI | James | 2013-08-01 | 2013-08-01 | 3 | 2013-08-01 | 2013-08-01 | 3
Account Deposit Read & Update - Account Deposit Read | Develop Basic UI | UI | James | 2013-08-01 | 2013-08-01 | 3 | 2013-08-01 | 2013-08-01 | 3
Account Deposit Read & Update - Account Deposit Update | Develop Basic UI | UI | James | 2013-08-01 | 2013-08-01 | 3 | 2013-08-01 | 2013-08-01 | 3
Account Loan Create Use Case - Account Loan Create | Develop Basic UI | UI | Juntao | 2013-08-02 | 2013-08-02 | 3 | 2013-08-02 | 2013-08-02 | 3
Manage Customer's Loan Accouts Use Case - Account List Read | Develop Basic UI | UI | Juntao | 2013-08-02 | 2013-08-02 | 3 | 2013-08-02 | 2013-08-02 | 3
Account Loan Read & Update - Account Deposit Read | Develop Basic UI | UI | Juntao | 2013-08-02 | 2013-08-02 | 3 | 2013-08-02 | 2013-08-02 | 3
Account Loan Read & Update - Account Deposit Update | Develop Basic UI | UI | Juntao | 2013-08-02 | 2013-07-28 | 3 | 2013-08-02 | 2013-07-28 | 3
Account Deposit Create Use Case - Account Deposit Create | Develop Complete UI | UI | James | 2013-08-03 | 2013-08-03 | 1 | 2013-08-03 | 2013-08-03 | 1
Manage Customer's Deposit Accounts Use Case - Account List Read | Develop Complete UI | UI | James | 2013-08-03 | 2013-08-03 | 1 | 2013-08-03 | 2013-08-03 | 1
Account Deposit Read & Update - Account Deposit Read | Develop Complete UI | UI | James | 2013-08-03 | 2013-08-03 | 1 | 2013-08-03 | 2013-08-03 | 1
Account Deposit Read & Update - Account Deposit Update | Develop Complete UI | UI | James | 2013-08-03 | 2013-08-03 | 1 | 2013-08-03 | 2013-08-03 | 1
Account Loan Create Use Case - Account Loan Create | Develop Complete UI | UI | Juntao | 2013-08-04 | 2013-08-04 | 1 | 2013-08-04 | 2013-08-04 | 1
Manage Customer's Loan Accouts Use Case - Account List Read | Develop Complete UI | UI | Juntao | 2013-08-04 | 2013-08-04 | 1 | 2013-08-04 | 2013-08-04 | 1
Account Loan Read & Update - Account Deposit Read | Develop Complete UI | UI | Juntao | 2013-08-04 | 2013-08-04 | 1 | 2013-08-04 | 2013-08-04 | 1
Account Loan Read & Update - Account Deposit Update | Develop Complete UI | UI | Juntao | 2013-08-04 | 2013-08-04 | 1 | 2013-08-04 | 2013-08-04 | 1
Project Scope | Change Management | PM & BA | Jon | 2013-07-28 | 2013-07-28 | 4 | 2013-07-28 | 2013-07-28 | 4
Schedule | Update v1.0 | PM & BA | Geraldine | 2013-07-28 | 2013-07-28 | 4 | 2013-07-28 | 2013-07-28 | 4
Wiki | Weekly Update | PM & BA | Geraldine | 2013-07-28 | 2013-07-28 | 4 | 2013-07-28 | 2013-07-28 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-07-28 | 2013-07-28 | 1 | 2013-07-28 | 2013-07-28 | 1
Complete Account Services |  |  |  | 2013-08-04 |  |  | 2013-08-04
FYP Wk 15 |  |  |  | 2013-08-05 | 2013-08-11 |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Transaction Deposit | Develop Base Case | Back End | Kevin | 2013-08-05 | 2013-08-05 | 2 | 2013-08-05 | 2013-08-05 | 2
Transaction Withdrawal | Develop Base Case | Back End | Kevin | 2013-08-05 | 2013-08-06 | 2 | 2013-08-05 | 2013-08-05 | 2
Transaction History Read | Develop Base Case | Back End | Kevin, Yao Guang | 2013-08-06 | 2013-08-06 | 2 | 2013-08-06 | 2013-08-06 | 2
BRMS, Next Best Offer | Hand Over | PM & BA | Geraldine, Jon, Kevin | 2013-08-06 | 2013-08-06 | 2 | 2013-08-06 | 2013-08-06 | 2 | Scope changed (No. 7 & 8); Met FYP Team Creagend
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 2013-08-06 | 2013-08-14 | 6 | 2013-08-06 | 2013-08-14 | 20
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-08-05 | 2013-08-11 | 6 | 2013-08-05 | 2013-08-11 | 16
Project Scope | Change Management | PM & BA | Jon | 2013-08-05 | 2013-08-11 | 2 | 2013-08-05 | 2013-08-11 | 2
Schedule | Overhaul v2.0 | PM & BA | Jon | 2013-08-05 | 2013-08-11 | 16 | 2013-08-05 | 2013-08-14 | 16
Wiki | Weekly Update | PM & BA | Geraldine | 2013-08-05 | 2013-08-11 | 12 | 2013-08-05 | 2013-08-14 | 12
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-08-05 | 2013-08-11 | 1 | 2013-08-05 | 2013-08-14 | 1
FYP Wk 16 |  |  |  | 2013-08-12 | 2013-08-18 |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 2013-08-12 | 2013-08-14 | 6 | 2013-08-12 | 2013-08-14 | 10
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-08-12 | 2013-08-14 | 6 | 2013-08-12 | 2013-08-14 | 16
Transaction Deposit | Develop Error Flows | Back End | Kevin | 2013-08-12 | 2013-08-12 | 1 | 2013-08-12 | 2013-08-12 | 1
Transaction Withdrawal | Develop Error Flows | Back End | Kevin | 2013-08-12 | 2013-08-12 | 1 | 2013-08-13 | 2013-08-13 | 1
Transaction History Read | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-08-13 | 2013-08-13 | 1 | 2013-08-13 | 2013-08-13 | 1
Credit Approval | Develop Spreadsheet | Back End | Kevin | 2013-08-13 | 2013-08-13 | 1 | 2013-08-13 | 2013-08-13 | 1.5 | Scope changed (No. 15)
Project Scope | Change Management | PM & BA | Jon | 2013-08-12 | 2013-08-14 | 2 | 2013-08-12 | 2013-08-14 | 2
Schedule | Overhaul v2.0 | PM & BA | Jon | 2013-08-12 | 2013-08-14 | 16 | 2013-08-12 | 2013-08-14 | 24
Wiki | Weekly Update | PM & BA | Geraldine | 2013-08-12 | 2013-08-14 | 12 | 2013-08-12 | 2013-08-14 | 12
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-08-12 | 2013-08-14 | 1 | 2013-08-12 | 2013-08-14 | 1
Acceptance Presentation |  |  | Jon | 2013-08-16 | 2013-08-16 | 2 | 2013-08-16 | 2013-08-16 | 2
Account Deposit Create | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-19 | 2013-08-19 | 1 | 2013-08-18 | 2013-08-19 | 1 | Scope changed (No. 13, 17)
Account Deposit Update | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-19 | 2013-08-19 | 1 | 2013-08-18 | 2013-08-19 | 2 | Scope changed (No. 13, 17)
Account Loan Create | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-19 | 2013-08-19 | 1 | 2013-08-18 | 2013-08-19 | 1 | Scope changed (No. 12 & 17)
Account Loan Read | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-19 | 2013-08-19 | 1 | 2013-08-18 | 2013-08-19 | 1 | Scope changed (No. 12)
Account Loan Update | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-19 | 2013-08-19 | 1 | 2013-08-18 | 2013-08-19 | 2 | Scope changed (No. 17)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-08-17 | 2013-08-19 | 10 | 2013-08-17 | 2013-08-19 | 6 | Spillover to next iteration
MDM Customer Type Read | Taking Over | Back End | Kevin | 2013-08-17 | 2013-08-17 | 0.5 |  |  |  | Scope changed (No. 13) | Alan didn't deliver on time
MDM Product Type Read | Taking Over | Back End | Kevin | 2013-08-17 | 2013-08-17 | 0.5 |  |  |  | Scope changed (No. 13) | Alan didn't deliver on time
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6
FYP Wk 17 / SMU Wk 1 |  |  |  | 2013-08-19 | 2013-08-25 |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-08-19 | 2013-08-19 | 4 | 2013-08-19 | 2013-08-19 | 4 | Task from previous iteration, replanned
MDM Customer Type Read | Develop Integration Code | Back End | Kevin | 2013-08-20 | 2013-08-20 | 2 | 2013-08-20 | 2013-08-20 | 2
MDM Product Type Read | Develop Integration Code | Back End | Kevin | 2013-08-20 | 2013-08-20 | 2 | 2013-08-20 | 2013-08-20 | 2.5
Transaction Deposit | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-20 | 2013-08-20 | 0.5 | 2013-08-20 | 2013-08-20 | 0.5 | Scope changed (No. 6)
Transaction Withdrawal | Modify Whole Case | Back End | Kevin, Yao Guang | 2013-08-20 | 2013-08-20 | 0.5 | 2013-08-20 | 2013-08-20 | 0.5 | Scope changed (No. 6)
Transaction SMS Notification | Taking Over | Back End | Kevin | 2013-08-20 | 2013-08-20 | 0.5 | 2013-08-20 | 2013-08-20 | 1
Transaction Deposit | Deploy to Server | Back End | Kevin, Yao Guang | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 0.5
Transaction Withdrawal | Deploy to Server | Back End | Kevin, Yao Guang | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 0.5
Transaction History Read | Deploy to Server | Back End | Kevin, Yao Guang | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 0.5
Transaction Deposit | Develop Integration Code | Back End | Kevin | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 0.5
Transaction Withdrawal | Develop Integration Code | Back End | Kevin | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 0.5
Transaction History Read | Develop Integration Code | Back End | Kevin | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 0.5
Registration |  |  |  | 2013-08-21
Account Deposit Create Use Case - MDM Product Type Read Changes | Develop Basic UI | UI | Juntao | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 1
Account Loan Create Use Case - MDM Product Type Read & Changes | Develop Basic UI | UI | Juntao | 2013-08-21 | 2013-08-21 | 1 | 2013-08-21 | 2013-08-21 | 1
Account Deposit Create Use Case - MDM Product Type Read & Changes | Develop Complete UI | UI | Juntao | 2013-08-22 | 2013-08-22 | 1 | 2013-08-22 | 2013-08-22 | 1
Account Loan Create Use Case - MDM Product Type Read & Changes | Develop Complete UI | UI | Juntao | 2013-08-22 | 2013-08-22 | 1 | 2013-08-22 | 2013-08-22 | 1
Party Create Use Case - MDM Customer Type Read | Develop Basic UI | UI | James | 2013-08-23 | 2013-08-23 | 1 | 2013-08-23 | 2013-08-23 | 1
Party Create Use Case - MDM Customer Type Read | Develop Complete UI | UI | James | 2013-08-23 | 2013-08-23 | 1 | 2013-08-23 | 2013-08-23 | 1
Transaction Deposit Use Case | Develop Basic UI | UI | James | 2013-08-22 | 2013-08-22 | 3 | 2013-08-22 | 2013-08-22 | 1
Transaction Withdrawal Use Case | Develop Basic UI | UI | James | 2013-08-22 | 2013-08-22 | 3 | 2013-08-22 | 2013-08-22 | 1
Transaction History Read Use Case | Develop Basic UI | UI | James | 2013-08-22 | 2013-08-22 | 3 | 2013-08-22 | 2013-08-22 | 2
Transaction Deposit Use Case | Develop Complete UI | UI | James | 2013-08-22 | 2013-08-22 | 1 | 2013-08-22 | 2013-08-22 | 1
Transaction Withdrawal Use Case | Develop Complete UI | UI | James | 2013-08-22 | 2013-08-22 | 1 | 2013-08-22 | 2013-08-22 | 1
Transaction History Read Use Case | Develop Complete UI | UI | James | 2013-08-22 | 2013-08-22 | 1 | 2013-08-22 | 2013-08-22 | 2
Login Use Case | Testing - JUnit | UI | Juntao | 2013-08-23 | 2013-08-23 | 1 | 2013-08-23 | 2013-08-23 | 2.5
Party Create Use Case | Testing - JUnit | UI | Juntao | 2013-08-24 | 2013-08-24 | 1 | 2013-08-24 | 2013-08-24 | 3
Party Read & Update | Testing - JUnit | UI | Juntao | 2013-08-25 | 2013-08-25 | 1 | 2013-08-25 | 2013-08-25 | 3
Login Use Case | Debugging | UI | Juntao, Kevin | 2013-08-24 | 2013-08-24 | 2 | 2013-08-26 | 2013-08-24 | 0
Party Create Use Case | Debugging | UI | Juntao, Kevin | 2013-08-24 | 2013-08-24 | 2 | 2013-08-24 | 2013-08-24 | 0
Party Read & Update | Debugging | UI | Juntao, Kevin | 2013-08-24 | 2013-08-24 | 2 | 2013-08-24 | 2013-08-24 | 0.5
Acceptance | Gather Back End Tutorial Requirements from Other Teams | Back End | Jon, Kevin, Yao Guang | 2013-08-23 | 2013-08-23 | 2 | 2013-08-23 | 2013-08-23 | 2
Back End Services | Writing Tutorial for Other FYP Teams | PM & BA | Jon | 2013-08-22 | 2013-08-22 | 4 | 2013-08-22 | 2013-08-22 | 8
Project Scope | Change Management | PM & BA | Jon, Kevin | 2013-08-19 | 2013-08-24 | 2 | 2013-08-23 | 2013-08-23 | 2
Schedule | Overhaul v2.0 | PM & BA | Jon | 2013-08-19 | 2013-08-24 | 4 | 2013-08-19 | 2013-08-24 | 4
Wiki | Weekly Update | PM & BA | Geraldine | 2013-08-19 | 2013-08-24 | 4 | 2013-08-19 | 2013-08-24 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-08-19 | 2013-08-24 | 1 | 2013-08-19 | 2013-08-24 | 1
Buffer Time |  |  |  | 2013-08-25
FYP Wk 18 / SMU Wk 2 |  |  |  | 2013-08-26 | 2013-09-01
Account Deposit Create | Debugging & Redeploy | Back End | Kevin & Yao Guang | 2013-08-26 | 2013-08-26 | 1 | 2013-08-26 | 2013-08-26 | 1
Account Deposit Update | Debugging & Redeploy | Back End | Kevin & Yao Guang | 2013-08-26 | 2013-08-26 | 1 | 2013-08-26 | 2013-08-26 | 0.5
Account Loan Create | Debugging & Redeploy | Back End | Kevin & Yao Guang | 2013-08-26 | 2013-08-26 | 1 | 2013-08-26 | 2013-08-26 | 1
Account Loan Read | Debugging & Redeploy | Back End | Kevin & Yao Guang | 2013-08-26 | 2013-08-26 | 1 | 2013-08-26 | 2013-08-26 | 0.5
Account Loan Update | Debugging & Redeploy | Back End | Kevin & Yao Guang | 2013-08-26 | 2013-08-26 | 1 | 2013-08-26 | 2013-08-26 | 1
Product Parameters Read | Taking Over | Back End | Kevin | 2013-08-30 | 2013-08-30 | 0.5 | 2013-08-29 | 2013-08-29 | 0.5 | Scope changed (No. 14)
Product Parameters Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-08-30 | 2013-08-30 | 1 | 2013-08-29 | 2013-08-29 | 1
Transaction SMS Notification | Integrate | Back End | Kevin | 2013-08-31 | 2013-08-31 | 2 | 2013-08-31 | 2013-08-31 | 2
Payment Credit Transfer | Develop Base Case | Back End | Kevin, Yao Guang | 2013-08-31 | 2013-09-01 | 2 | 2013-08-31 | 2013-08-31 | 2
Payment Loan Repayment Full | Develop Base Case | Back End | Kevin, Yao Guang | 2013-08-31 | 2013-09-01 | 2 | 2013-09-01 | 2013-09-01 | 2
Payment Loan Repayment Partial | Develop Base Case | Back End | Kevin, Yao Guang | 2013-08-31 | 2013-09-01 | 4 | 2013-09-01 | 2013-09-01 | 3
Payment Credit Transfer | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-08-31 | 2013-09-01 | 1 | 2013-09-01 | 2013-09-01 | 1
Payment Loan Repayment Full | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-08-31 | 2013-09-01 | 1 | 2013-09-01 | 2013-09-01 | 2
Account Deposit Create Use Case | Testing - JUnit | UI | Juntao | 2013-08-26 | 2013-08-27 | 2 | 2013-08-26 | 2013-08-27 | 2
Account Deposit Read & Update Use Case | Testing - JUnit | UI | Juntao | 2013-08-26 | 2013-08-27 | 1 | 2013-08-26 | 2013-08-27 | 1
Account Loan Create Use Case | Testing - JUnit | UI | Juntao | 2013-08-26 | 2013-08-27 | 1 | 2013-08-26 | 2013-08-27 | 2
Account Loan Read & Update Use Case | Testing - JUnit | UI | Juntao | 2013-08-26 | 2013-08-27 | 1 | 2013-08-26 | 2013-08-27 | 1.5
Transaction Deposit Use Case | Develop Complete UI | UI | James | 2013-08-27 | 2013-08-27 | 2 | 2013-08-27 | 2013-08-27 | 2
Transaction Withdrawal Use Case | Develop Complete UI | UI | James | 2013-08-27 | 2013-08-27 | 2 | 2013-08-27 | 2013-08-27 | 2
Transaction History Read Use Case | Develop Complete UI | UI | James | 2013-08-27 | 2013-08-27 | 2 | 2013-08-27 | 2013-08-27 | 1
Login Use Case | Testing - HTMLUnit | UI | Juntao | 2013-08-29 | 2013-08-30 | 1 | 2013-08-30 | 2013-08-30 | 6
Tutorial |  | PM & BA | Jon | 2013-08-27 | 2013-08-27 | 4 | 2013-08-27 | 2013-08-27 | 4.5
Project Scope | Change Management | PM & BA | Jon | 2013-08-26 | 2013-08-30 | 2 | 2013-08-26 | 2013-08-30 | 2
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-08-26 | 2013-08-30 | 4 | 2013-08-26 | 2013-08-30 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-08-26 | 2013-08-30 | 2 | 2013-09-01 | 2013-09-01 | 1
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-08-26 | 2013-08-30 | 1 | 2013-08-26 | 2013-08-30 | 1
Buffer Time |  |  |  | 2013-09-01
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 |  |  |  | 2013-09-02 | 2013-09-15
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Payment Loan Repayment Partial | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 2
Payment Credit Transfer | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Full | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Partial | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Credit Transfer | Deploy to Server | Back End | Kevin | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Full | Deploy to Server | Back End | Kevin, Yao Guang | 2013-09-05 | 2013-09-05 | 1 | 2013-09-06 | 2013-09-06 | 1
Payment Loan Repayment Partial | Deploy to Server | Back End | Kevin, Yao Guang | 2013-09-05 | 2013-09-05 | 1 | 2013-09-06 | 2013-09-06 | 1
Direct Debit Authorization Service | Taking Over | Back End | Kevin | 2013-09-01 | 2013-09-06 | 0.5 | 2013-09-06 | 2013-09-06 | 0.5
Direct Debit Authorization | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-06 | 2013-09-06 | 1 | 2013-09-06 | 2013-09-06 | 1
Account Deposit Create Use Case - Product Parameters Read | Develop Basic UI | UI | James, Kevin | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Read & Update Use Case - Product Parameters Read | Develop Basic UI | UI | James, Kevin | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Create Use Case Product Parameters Read | Develop Basic UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Read & Update Use Case - Product Parameters Read | Develop Basic UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Create Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Read & Update Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Create Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Read & Update Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Party Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 3
Party Read & Update | Testing - HTMLUnit | UI | Juntao | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 3
Complete & Tested Party Customer Use Cases & Services |  |  |  | 2013-08-20 |  |  | 2013-09-01
Account Deposit Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Account Deposit Read & Update Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Account Loan Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Account Loan Read & Update Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Test Plan | Writing | UI | Jon | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
UT 1 | Writing | UI | Geraldine | 2013-09-05 | 2013-09-05 | 3 | 2013-09-05 | 2013-09-05 | 3
Lab |  | PM & BA | Geraldine, Jon, Juntao | 2013-09-04 | 2013-09-04 | 2 | 2013-09-04 | 2013-09-04 | 2
Lab | Writing | PM & BA | Jon | 2013-09-05 | 2013-09-05 | 3 | 2013-09-05 | 2013-09-05 | 3
Project Scope | Change Management | PM & BA | Jon, Kevin | 2013-09-02 | 2013-09-07 | 2 | 2013-09-02 | 2013-09-07 | 2
Schedule | Revise | PM & BA | Jon | 2013-09-02 | 2013-09-07 | 2 | 2013-09-02 | 2013-09-07 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-02 | 2013-09-07 | 1 | 2013-09-02 | 2013-09-07 | 3
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-02 | 2013-09-07 | 1 | 2013-09-02 | 2013-09-07 | 1
Buffer Time |  |  |  | 2013-09-08
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-10 | 2013-09-11 | 10 | 2013-09-10 | 2013-09-11 | 10.5
MDM Billing Organization Read List Service | Taking Over | Back End | Kevin | 2013-09-01 | 2013-09-01 | 0.5 | 2013-09-10 | 2013-09-10 | 0.5
MDM Billing Organization Read List | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-13 | 2013-09-13 | 1 | 2013-09-12 | 2013-09-12 | 1
Direct Debit Authorization | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-12 | 2013-09-12 | 3 | 2013-09-12 | 2013-09-12 | 3
Technology Research | Normalised vs Denormalized Database Comparision | Back End | Kevin | 2013-09-10 | 2013-09-10 | 2 | 2013-09-10 | 2013-09-10 | 2
Customer's Accounts Dashboard Use Case - Transaction History Read | Develop Basic UI | UI | Juntao | 2013-09-10 | 2013-09-11 | 2 | 2013-09-10 | 2013-09-11 | 3
Customer's Accounts Dashboard Use Case - Account List Read | Develop Basic UI | UI | Juntao | 2013-09-10 | 2013-09-11 | 2 | 2013-09-10 | 2013-09-11 | 2
Customer's Accounts Dashboard Use Case - Transaction History Read | Develop Basic UI | UI | Juntao | 2013-09-14 | 2013-09-15 | 2 | 2013-09-15 | 2013-09-15 | 2
Customer's Accounts Dashboard Use Case - Account List Read | Develop Basic UI | UI | Juntao | 2013-09-14 | 2013-09-15 | 2 | 15 Sep, Sun | 2013-09-15 | 2
Payment Credit Transfer Bill Payment Use Case | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3 | 2013-09-11 | 2013-09-14 | 2
Payment Loan Repayment Full | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3 | 2013-09-11 | 2013-09-14 | 2
Payment Loan Repayment Partial | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3 | 2013-09-11 | 2013-09-14 | 2
Payment Loan Repayment Full | Develop Complete UI | UI | James | 2013-09-11 | 2013-09-15 | 1 | 2013-09-11 | 2013-09-14 | 1
Payment Loan Repayment Partial | Develop Complete UI | UI | James | 2013-09-11 | 2013-09-15 | 1 | 2013-09-11 | 2013-09-14 | 1
Debugging & Modifications | Payment_CreditTransfer_Create fix beneficiary ID error |  | Yao Guang | 2013-09-11 | 2013-09-11 | 1 | 2013-09-11 | 2013-09-11 | 0.5
Debugging & Modifications | Product Parameters Read |  | Kevin, James | 2013-09-13 | 2013-09-13 | 1 | 2013-09-13 | 2013-09-13 | 1
Debugging & Modifications | Redeploy Transaction Services |  | Yao Guang | 2013-09-10 | 2013-09-10 | 2 | 2013-09-10 | 2013-09-10 | 2
Debugging & Modifications | Added Leading Zeroes to Values |  | James | 2013-09-15 | 2013-09-15 | 2 | 2013-09-15 | 2013-09-15 | 2
Debugging & Modifications | Reworked Party, Account & Transactions |  | James | 2013-09-15 | 2013-09-15 | 3 | 2013-09-15 | 2013-09-15 | 3
UT 1 | Writing | UI | Geraldine | 2013-09-12 | 2013-09-12 | 4 | 2013-09-12 | 2013-09-12 | 3
UT 3 | Working with Client to ge Expert Users | UI | Jon | 2013-09-11 | 2013-09-11 | 1 | 2013-09-11 | 2013-09-11 | 1
Market Research | Comparing with Oracle Branch Teller | PM & BA | Jon, Kevin | 2013-09-13 | 2013-09-13 | 3 | 2013-09-13 | 2013-09-13 | 1 | Market Research Incomplete due to Inability to Access Oracle Software
Lab | Liasing with Other Groups | PM & BA | Jon | 2013-09-09 | 2013-09-09 | 2 | 2013-09-09 | 2013-09-09 | 2
Tutorial | Liasing with ESB Team | PM & BA | Jon | 2013-09-10 | 2013-09-10 | 1 | 2013-09-10 | 2013-09-10 | 1
Meetings | Weekly Client, Supervisor Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-09 | 2013-09-14 | 4 | 2013-09-09 | 2013-09-14 | 4
Project Scope | Change Management | PM & BA | Jon | 2013-09-09 | 2013-09-14 | 2 | 2013-09-09 | 2013-09-14 | 0.5
Schedule | Revise | PM & BA | Jon | 2013-09-09 | 2013-09-14 | 2 | 2013-09-09 | 2013-09-14 | 1
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-09 | 2013-09-14 | 3 | 2013-09-12 | 2013-09-12 | 2.5
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-09 | 2013-09-14 | 1 | 2013-09-09 | 2013-09-14 | 1
Buffer Time |  |  |  | 2013-09-15
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 8
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Debugging & Modifications | Party_CustomerAccountList_Read leading zeroes | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Payment_CreditTransfer_Create accountFrom mapping error | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Account_Loan_Read & Account_Deposit_Read maturitydate error | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Redeployed Account & Transaction Services | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Payment_CreditTransfer_Create error code fix | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 1 | 2013-09-16 | 2013-09-16 | 1
Transaction SMS Notification | Assist Client | Back End | Kevin | 2013-09-17 | 2013-09-17 | 1 | 2013-09-17 | 2013-09-17 | 1
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-19 | 2013-09-22 | 9 | 2013-09-19 | 2013-09-22 | 12
Debugging & Modifications | Redeployed Party_Customer_ReadIC | Back End | Yao Guang | 2013-09-20 | 2013-09-20 | 0.5 | 2013-09-20 | 2013-09-20 | 0.5
Credit Approval | Develop Base Case | Back End | Yao Guang | 2013-09-20 | 2013-09-20 | 1 | 2013-09-20 | 2013-09-20 | 1
Party Login Create | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-21 | 2013-09-21 | 2 | 2013-09-21 | 2013-09-21 | 2
Party Login Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-21 | 2013-09-21 | 1.5 | 2013-09-21 | 2013-09-21 | 1.5
Debugging & Modifications | Modified MDM Billing Organization Read List | Back End | Kevin | 2013-09-22 | 2013-09-22 | 2 | 2013-09-22 | 2013-09-22 | 2
Credit Approval | Develop Base Case | Back End | Kevin | 2013-09-22 | 2013-09-22 | 6 | 2013-09-22 | 2013-09-22 | 6.5
Customer's Accounts Dashboard Use Case | Develop Complete UI | UI | Juntao | 2013-09-16 | 2013-09-16 | 5 | 2013-09-16 | 2013-09-16 | 5
Debugging & Modifications | Transaction Deposit & Withdrawal Penalty Rate, validation issues | UI | James | 2013-09-16 | 2013-09-16 | 4 | 2013-09-16 | 2013-09-16 | 7
Lab | Working with Instructor Arul , Client & Other Teams | PM & BA | Jon | 2013-09-20 | 2013-09-20 | 2 | 2013-09-20 | 2013-09-20 | 4
Market Research | Approach OCBC Branch Manager | PM & BA | Geraldine | 2013-09-18 | 2013-09-18 | 1 | 2013-09-18 | 2013-09-18 | 1
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
Project Scope | Change Management | PM & BA | Jon | 2013-09-16 | 2013-09-21 | 2 | 2013-09-16 | 2013-09-21 | 2
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-09-16 | 2013-09-21 | 2 | 2013-09-16 | 2013-09-21 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-16 | 2013-09-21 | 1 | 2013-09-16 | 2013-09-21 | 1
User Test 1 | Preparation for Test Scenarios | PM & BA | Geraldine | 2013-09-17 | 2013-09-17 | 2 | 2013-09-17 | 2013-09-17 | 2
User Test 1 |  |  | Whole Team | 2013-09-20 | 2013-09-20 | 2 | 20 Sep, Fri | 20 Sep, Fri | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
Buffer Time |  |  |  | 2013-09-22
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Debugging & Modifications | Edited Transaction_LoanRepayment_Create & Transaction_LoanPartialRepayment_Create to include settlement account | Back End | Yao Guang | 2013-09-23 | 2013-09-23 | 1 | 2013-09-23 | 2013-09-23 | 1
Credit Approval | Develop Base Case | Back End | Yao Guang | 2013-09-23 | 2013-09-28 | 3 | 2013-09-23 | 2013-09-28 | 2.5 | Re-wrote Credit Rules from mvel to java dialect
Debugging & Modifications | Assist Client with Taking Over | Back End | Kevin | 2013-09-23 | 2013-09-23 | 0.5 | 2013-09-23 | 2013-09-23 | 0.5
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-23 | 2013-09-26 | 6 | 2013-09-23 | 2013-09-26 | 8
Wiki | Technical writeup for account & party services for wiki | PM & BA | Kevin | 2013-09-23 | 2013-09-23 | 3 | 2013-09-23 | 2013-09-23 | 3
Debugging & Modifications | Standardize & Revamp UI | UI | James | 2013-09-23 | 2013-09-23 | 5 | 2013-09-23 | 2013-09-23 | 7
Debugging & Modifications | Modified Account_Loan_Read & Product_List_Read Services | Back End | Kevin | 2013-09-24 | 2013-09-24 | 0.5 | 2013-09-24 | 2013-09-24 | 0.5
Party User PIN Create | Taking Over | Back End | Juntao | 2013-09-24 | 2013-09-24 | 1.5 | 2013-09-24 | 2013-09-24 | 1.5
Party User PIN Create | Develop Integration Code | Back End | Juntao | 2013-09-24 | 2013-09-24 | 1.5 | 2013-09-24 | 2013-09-24 | 1.5
Debugging & Modifications | Modified SMU Core Services for Lab Walkthrough Standardization | Back End | Kevin, Yao Guang | 2013-09-27 | 2013-09-27 | 4 | 2013-09-27 | 2013-09-27 | 4
Debugging & Modifications | Modified Payment Loan Repayment Full and Partial | Back End | Yao Guang | 2013-09-28 | 2013-09-28 | 0.5 | 2013-09-28 | 2013-09-28 | 0.5
Debugging & Modifications | Debug Transaction_History_Read (2 bugs) | Back End | Kevin | 2013-09-29 | 2013-09-29 | 1 | 2013-09-29 | 2013-09-29 | 1
Party User PIN Create | Develop Basic UI | UI | Juntao | 2013-09-25 | 2013-09-25 | 1 | 2013-09-25 | 2013-09-25 | 1.5
Party User PIN Create | Develop Complete UI | UI | Juntao | 2013-09-25 | 2013-09-25 | 1 | 2013-09-25 | 2013-09-25 | 1.5
Debugging & Modifications | Modified Payment Credit Transfer Bill Payment Use Case, adjusted buttonc olour, date calendar changes, minimum amount | UI | James | 2013-09-23 | 2013-09-23 | 1 | 2013-09-23 | 2013-09-23 | 2
Debugging & Modifications | Party User PIN Create | UI | Juntao | 2013-09-27 | 2013-09-27 | 1 | 2013-09-27 | 2013-09-27 | 2
User Test 2 | Preparation for Test Scenarios | PM & BA | Geraldine | 2013-09-29 | 2013-09-29 | 2 | 2013-09-29 | 2013-09-29 | 2
Lab | Working with Instructor Arul & Client | PM & BA | Jon | 2013-09-20 | 2013-09-20 | 6 | 2013-09-20 | 2013-09-20 | 6
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4
Project Scope | Change Management | PM & BA | Jon | 2013-09-23 | 2013-09-29 | 2 | 2013-09-23 | 2013-09-29 | 6 | Increased 1 on 1 Meetings between BA & Client due to Sharp Increase in Bugs, Modifications and Changes
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-23 | 2013-09-29 | 3 | 2013-09-23 | 2013-09-29 | 3
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-23 | 2013-09-29 | 1 | 2013-09-23 | 2013-09-29 | 1
Buffer Time |  |  |  | 2013-09-28 | 2013-09-29 |  |  |  |  | Exam Prep
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 9
FYP Wk 23 / SMU Wk 7 |  |  |  | 2013-09-30 | 2013-10-06 |  |  |  |  | Midterm
User Test 2 | Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 2
User Test 2 |  |  |  | 2013-10-02 | 2013-10-02 | 2
User Test 2 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 2
User Test 2 | Making Changes to Product | Whole Team | Jon, James, Juntao, Kevin, Yao Guang |  |  | 2
Buffer Time |  |  |  | 2013-10-06
FYP Wk 24 / SMU Wk 8 |  |  |  | 2013-10-07 | 2013-10-13
Credit Approval | Develop Base Case | Back End | Kevin, Yao Guang |  |  | 3 |  |  |  | Scope changed (No. 15)
Credit Approval | Develop Error Flows | Back End | Kevin, Yao Guang |  |  | 1.5
Credit Approval | Deploy to Server | Back End | Kevin, Yao Guang |  |  | 1
Credit Approval | Develop Integration Code | Back End | Kevin, Yao Guang |  |  | 1
Modify Business Rules Parameters | Develop | Back End | Kevin, Yao Guang |  |  | 5
Generate Data Set | Develop | Back End | Kevin, Yao Guang |  |  | 2
Direct Debit Authorization | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3
Direct Debit Authorization | Develop Complete UI | UI | James | 2013-09-11 | 2013-09-15 | 1
Account Deposit Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Account Deposit Read & Update Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Account Loan Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Account Loan Read & Update Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Account Deposit Create Use Case | Testing - Junit (Product Parameters Read) | UI | Juntao | 2013-09-12 | 2013-09-13 | 0.5
Account Deposit Read & Update Use Case | Testing - Junit (Product Parameters Read) | UI | Juntao | 2013-09-12 | 2013-09-13 | 0.5
Account Loan Create Use Case | Testing - Junit (Product Parameters Read) | UI | Juntao | 2013-09-12 | 2013-09-13 | 0.5
Account Loan Read & Update Use Case | Testing - Junit (Product Parameters Read) | UI | Juntao | 2013-09-12 | 2013-09-13 | 0.5
Customer's Accounts Dashboard Use Case - Transaction History Read | Testing - JUnit | UI | Juntao |  |  | 1
Customer's Accounts Dashboard Use Case - Account List Read | Testing - JUnit | UI | Juntao |  |  | 1
Customer's Accounts Dashboard Use Case - Transaction History Read | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 1
Customer's Accounts Dashboard Use Case - Account List Read | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 1
Manage Customer's Deposit Accounts Use Case | Testing - JUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Manage Customer's Loan Accounts Use Case | Testing - JUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Manage Customer's Deposit Accounts Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Manage Customer's Loan Accounts Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-12 | 2013-09-13 | 1
Transaction Deposit Use Case | Testing - JUnit | UI | Juntao |  |  | 1
Transaction Withdrawal Use Case | Testing - JUnit | UI | Juntao |  |  | 1
Transaction History Read Use Case | Testing - JUnit | UI | Juntao |  |  | 1
Transaction Deposit Use Case | Testing - HTMLUnit | UI | Juntao |  |  | 1
Transaction Withdrawal Use Case | Testing - HTMLUnit | UI | Juntao |  |  | 1
Transaction History Read Use Case | Testing - HTMLUnit | UI | Juntao |  |  | 1
Payment Credit Transfer Bill Payment Use Case | Testing - JUnit | UI | James, Juntao, Jon |  |  | 1
Payment Loan Repayment Full | Testing - JUnit | UI | James, Juntao, Jon |  |  | 1
Payment Loan Repayment Partial | Testing - JUnit | UI | James, Juntao, Jon |  |  | 1
Direct Debit Authorization | Testing - JUnit | UI | James, Juntao, Jon |  |  | 1
Payment Credit Transfer Bill Payment Use Case | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 1
Payment Loan Repayment Full | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 1
Payment Loan Repayment Partial | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 1
Direct Debit Authorization | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 1
Completed & Tested Account Use Cases & Services |  |  |  | 2013-09-15 |  |  | 2013-09-22
Completed & Tested Transactions |  | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 16 Sep, Mon |  |  | 2013-09-29
Midterm | Prototype Demo Preparation | UI | James, Juntao, Yao Guang |  |  | 6
Midterm | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 6
Midterm Presentation |  |  |  | 2013-10-10 | 2013-10-10
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 6
Midterm | Making Changes to Product | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 10
Credit Approval | Testing - JUnit | UI | James, Juntao, Jon |  |  | 2 |  |  |  | Special Attention*
Credit Approval | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 8 |  |  |  | Special Attention*
Credit Approval | Debugging | UI | Jon, James, Juntao, Kevin, Yao Guang |  |  | 8
Modify Business Rules Parameters | Develop | Back End | Kevin, Yao Guang |  |  | 8
Generate Data Set | Develop | Back End | Kevin, Yao Guang |  |  | 8
Project Scope | Change Management | PM & BA | Jon |  |  | 2
Schedule | Revise | PM & BA | Jon, Geraldine |  |  | 4
Wiki | Weekly Update | PM & BA | Geraldine |  |  | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon |  |  | 1
Buffer Time |  |  |  | 2013-10-12 | 2013-10-13
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 10
FYP Wk 25 / SMU Wk 9 |  |  |  | 2013-10-14 | 2013-10-20 |  |  |  |  | Hari Raya Haji (15 Oct, Tue)
Modify Business Rules Parameters | Develop Complete UI | UI | James, Juntao |  |  | 4
Generate Data Set | Develop Complete UI | UI | James, Juntao |  |  | 4
Modify Business Rules Parameters | Testing - JUnit | Back End | James, Juntao, Jon |  |  | 2
Generate Data Set | Testing - JUnit | Back End | James, Juntao, Jon |  |  | 2
Modify Business Rules Parameters | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 4
Generate Data Set | Testing - HTMLUnit | UI | James, Juntao, Jon |  |  | 4
Modify Business Rules Parameters | Debugging | UI | Jon, James, Juntao, Kevin, Yao Guang |  |  | 8 |  |  |  | Special Attention*
Generate Data Set | Debugging | UI | Jon, James, Juntao, Kevin, Yao Guang |  |  | 8 |  |  |  | Special Attention*
Run Test | Develop | Back End | Kevin, Yao Guang |  |  | 4
Run Test | Develop Error Flows | Back End | Kevin, Yao Guang |  |  | 4
Run Test | Deploy to Server | Back End | Kevin, Yao Guang |  |  | 2
Run Test | Develop Integration Code | Back End | Kevin, Yao Guang |  |  | 2
Run Test | Develop Basic UI | UI | James, Juntao |  |  | 2
Run Test | Develop Complete UI | UI | James, Juntao |  |  | 2
Display Test Results | Develop Basic UI | UI | James, Juntao |  |  | 2
Display Test Results | Develop Complete UI | UI | James, Juntao |  |  | 2
Project Scope | Change Management | PM & BA | Jon |  |  | 2
Schedule | Revise | PM & BA | Jon, Geraldine |  |  | 4
Wiki | Weekly Update | PM & BA | Geraldine |  |  | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon |  |  | 1
Buffer Time |  |  |  | 2013-10-20 | 2013-10-20
FYP Wk 26 / SMU Wk 10 |  |  |  | 2013-10-21 | 2013-10-27
Run Test | Testing - JUnit | Back End |  |  |  | 2
Display Test Results | Testing - JUnit | UI |  |  |  | 1
Run Test | Testing - HTMLUnit | Back End |  |  |  | 4
Display Test Results | Testing - HTMLUnit | UI |  |  |  | 4
Run Test | Debugging | Back End |  |  |  | 4
Display Test Results | Debugging | UI |  |  |  | 4
Project Scope | Change Management | PM & BA | Jon |  |  | 2
Schedule | Revise | PM & BA | Jon, Geraldine |  |  | 4
Wiki | Weekly Update | PM & BA | Geraldine |  |  | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon |  |  | 1
User Test 3 | Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 2
User Test 3 |  |  |  | 2013-10-25 | 2013-10-25 | 2
User Test 3 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 2
User Test 3 | Making Changes to Product | Whole Team | Jon, James, Juntao, Kevin, Yao Guang |  |  | 2
Buffer Time |  |  |  | 2013-10-27
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 11
FYP Wk 27 / SMU Wk 11 |  |  |  | 2013-10-28 | 2013-11-03
Project Scope | Change Management | PM & BA | Jon |  |  | 2
Schedule | Revise | PM & BA | Jon, Geraldine |  |  | 4
Wiki | Weekly Update | PM & BA | Geraldine |  |  | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon |  |  | 1
Buffer Time |  |  |  | 2013-11-02 | 2013-11-03
FYP Wk 28 / SMU Wk 12 |  |  |  | 2013-11-04 | 2013-11-10
UAT | Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 8
User Acceptance Test |  | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-11-08 | 2013-11-08 | 8
UAT | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 10
UAT | Making Changes to Product | Whole Team | Jon, James, Juntao, Kevin, Yao Guang |  |  | 10
Project Scope | Change Management | PM & BA | Jon |  |  | 2
Schedule | Revise | PM & BA | Jon, Geraldine |  |  | 4
Wiki | Weekly Update | PM & BA | Geraldine |  |  | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon |  |  | 1
Buffer Time |  |  |  | 2013-11-09 | 2013-11-10
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 12
FYP Wk 29 / SMU Wk 13 |  |  |  | 2013-11-11 | 2013-11-17 |  |  |  |  | Poster Due (12 Nov, Tue)
Poster | Preparation |  | Jon |  |  | 8
Poster Due |  |  |  | 2013-11-12
Project Scope | Change Management | PM & BA | Jon |  |  | 2
Schedule | Revise | PM & BA | Jon, Geraldine |  |  | 4
Wiki | Weekly Update | PM & BA | Geraldine |  |  | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon |  |  | 1
Buffer Time |  |  |  | 2013-07-13 | 2013-07-17
FYP Wk 30 / SMU Wk 14 |  |  |  | 2013-11-18 | 2013-11-24
Finals | Presentation Preparation | Whole Team | James, Juntao, Kevin, Yao Guang |  |  | 20
Finals | Demo Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang |  |  | 20
FYP Wk 31 / SMU Wk 15 |  |  |  | 2013-11-25 | 2013-12-01 |  |  |  |  | Finals
Finals |  |  |  | 2013-11-29 | 2013-12-05
FYP Wk 32 / SMU Wk 16 |  |  |  | 2013-12-02 | 2013-12-08 |  |  |  |  | Poster Day (7 Dec, Sat)
Poster Day |  |  |  | 2013-12-05

## Changes
Changes Made to Project
No. | Description | Change | Completed | Status
1 | SharePoint moved to FYP Team Creagend's Scope | 2013-06-01 | 2013-06-01 | DONE
2 | New Architecture Requirement for SMU Core Services & Flexcube to be interchangeable | 2013-06-29
| --> Modifying & Standardizing Existing TIBCO processes with Flexcube Tibco Processes (4) |  | 2013-07-03 | DONE
- Account Deposit Create
- Account Deposit Read
- Account Deposit Update
- Account List Read
--> Additional Task for Transaction TIBCO processes with Flexcube Tibco Processes (8)
- Account Loan Create
- Account Loan Read
- Account Loan Update
| - Transaction Deposit |  | 2013-08-03 | DONE
| - Transaction Withdrawal |  | 2013-08-03 | DONE
| - Transaction History Read |  |  | NOT YET
| - Payment Credit Transfer |  |  | NOT YET
| - Payment Loan Repayment Full |  |  | NOT YET
3 | Modified Common Data Model - Transaction | 2013-07-06 | 2013-07-06 | DONE
4 | Change in Service Mediation Layer | 2013-07-12 | 2013-07-14 | DONE
--> Modifying existing TIBCO processes to conform to new service mediation (10)
| - Party Customer Create |  | 2013-07-12 | DONE
- Party Customer Read
- Party Customer Update
| - Account Deposit Create |  | 2013-07-13 | DONE
- Account Deposit Read
- Account Deposit Update
| - Account Loan Create |  | 2013-07-14 | DONE
- Account Loan Read
- Account Loan Update
| - Account List Read |  | 2013-07-14 | DONE
5 | Modified Common Data Model - Account | 2013-07-22 | 2013-07-27 | DONE
--> Modifying existing TIBCO processes (7)
- Account Deposit Create
- Account Deposit Read
- Account Deposit Update
- Account Loan Create
- Account Loan Read
- Account Loan Update
- Account List Read
6 | New Business Logic Requirements for Transaction Withdrawal and Transaction Deposit | 2013-07-27 |  | NOT YET
--> Additional Business Logic Events in TIBCO processes (2)
- internal TIBCO: database read of withdrawal limit + call a web service for SMS
- New Service: SMS notification when transaction above withdrawal limit for above services
7 | Cross Sell Engine moved to FYP Team Creagend's Scope | 2013-08-03 |  | DONE
8 | BRMS handed over to FYP Team Creagend's Scope | 2013-08-03 |  | DONE
9 | Blacklist check for originate a customer dropped | 2013-08-03 |  | DONE
10 | Credit Bureau Check for loan dropped | 2013-08-03 |  | DONE
11 | New Service Payment Loan Repayment Partial | 2013-08-03 |  | NOT YET
12 | New Business Logic Requirements for Account Loan Create & Account Loan Read | 2013-08-03 |  | NOT YET
--> Modify existing TIBCO processes Account Loan Create & Account Loan Read (2)
- internal: installment amount computed internally for account loan create
- internal: compute PenaltyRate for account loan create
- output: return installment amount in output for account loan read
- output: return PenaltyRate for account loan read
13 | New Requirement to Integrate Service MDM Customer Type Read, MDM Product Type Read & MDM Billing Organization Read List | 2013-08-03 |  | NOT YET
--> Develop integration code for mentioned services (3)
--> Integrate with front end UI (5 pages)
- Party Create
- Account Deposit Create
- Account Loan Create
- Payment Credit Transfer Bill Payment
- Direct Debit Authorization
14 | New Requirement to Integrate Service Product Parameters Read |  |  | NOT YET
--> Develop integration code (1)
--> Integrate with front end UI (4 pages)
- Account Deposit Create
- Account Deposit Read & Update
- Account Loan Create
- Account Deposit Read & Update
15 | New X-Factor Credit Approval | 2013-08-07 |  | NOT YET
--> Create spreadsheet for acceptance as POC
16 | New X-Factor Business Rules Teaching Tool | 2013-08-07 |  | NOT YET
17 | New Requirement where maturity date in smu_core_services is changed to date from string | 2013-08-13 |  | NOT YET
--> Modifying existing TIBCO processes (4)
- Account Deposit Create
- Account Deposit Update
- Account Loan Create
- Account Loan Update
18 | Drop Payment Credit Transfer Account | 2013-08-23 |  | DONE
19 | New Global Parameters for Database | 2013-08-23 |  | DONE
--> Modifying existing TIBCO processes (14)
20 | Fixed String for Integer Fields
accountTo and accountFrom
21 | Transaction State Activity Addition for TIBCO Projects
22 | Renaming of Loan Repayment Partial & Full Services

## Risks
Risk Management
Risk Exposure |  | Likelihood |  |  | S/N | Risk Statement | Consequence | Likelihood | Impact | Level (Derived) | Risk Management Strategy
|  | Low | Medium | High | 1 | Team is unfamiliar with software (TIBCO, Drools, Guvnor etc.) | (a) Unable to grasp the scale and difficulty of the project | Medium | High | A | (a) Team started early since May to familiarize with software
Impact | High | B | A | A |  |  | (b) Team does not know how and where to start programming |  |  |  | (b) Background in Enterprise Integration course provided a foundation, albeit insufficient
| Medium | C | B | A |  |  | (c) Project delays due to incorrect estimates on project schedule
| Low | C | C | B |  |  | (d) Increased tendency for last minute work
Risk Exposure = Probability of Occurrence X Impact on Project |  |  |  |  | 2 | Change in Project Requirements & Scope from Client | (a) Unforeseen tasks and demands on project team | High | High | A | (a) Define current project requirements as clearly as possible
[7 empty] | (b) Tendency for Scope Creep, FYP becomes more than what we can handle |  |  |  | (b) Whole team to make decision in inclusion / exclusion of scope changes
[7 empty] | (c) Deliverables quality and / or inability to complete entire project scope affected |  |  |  | (c) Spend more time with the client!
Risk Management Strategies
Strategies | Strategies |  |  |  | 3 | Other FYP Teams developing retail banking channels may not know how to invoke our service | (a) Reduced effectiveness of SOA architecture | Medium | Medium | B | Provide a tutorial to other teams containing sample java code and a walkthrough on how to generate a SOAP request
Risk Avoidance | Reorganize the project plan to eliminate the risk | [5 empty] | (b) Unable to prove successfulness of service deployment
Risk Mitigation | Reduce the probability or impact of the risk to an acceptable level. E.g. Scope reduction, additional tests, incorporating redudancy
Risk Transfer | Move responsibility of potential risk to a third party. |  |  |  | 4 | Project Scope not logically related together, some components overlapping with other FYP teams | Some components of project not seen as value-adding. Difficulty in defining requirements and claiming credit for work done. | Medium | Medium | B | Both teams' PMs and BAs to coordinate more closely on wiki and presentations
Risk Acceptance | Live with it, can't do anything, no choice.
Contingency Plan | Plan "Plan B". This kicks in when the risk is about to materialize or has occurred |  |  |  | 5 | Unavailability of SMU tBank Servers due to Virtual Machine migration from VMWare to Virtual Box | Entire FYP project could be delayed severely, failure to deploy during acceptance | High (100% Certain) | Medium | A | Run relevant back end systems on our own team's laptops for demonstration at FYP acceptance presentation if services not yet deployed
[5 empty] | 6 | Delay / Changes in delivery of services we need to integrate but are developed by others | Severe downstream delays in FYP project | High | High | A | Reschedule tasks in schedule, perform tasks that do not face such downstream risk in the event of a delay
[5 empty] | 7 | Failure in Accessing FICO Credit Check Web Service | Unable to complete Open Loan account use case | High | Low | B | Developers to explore feasibility through Proof of Concept as soon as possible. If unsuccessful, negotiate with Project Sponsor to remove Credit Check requirement from scope
[5 empty] | 8 | Lack of market research due to high confidentiality of branch teller applications | (a) Branch Teller Application does not follow industry best practices | High | High | A | (a) Approach Client & Professors with Banking Industry links for contacts to interview and consult
[7 empty] | (b) Branch Teller Application is too different from industry norms |  |  |  | (b) Try to obtain industry product samples despite bank branches disallowing us to view their Branch Teller Applications

## MIlestones (Table)
Milestones (Table)
Iteration 1
FYP Wk 1 |  |  |  | 2013-04-29 | 2013-05-05 |  |  |  |  | Labour Day (1 May, Wed)
FYP Wk 2 |  |  |  | 2013-05-06 | 2013-05-12
FYP Wk 3 |  |  |  | 2013-05-13 | 2013-05-19
FYP Wk 4 |  |  |  | 2013-05-20 | 2013-05-26 |  |  |  |  | Vesak Day (24 May, Fri)
FYP Wk 5 |  |  |  | 2013-05-27 | 2013-06-02
Iteration 2
FYP Wk 6 |  |  |  | 2013-06-03 | 2013-06-09
FYP Wk 7 |  |  |  | 2013-06-10 | 2013-06-16
FYP Wk 8 |  |  |  | 2013-06-17 | 2013-06-23 |  |  |  |  | Proposal (20 June, Fri)
Iteration 3
FYP Wk 9 |  |  |  | 2013-06-24 | 2013-06-30
FYP Wk 10 |  |  |  | 2013-07-01 | 2013-07-07
Iteration 4
FYP Wk 11 |  |  |  | 2013-07-08 | 2013-07-14
FYP Wk 12 |  |  |  | 2013-07-15 | 2013-07-21
Party Customer Services Complete |  |  |  | 2013-07-21 |  |  | 2013-07-21
FYP Wk 13 |  |  |  | 2013-07-22 | 2013-07-28
Iteration 5
FYP Wk 14 |  |  |  | 2013-07-29 | 2013-08-04
Complete Account Services |  |  |  | 2013-08-04 |  |  | 2013-08-04
FYP Wk 15 |  |  |  | 2013-08-05 | 2013-08-11 |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
FYP Wk 16 |  |  |  | 2013-08-12 | 2013-08-18 |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance Presentation |  |  | Jon | 2013-08-16 | 2013-08-16 | 2 | 2013-08-16 | 2013-08-16 | 2
Iteration 6
FYP Wk 17 / SMU Wk 1 |  |  |  | 2013-08-19 | 2013-08-25 |  |  |  |  | Registration (21 Aug, Wed)
Registration |  |  |  | 2013-08-21
FYP Wk 18 / SMU Wk 2 |  |  |  | 2013-08-26 | 2013-09-01
Iteration 7
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Complete & Tested Party Customer Use Cases & Services |  |  |  | 2013-08-20 |  |  | 2013-09-01
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
Iteration 8
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
User Test 1 |  |  |  | 2013-09-20 | 2013-09-20 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 9
FYP Wk 23 / SMU Wk 7 |  |  |  | 2013-09-30 | 2013-10-06 |  |  |  |  | Midterm
User Test 2 |  |  |  | 2013-10-02 | 2013-10-02 | 2
FYP Wk 24 / SMU Wk 8 |  |  |  | 2013-10-07 | 2013-10-13
Midterm Presentation |  |  |  | 2013-10-10 | 2013-10-10
Iteration 10
FYP Wk 25 / SMU Wk 9 |  |  |  | 2013-10-14 | 2013-10-20 |  |  |  |  | Hari Raya Haji (15 Oct, Tue)
FYP Wk 26 / SMU Wk 10 |  |  |  | 2013-10-21 | 2013-10-27
Completed & Tested Account Use Cases & Services |  |  |  | 2013-09-15 |  |  | 2013-10-24
Completed & Tested Transactions |  | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 16 Sep, Mon |  |  | 2013-10-24
User Test 3 |  |  |  | 2013-10-25 | 2013-10-25 | 2
Iteration 11
FYP Wk 27 / SMU Wk 11 |  |  |  | 2013-10-28 | 2013-11-03
FYP Wk 28 / SMU Wk 12 |  |  |  | 2013-11-04 | 2013-11-10
User Acceptance Test |  | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-11-08 | 2013-11-08 | 8
Iteration 12
FYP Wk 29 / SMU Wk 13 |  |  |  | 2013-11-11 | 2013-11-17 |  |  |  |  | Poster Due (12 Nov, Tue)
Poster Due |  |  |  | 2013-11-12
FYP Wk 30 / SMU Wk 14 |  |  |  | 2013-11-18 | 2013-11-24
FYP Wk 31 / SMU Wk 15 |  |  |  | 2013-11-25 | 2013-12-01 |  |  |  |  | Finals
Finals |  |  |  | 2013-11-29 | 2013-12-05
FYP Wk 32 / SMU Wk 16 |  |  |  | 2013-12-02 | 2013-12-08 |  |  |  |  | Poster Day (7 Dec, Sat)
Poster Day |  |  |  | 2013-12-05

## Test Plan (hidden)
Test Plan
Test | Date |  | Users | Approach | Use Cases Tested
User Test 1 | 20 Sep, Fri |  | Client | User Test | Login | Party Create | Party Read & Update | Account Deposit Create | Manage Customer’s Deposit Accounts | Account Deposit Read & Update | Account Loan Create | Manage Customer’s Loan Accounts | Account Loan Read & Update
User Test 2 | 2 Oct, Wed |  | IS 419 Retail Banking Processes & Technology Class | User Test | Login | Party Create | Party Read & Update | Account Deposit Create | Manage Customer’s Deposit Accounts | Account Deposit Read & Update | Account Loan Create | Manage Customer’s Loan Accounts | Account Loan Read & Update
User Test 3 | 25 Oct, Fri |  | Banking Executives (SIS Board of Directors) | User Test | Login | Party Create | Party Read & Update | Customer’s Accounts Dashboard | Account Deposit Create | Manage Customer’s Deposit Accounts | Account Deposit Read & Update | Account Loan Create | Manage Customer’s Loan Accounts | Account Loan Read & Update
[5 empty] | Transaction Deposit | Transaction Withdrawal | Transaction History Read | Payment Credit Transfer Bill Payment | Payment Loan Repayment Full | Payment Loan Repayment Partial | Direct Debit Authorization
[5 empty] | Credit Approval | Business Rules | Upload Documents | Read Documents | Modify Business Rules | Generate Data Set | Run Test | Display Test Results
User Acceptance Test | 8 Nov, Fri |  | Client, SMU tBank FYP Teams, ESB Team | UAT | Login | Party Create | Party Read & Update | Customer’s Accounts Dashboard | Account Deposit Create | Manage Customer’s Deposit Accounts | Account Deposit Read & Update | Account Loan Create | Manage Customer’s Loan Accounts | Account Loan Read & Update
[5 empty] | Transaction Deposit | Transaction Withdrawal | Transaction History Read | Payment Credit Transfer Bill Payment | Payment Loan Repayment Full | Payment Loan Repayment Partial | Direct Debit Authorization
[5 empty] | Credit Approval | Business Rules | Upload Documents | Read Documents | Modify Business Rules | Generate Data Set | Run Test | Display Test Results
Users
Environment
Method | Tasks
| Measures | Surveys etc. | Time? | Whether path on completing a task differs from what we expect

## Schedule Metrics
Schedule Metrics
|  | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10 | Iteration 11 |  |  | Total | Average
Geraldine | Planned | 0 | 12 | 18 | 21 | 57 | 16 | 19 | 32 |  |  |  | Geraldine | Planned | 175
| Actual | 0 | 12 | 18 | 21 | 73 | 16 | 23 | 32 |  |  |  |  | Actual | 195
| Schedule Metrics |  | 1 | 1 | 1 | 1.2807 | 1 | 1.2105 | 1 |  |  |  |  | Schedule Metrics |  | 1.1143
Jon | Planned | 3 | 17 | 20 | 17 | 61 | 28 | 27 | 32 |  |  |  | Jon | Planned | 205
| Actual | 4 | 21 | 20 | 15 | 75 | 30.5 | 22.5 | 38 |  |  |  |  | Actual | 226
| Schedule Metrics | 1.3333 | 1.2353 | 1 | 0.88235 | 1.2295 | 1.0893 | 0.83333 | 1.1875 |  |  |  |  | Schedule Metrics |  | 1.1024
Kevin | Planned | 28 | 59 | 27 | 50 | 54 | 42 | 32 | 48 |  |  |  | Kevin | Planned | 340
| Actual | 29 | 59 | 28 | 52 | 78.5 | 33.5 | 31.5 | 51.5 |  |  |  |  | Actual | 363
| Schedule Metrics | 1.0357 | 1 | 1.037 | 1.04 | 1.4537 | 0.79762 | 0.98438 | 1.0729 |  |  |  |  | Schedule Metrics |  | 1.0676
Yao Guang | Planned | 15 | 35 | 27 | 50 | 56 | 26 | 28 | 43.5 |  |  |  | Yao Guang | Planned | 280.5
| Actual | 16 | 35 | 28 | 52 | 99 | 23.5 | 29 | 46 |  |  |  |  | Actual | 328.5
| Schedule Metrics | 1.0667 | 1 | 1.037 | 1.04 | 1.7679 | 0.90385 | 1.0357 | 1.0575 |  |  |  |  | Schedule Metrics |  | 1.1711
James | Planned | 0 | 0 | 14 | 28 | 50 | 24 | 25 | 22 |  |  |  | James | Planned | 163
| Actual | 0 | 0 | 14 | 27 | 84 | 19 | 22 | 26 |  |  |  |  | Actual | 192
| Schedule Metrics |  |  | 1 | 0.96429 | 1.68 | 0.79167 | 0.88 | 1.1818 |  |  |  |  | Schedule Metrics |  | 1.1779
Juntao | Planned | 0 | 0 | 14 | 28 | 50 | 22 | 18 | 23 |  |  |  | Juntao | Planned | 155
| Actual | 0 | 0 | 14 | 27 | 84 | 23.5 | 23 | 23 |  |  |  |  | Actual | 194.5
| Schedule Metrics |  |  | 1 | 0.96429 | 1.68 | 1.0682 | 1.2778 | 1 |  |  |  |  | Schedule Metrics |  | 1.2548
Total | Planned | 46 | 123 | 120 | 194 | 328 | 158 | 149 | 200.5 | 0 | 0 | 0 | Total | Planned | 1318.5
| Actual | 49 | 127 | 122 | 194 | 493.5 | 146 | 151 | 216.5 | 0 | 0 | 0 |  | Actual | 1499
| Schedule Metrics | 1.0652 | 1.0325 | 1.0167 | 1 | 1.5046 | 0.92405 | 1.0134 | 1.0798 |  |  |  |  | Schedule Metrics |  | 1.1369

## Bug Metrics
Bugs listed according to the Date Created | [7 empty] | * Date of metrics is calculated on Sat (Sun is our buffer day)
[6 empty] | Updated Status |  |  |  |  | Severity
No | Bug ID | Current Status | Date Created | Date Resolved | Severity | Total no. of bugs | 37 | FYP Wk | End Date (Sat) | Active Bugs | 1 | 5 | 10 | Bug Metrics
1 | #12 | Resolved | 2013-07-30 | 2013-08-03 | 1 | Active bugs | 1 | 1 | 2013-05-04 | 0 | 0 | 0 | 0 | 0
2 | #16 | Resolved | 2013-08-01 | 2013-08-04 | 1 | Resolved bugs | 34 | 2 | 2013-05-11 | 0 | 0 | 0 | 0 | 0
3 | #32 | Resolved | 2013-08-03 | 2013-08-03 | 2 | Closed bugs | 1 | 3 | 2013-05-18 | 0 | 0 | 0 | 0 | 0
4 | #54 | Resolved | 2013-08-03 | 2013-08-03 | 1 | *Not resolved but it doesn’t matter anymore |  | 4 | 2013-05-25 | 0 | 0 | 0 | 0 | 0
5 | #67 | Resolved | 2013-08-03 | 2013-08-21 | 1 |  |  | 5 | 2013-06-01 | 0 | 0 | 0 | 0 | 0
6 | #36 | Resolved | 2013-08-03 | 2013-08-21 | 1 |  |  | 6 | 2013-06-08 | 0 | 0 | 0 | 0 | 0
7 | #40 | Resolved | 2013-08-03 | 2013-08-21 | 1 |  |  | 7 | 2013-06-15 | 0 | 0 | 0 | 0 | 0
8 | #62 | Resolved | 2013-08-03 | 2013-08-21 | 1 |  |  | 8 | 2013-06-22 | 0 | 0 | 0 | 0 | 0
9 | #19 | Resolved | 2013-08-03 | 2013-08-30 | 1 |  |  | 9 | 2013-06-29 | 0 | 0 | 0 | 0 | 0
10 | #24 | Resolved | 2013-08-03 | 2013-08-30 | 1 |  |  | 10 | 2013-07-06 | 0 | 0 | 0 | 0 | 0
11 | #29 | Closed | 2013-08-03 | 2013-09-03 | 1 |  |  | 11 | 2013-07-13 | 0 | 0 | 0 | 0 | 0
12 | #91 | Resolved | 2013-08-04 | 2013-08-15 | 2 |  |  | 12 | 2013-07-20 | 0 | 0 | 0 | 0 | 0
13 | #100 | Resolved | 2013-08-14 | 2013-08-15 | 2 |  |  | 13 | 2013-07-27 | 0 | 0 | 0 | 0 | 0
14 | #107 | Resolved | 2013-08-15 | 2013-08-15 | 1 |  |  | 14 | 2013-08-03 | 8 | 8 | 0 | 0 | 8
15 | #112 | Resolved | 2013-08-15 | 2013-08-15 | 1 |  |  | 15 | 2013-08-10 | 8 | 7 | 1 | 0 | 12
16 | #117 | Resolved | 2013-08-15 | 2013-08-15 | 3 |  |  | 16 | 2013-08-17 | 7 | 7 | 0 | 0 | 7
17 | #126 | Resolved | 2013-08-15 | 2013-08-15 | 2 |  |  | 17 | 2013-08-24 | 4 | 3 | 1 | 0 | 8
18 | #130 | Resolved | 2013-08-15 | 2013-08-15 | 1 |  |  | 18 | 2013-08-31 | 2 | 1 | 1 | 0 | 6
19 | #135 | Resolved | 2013-08-15 | 2013-08-15 | 3 |  |  | 19 | 2013-09-07 | 1 | 0 | 1 | 0 | 5
20 | #145 | Resolved | 2013-08-21 | 2013-08-30 | 2 |  |  | 20 | 2013-09-14 | 3 | 2 | 1 | 0 | 7
21 | #159 | Resolved | 2013-08-29 | 2013-09-08 | 2 |  |  | 21 | 2013-09-21 | 4 | 2 | 2 | 0 | 12
22 | #180 | Resolved | 2013-09-03 | 2013-09-07 | 1 |  |  | 22 | 2013-09-28 | 1 | 1 | 0 | 0 | 1
23 | #184 | Resolved | 2013-09-04 | 2013-09-07 | 2 |  |  | 23 | 2013-10-05 |  |  |  |  | 0
24 | #190 | Resolved | 2013-09-06 | 2013-09-07 | 1 |  |  | 24 | 2013-10-12 |  |  |  |  | 0
25 | #193 | Resolved | 2013-09-06 | 2013-09-07 | 1 |  |  | 25 | 2013-10-19 |  |  |  |  | 0
26 | #199 | Resolved | 2013-09-06 | 2013-09-07 | 1 |  |  | 26 | 2013-10-26 |  |  |  |  | 0
27 | #202 | Resolved | 2013-09-06 | 2013-09-07 | 1 |  |  | 27 | 2013-11-02 |  |  |  |  | 0
28 | #205 | Resolved | 2013-09-06 | 2013-09-07 | 1 |  |  | 28 | 2013-11-09 |  |  |  |  | 0
29 | #223 | Resolved | 2013-09-12 | 2013-09-16 | 1 |  |  | 29 | 2013-11-16 |  |  |  |  | 0
30 | #226 | Resolved | 2013-09-12 | 2013-09-16 | 2 |  |  | 30 | 2013-11-23 |  |  |  |  | 0
31 | #229 | Resolved | 2013-09-13 | 2013-09-16 | 1 |  |  | 31 | 2013-11-30 |  |  |  |  | 0
32 | #236 | Closed | 2013-09-19 | 2013-09-29 | 1
33 | #239 | Resolved | 2013-09-19 | 2013-09-29 | 2
34 | #242 | Resolved | 2013-09-19 | 2013-09-29 | 2
35 | #245 | Active | 2013-09-19 | - | 1
36 | #258 | Resolved | 2013-09-29 | 2013-09-29 | 3
37 | #262 | Resolved | 2013-09-29 | 2013-09-29 | 3

## Geraldine
Geraldine
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1 | [5 empty] | 0 |  |  | 0
FYP Wk 1 |  |  |  | 29 Apr, Mon | 5 May, Sun |  |  |  |  | Labour Day (1 May, Wed)
FYP Wk 2 |  |  |  | 6 May, Mon | 12 May, Sun
FYP Wk 3 |  |  |  | 13 May, Mon | 19 May, Sun
FYP Wk 4 |  |  |  | 20 May, Mon | 26 May, Sun |  |  |  |  | Vesak Day (24 May, Fri)
FYP Wk 5 |  |  |  | 27 May, Mon | 2 Jun, Sun
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2 | [5 empty] | 12 |  |  | 12
FYP Wk 6 |  |  |  | 3 Jun, Mon | 9 Jun, Sun
FYP Wk 7 |  |  |  | 10 Jun, Mon | 16 Jun, Sun
Wiki | Design Structure | PM & BA | Geraldine | 14 Jun, Fri | 16 Jun, Sun | 6 | 14 Jun, Fri | 16 Jun, Sun | 6
FYP Wk 8 |  |  |  | 17 Jun, Mon | 23 Jun, Sun |  |  |  |  | Proposal (20 June, Fri)
Wiki | Update | PM & BA | Geraldine | 17 Jun, Mon | 20 Jun, Thu | 6 | 17 Jun, Mon | 20 Jun, Thu | 6
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3 | [5 empty] | 18 |  |  | 18
FYP Wk 9 |  |  |  | 24 Jun, Mon | 30 Jun, Sun
Schedule | Draft (v0.1) | PM & BA | Geraldine | 24 Jun, Mon | 30 Jun, Sun | 2 | 24 Jun, Mon | 30 Jun, Sun | 2
Wiki | Weekly Update | PM & BA | Geraldine | 24 Jun, Mon | 30 Jun, Sun | 8 | 24 Jun, Mon | 30 Jun, Sun | 8
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 30 Jun, Sun | 30 Jun, Sun | 1 | 30 Jun, Sun | 30 Jun, Sun | 1
FYP Wk 10 |  |  |  | 1 Jul, Mon | 7 Jul, Sun
Schedule | Draft (v0.2) | PM & BA | Geraldine | 7 Jul, Sun | 7 Jul, Sun | 2 | 7 Jul, Sun | 7 Jul, Sun | 2
Wiki | Weekly Update | PM & BA | Geraldine | 7 Jul, Sun | 7 Jul, Sun | 4 | 7 Jul, Sun | 7 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 7 Jul, Sun | 7 Jul, Sun | 1 | 7 Jul, Sun | 7 Jul, Sun | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4 | [5 empty] | 21 |  |  | 21
FYP Wk 11 |  |  |  | 8 Jul, Mon | 14 Jul, Sun
Schedule | Draft (v0.3) | PM & BA | Geraldine | 14 Jul, Sun | 14 Jul, Sun | 2 | 7 Jul, Sun | 7 Jul, Sun | 2
Wiki | Weekly Update | PM & BA | Geraldine | 14 Jul, Sun | 14 Jul, Sun | 4 | 7 Jul, Sun | 7 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 14 Jul, Sun | 14 Jul, Sun | 1 | 14 Jul, Sun | 14 Jul, Sun | 1
FYP Wk 12 |  |  |  | 15 Jul, Mon | 21 Jul, Sun
Schedule | Draft (v0.4) | PM & BA | Geraldine | 15 Jul, Mon | 21 Jul, Sun | 2 | 15 Jul, Mon | 21 Jul, Sun | 2
Wiki | Weekly Update | PM & BA | Geraldine | 15 Jul, Mon | 21 Jul, Sun | 4 | 15 Jul, Mon | 21 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 21 Jul, Sun | 21 Jul, Sun | 1 | 21 Jul, Sun | 21 Jul, Sun | 1
FYP Wk 13 |  |  |  | 22 Jul, Mon | 28 Jul, Sun
Schedule | Draft (v0.5) | PM & BA | Geraldine | 28 Jul, Sun | 28 Jul, Sun | 2 | 28 Jul, Sun | 28 Jul, Sun | 2
Wiki | Weekly Update | PM & BA | Geraldine | 28 Jul, Sun | 28 Jul, Sun | 4 | 28 Jul, Sun | 28 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 28 Jul, Sun | 28 Jul, Sun | 1 | 28 Jul, Sun | 28 Jul, Sun | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5 | [5 empty] | 57 |  |  | 73
FYP Wk 14 |  |  |  | 29 Jul, Mon | 4 Aug, Sun
Schedule | Update v1.0 | PM & BA | Geraldine | 28 Jul, Sun | 28 Jul, Sun | 4 | 28 Jul, Sun | 28 Jul, Sun | 4
Wiki | Weekly Update | PM & BA | Geraldine | 28 Jul, Sun | 28 Jul, Sun | 4 | 28 Jul, Sun | 28 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 28 Jul, Sun | 28 Jul, Sun | 1 | 28 Jul, Sun | 28 Jul, Sun | 1
FYP Wk 15 |  |  |  | 5 Aug, Mon | 11 Aug, Sun |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 5 Aug, Mon | 11 Aug, Sun | 6 | 5 Aug, Mon | 11 Aug, Sun | 16
Wiki | Weekly Update | PM & BA | Geraldine | 5 Aug, Mon | 11 Aug, Sun | 12 | 5 Aug, Mon | 14 Aug, Wed | 12
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 5 Aug, Mon | 11 Aug, Sun | 1 | 5 Aug, Mon | 14 Aug, Wed | 1
FYP Wk 16 |  |  |  | 12 Aug, Mon | 18 Aug, Sun |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 16
Wiki | Weekly Update | PM & BA | Geraldine | 12 Aug, Mon | 14 Aug, Wed | 12 | 12 Aug, Mon | 14 Aug, Wed | 12
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 12 Aug, Mon | 14 Aug, Wed | 1 | 12 Aug, Mon | 14 Aug, Wed | 1
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 17 Aug, Sat | 19 Aug, Mon | 10 | 17 Aug, Sat | 19 Aug, Mon | 6 | Spillover to next iteration
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6 | [5 empty] | 16 |  |  | 16 | (17 August - 1 September) - SMU Week 1 & 2
FYP Wk 17 / SMU Wk 1 |  |  |  | 19 Aug, Mon | 25 Aug, Sun |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 4 | 19 Aug, Mon | 19 Aug, Mon | 4 | Task from previous iteration, replanned
Wiki | Weekly Update | PM & BA | Geraldine | 19 Aug, Mon | 24 Aug, Sat | 4 | 19 Aug, Mon | 24 Aug, Sat | 5
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 19 Aug, Mon | 24 Aug, Sat | 1 | 19 Aug, Mon | 24 Aug, Sat | 1
FYP Wk 18 / SMU Wk 2 |  |  |  | 26 Aug, Mon | 1 Sep, Sun
Schedule | Revise | PM & BA | Jon, Geraldine | 26 Aug, Mon | 30 Aug, Fri | 4 | 26 Aug, Mon | 30 Aug, Fri | 2
Wiki | Weekly Update | PM & BA | Geraldine | 26 Aug, Mon | 30 Aug, Fri | 2 | 1 Sep, Sun | 1 Sep, Sun | 3
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 26 Aug, Mon | 30 Aug, Fri | 1 | 26 Aug, Mon | 30 Aug, Fri | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 | [5 empty] | 19 |  |  | 23
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
UT 1 | Writing | UI | Geraldine | 2013-09-05 | 2013-09-05 | 3 | 2013-09-05 | 2013-09-05 | 3
Lab |  | PM & BA | Geraldine, Jon, Juntao | 2013-09-04 | 2013-09-04 | 2 | 2013-09-04 | 2013-09-04 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-02 | 2013-09-07 | 1 | 2013-09-02 | 2013-09-07 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-02 | 2013-09-07 | 1 | 2013-09-02 | 2013-09-07 | 1
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
UT 1 | Writing | UI | Geraldine | 2013-09-12 | 2013-09-12 | 4 | 2013-09-12 | 2013-09-13 | 5
Meetings | Weekly Client, Supervisor Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-09 | 2013-09-14 | 4 | 2013-09-09 | 2013-09-14 | 4
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-09 | 2013-09-14 | 3 | 2013-09-12 | 2013-09-12 | 3
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-09 | 2013-09-14 | 1 | 2013-09-09 | 2013-09-14 | 1
Iteration 8 | [5 empty] | 32 |  |  | 32
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Market Research | Approach OCBC Branch Manager | PM & BA | Geraldine | 2013-09-18 | 2013-09-18 | 1 | 2013-09-18 | 2013-09-18 | 1
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-09-16 | 2013-09-21 | 2 | 2013-09-16 | 2013-09-21 | 2
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-16 | 2013-09-21 | 1 | 2013-09-16 | 2013-09-21 | 1
User Test 1 | Preparation for Test Scenarios | PM & BA | Geraldine | 2013-09-17 | 2013-09-17 | 2 | 2013-09-17 | 2013-09-17 | 2
User Test 1 |  |  | Whole Team | 2013-09-20 | 2013-09-20 | 2 | 2013-09-20 | 2013-09-20 | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
User Test 2 | Preparation for Test Scenarios | PM & BA | Geraldine | 2013-09-29 | 2013-09-29 | 2 | 2013-09-29 | 2013-09-29 | 2
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4
Wiki | Weekly Update | PM & BA | Geraldine | 2013-09-23 | 2013-09-29 | 3 | 2013-09-23 | 2013-09-29 | 3
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-23 | 2013-09-29 | 1 | 2013-09-23 | 2013-09-29 | 1

## Jonathan
Jonathan
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1 | [5 empty] | 3 |  |  | 4
FYP Wk 1 |  |  |  | 29 Apr, Mon | 5 May, Sun |  |  |  |  | Labour Day (1 May, Wed)
FYP Wk 2 |  |  |  | 6 May, Mon | 12 May, Sun
FYP Wk 3 |  |  |  | 13 May, Mon | 19 May, Sun
FYP Wk 4 |  |  |  | 20 May, Mon | 26 May, Sun |  |  |  |  | Vesak Day (24 May, Fri)
FYP Wk 5 |  |  |  | 27 May, Mon | 2 Jun, Sun
Project Scope | Conceptualize Use Cases | PM & BA | Jon, Kevin, Yao Guang | 2 Jun, Sun | 2 Jun, Sun | 3 | 2 Jun, Sun | 2 Jun, Sun | 4 | SIS Level 3 Benches
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2 | [5 empty] | 17 |  |  | 21
FYP Wk 6 |  |  |  | 3 Jun, Mon | 9 Jun, Sun
FYP Wk 7 |  |  |  | 10 Jun, Mon | 16 Jun, Sun
TIBCO Environment | Setup | Back End | Jon, Kevin, Yao Guang | 16 Jun, Sun | 16 Jun, Sun | 3 | 16 Jun, Sun | 16 Jun, Sun | 3 | Kevin & Yao Guang teach Jon
Proposal | Writing | PM & BA | Jon | 14 Jun, Fri | 16 Jun, Sun | 2 | 14 Jun, Fri | 16 Jun, Sun | 2
Project Scope | Define | PM & BA | Jon | 14 Jun, Fri | 16 Jun, Sun | 6 | 14 Jun, Fri | 16 Jun, Sun | 6
FYP Wk 8 |  |  |  | 17 Jun, Mon | 23 Jun, Sun |  |  |  |  | Proposal (20 June, Fri)
Proposal | Revision | PM & BA | Jon | 17 Jun, Mon | 20 Jun, Thu | 6 | 17 Jun, Mon | 20 Jun, Thu | 10
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3 | [5 empty] | 20 |  |  | 20
FYP Wk 9 |  |  |  | 24 Jun, Mon | 30 Jun, Sun
PM Tools | Experiment & Analyse | PM & BA | Jon | 24 Jun, Mon | 30 Jun, Sun | 6 | 24 Jun, Mon | 30 Jun, Sun | 6
Project Scope | Define | PM & BA | Jon | 24 Jun, Mon | 30 Jun, Sun | 8 | 24 Jun, Mon | 30 Jun, Sun | 8
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 30 Jun, Sun | 30 Jun, Sun | 1 | 30 Jun, Sun | 30 Jun, Sun | 1
FYP Wk 10 |  |  |  | 1 Jul, Mon | 7 Jul, Sun
Project Scope | Change Management | PM & BA | Jon | 7 Jul, Sun | 7 Jul, Sun | 4 | 7 Jul, Sun | 7 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 7 Jul, Sun | 7 Jul, Sun | 1 | 7 Jul, Sun | 7 Jul, Sun | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4 | [5 empty] | 17 |  |  | 15
FYP Wk 11 |  |  |  | 8 Jul, Mon | 14 Jul, Sun
Project Scope | Change Management | PM & BA | Jon | 8 Jul, Mon | 14 Jul, Sun | 6 | 8 Jul, Mon | 14 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 14 Jul, Sun | 14 Jul, Sun | 1 | 14 Jul, Sun | 14 Jul, Sun | 1
FYP Wk 12 |  |  |  | 15 Jul, Mon | 21 Jul, Sun
Project Scope | Change Management | PM & BA | Jon | 15 Jul, Mon | 21 Jul, Sun | 4 | 15 Jul, Mon | 21 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 21 Jul, Sun | 21 Jul, Sun | 1 | 21 Jul, Sun | 21 Jul, Sun | 1
FYP Wk 13 |  |  |  | 22 Jul, Mon | 28 Jul, Sun
Project Scope | Change Management | PM & BA | Jon | 28 Jul, Sun | 28 Jul, Sun | 4 | 28 Jul, Sun | 28 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 28 Jul, Sun | 28 Jul, Sun | 1 | 28 Jul, Sun | 28 Jul, Sun | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5 | [5 empty] | 61 |  |  | 75
FYP Wk 14 |  |  |  | 29 Jul, Mon | 4 Aug, Sun
Project Scope | Change Management | PM & BA | Jon | 28 Jul, Sun | 28 Jul, Sun | 4 | 28 Jul, Sun | 28 Jul, Sun | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 28 Jul, Sun | 28 Jul, Sun | 1 | 28 Jul, Sun | 28 Jul, Sun | 1
FYP Wk 15 |  |  |  | 5 Aug, Mon | 11 Aug, Sun |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Project Scope | Change Management | PM & BA | Jon | 5 Aug, Mon | 11 Aug, Sun | 2 | 5 Aug, Mon | 11 Aug, Sun | 2
Schedule | Overhaul v2.0 | PM & BA | Jon | 5 Aug, Mon | 11 Aug, Sun | 16 | 5 Aug, Mon | 14 Aug, Wed | 16
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 5 Aug, Mon | 11 Aug, Sun | 1 | 5 Aug, Mon | 14 Aug, Wed | 1
FYP Wk 16 |  |  |  | 12 Aug, Mon | 18 Aug, Sun |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 16
Project Scope | Change Management | PM & BA | Jon | 12 Aug, Mon | 14 Aug, Wed | 2 | 12 Aug, Mon | 14 Aug, Wed | 2
Schedule | Overhaul v2.0 | PM & BA | Jon | 12 Aug, Mon | 14 Aug, Wed | 16 | 12 Aug, Mon | 14 Aug, Wed | 24
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 12 Aug, Mon | 14 Aug, Wed | 1 | 12 Aug, Mon | 14 Aug, Wed | 1
Acceptance Presentation |  |  | Jon | 2013-08-16 | 2013-08-16 | 2 | 2013-08-16 | 2013-08-16 | 2
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 17 Aug, Sat | 19 Aug, Mon | 10 | 17 Aug, Sat | 19 Aug, Mon | 6 | Spillover to next iteration
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6 | [5 empty] | 28 |  |  | 30.5 | (17 August - 1 September) - SMU Week 1 & 2
FYP Wk 17 / SMU Wk 1 |  |  |  | 19 Aug, Mon | 25 Aug, Sun |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 4 | 19 Aug, Mon | 19 Aug, Mon | 4 | Task from previous iteration, replanned
Acceptance | Gather Back End Tutorial Requirements from Other Teams | Back End | Jon, Kevin, Yao Guang | 23 Aug, Fri | 23 Aug, Fri | 2 | 23 Aug, Fri | 23 Aug, Fri | 2
Back End Services | Writing Tutorial for Other FYP Teams | PM & BA | Jon | 22 Aug, Thu | 22 Aug, Thu | 4 | 22 Aug, Thu | 22 Aug, Thu | 8
Project Scope | Change Management | PM & BA | Jon, Kevin | 19 Aug, Mon | 24 Aug, Sat | 2 | 23 Aug, Fri | 23 Aug, Fri | 2
Schedule | Overhaul v2.0 | PM & BA | Jon | 19 Aug, Mon | 24 Aug, Sat | 4 | 19 Aug, Mon | 24 Aug, Sat | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 19 Aug, Mon | 24 Aug, Sat | 1 | 19 Aug, Mon | 24 Aug, Sat | 1
FYP Wk 18 / SMU Wk 2 |  |  |  | 26 Aug, Mon | 1 Sep, Sun
Tutorial |  | PM & BA | Jon | 27 Aug, Tue | 27 Aug, Tue | 4 | 27 Aug, Tue | 27 Aug, Tue | 4.5
Project Scope | Change Management | PM & BA | Jon | 26 Aug, Mon | 30 Aug, Fri | 2 | 26 Aug, Mon | 30 Aug, Fri | 2
Schedule | Revise | PM & BA | Jon, Geraldine | 26 Aug, Mon | 30 Aug, Fri | 4 | 26 Aug, Mon | 30 Aug, Fri | 2
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 26 Aug, Mon | 30 Aug, Fri | 1 | 26 Aug, Mon | 30 Aug, Fri | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 | [5 empty] | 27 |  |  | 22.5
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Test Plan | Writing | UI | Jon | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Lab |  | PM & BA | Geraldine, Jon, Juntao | 2013-09-04 | 2013-09-04 | 2 | 2013-09-04 | 2013-09-04 | 2
Lab | Writing | PM & BA | Jon | 2013-09-05 | 2013-09-05 | 3 | 2013-09-05 | 2013-09-05 | 3
Project Scope | Change Management | PM & BA | Jon, Kevin | 2013-09-02 | 2013-09-07 | 2 | 2013-09-02 | 2013-09-07 | 2
Schedule | Revise | PM & BA | Jon | 2013-09-02 | 2013-09-07 | 2 | 2013-09-02 | 2013-09-07 | 2
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-02 | 2013-09-07 | 1 | 2013-09-02 | 2013-09-07 | 1
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
UT 3 | Working with Client to ge Expert Users | UI | Jon | 2013-09-11 | 2013-09-11 | 1 | 2013-09-11 | 2013-09-11 | 1
Market Research | Comparing with Oracle Branch Teller | PM & BA | Jon, Kevin | 2013-09-13 | 2013-09-13 | 3 | 2013-09-13 | 2013-09-13 | 1 | Market Research Incomplete due to Inability to Access Oracle Software
Lab | Liasing with Other Groups | PM & BA | Jon | 2013-09-09 | 2013-09-09 | 2 | 2013-09-09 | 2013-09-09 | 2
Tutorial | Liasing with ESB Team | PM & BA | Jon | 2013-09-10 | 2013-09-10 | 1 | 2013-09-10 | 2013-09-10 | 1
Meetings | Weekly Client, Supervisor Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-09 | 2013-09-14 | 4 | 2013-09-09 | 2013-09-14 | 4
Project Scope | Change Management | PM & BA | Jon | 2013-09-09 | 2013-09-14 | 2 | 2013-09-09 | 2013-09-14 | 0.5
Schedule | Revise | PM & BA | Jon | 2013-09-09 | 2013-09-14 | 2 | 2013-09-09 | 2013-09-14 | 1
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-09 | 2013-09-14 | 1 | 2013-09-09 | 2013-09-14 | 1
Iteration 8 | [5 empty] | 32 |  |  | 38
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Lab | Working with Instructor Arul , Client & Other Teams | PM & BA | Jon | 2013-09-20 | 2013-09-20 | 2 | 2013-09-20 | 2013-09-20 | 4
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
Project Scope | Change Management | PM & BA | Jon | 2013-09-16 | 2013-09-21 | 2 | 2013-09-16 | 2013-09-21 | 2
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-09-16 | 2013-09-21 | 2 | 2013-09-16 | 2013-09-21 | 2
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-16 | 2013-09-21 | 1 | 2013-09-16 | 2013-09-21 | 1
User Test 1 |  |  | Whole Team | 2013-09-20 | 2013-09-20 | 2 | 2013-09-20 | 2013-09-20 | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Lab | Working with Instructor Arul & Client | PM & BA | Jon | 2013-09-20 | 2013-09-20 | 6 | 2013-09-20 | 2013-09-20 | 6
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4
Project Scope | Change Management | PM & BA | Jon | 2013-09-23 | 2013-09-29 | 2 | 2013-09-23 | 2013-09-29 | 6 | Increased 1 on 1 Meetings between BA & Client due to Sharp Increase in Bugs, Modifications and Changes
Schedule | Revise | PM & BA | Jon, Geraldine | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4
Stakeholder Management | Communications & Email etc. | PM & BA | Geraldine, Jon | 2013-09-23 | 2013-09-29 | 1 | 2013-09-23 | 2013-09-29 | 1

## Kevin
Kevin
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1 | [5 empty] | 28 |  |  | 29
FYP Wk 1 |  |  |  | 29 Apr, Mon | 5 May, Sun |  |  |  |  | Labour Day (1 May, Wed)
BRMS Drools Server | Install & Setup | Back End | Kevin | 3 May, Fri | 3 May, Fri | 2 | 3 May, Fri | 3 May, Fri | 2 | Surveying Business Rules Mgmt Systems (BRMS) Drools
FYP Wk 2 |  |  |  | 6 May, Mon | 12 May, Sun
BRMS Drools Server | Learn API | Back End | Kevin | 11 May, Sat | 11 May, Sat | 8 | 11 May, Sat | 11 May, Sat | 8 | Learning Drools Basic API
FYP Wk 3 |  |  |  | 13 May, Mon | 19 May, Sun
BRMS Drools Server | Learn Administrative Console | Back End | Kevin | 18 May, Sat | 18 May, Sat | 6 | 18 May, Sat | 18 May, Sat | 6
BRMS Drools Rules Repository Guvnor | Learn | Back End | Kevin | 19 May, Sun | 19 Feb, Tue | 6 | 19 May, Sun | 19 Feb, Tue | 6
FYP Wk 4 |  |  |  | 20 May, Mon | 26 May, Sun |  |  |  |  | Vesak Day (24 May, Fri)
TIBCO Environment | Install & Setup | Back End | Kevin, Yao Guang | 25 May, Sat | 25 May, Sat | 3 | 25 May, Sat | 25 May, Sat | 3
FYP Wk 5 |  |  |  | 27 May, Mon | 2 Jun, Sun
Project Scope | Conceptualize Use Cases | PM & BA | Jon, Kevin, Yao Guang | 2 Jun, Sun | 2 Jun, Sun | 3 | 2 Jun, Sun | 2 Jun, Sun | 4 | SIS Level 3 Benches
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2 | [5 empty] | 59 |  |  | 59
FYP Wk 6 |  |  |  | 3 Jun, Mon | 9 Jun, Sun
TIBCO Environment | Setup | Back End | Kevin, Yao Guang | 4 Jun, Tue | 4 Jun, Tue | 5 | 4 Jun, Tue | 4 Jun, Tue | 5
Party Customer Create | Develop Base Case | Back End | Kevin, Yao Guang | 5 Jun, Wed | 5 Jun, Wed | 5 | 5 Jun, Wed | 5 Jun, Wed | 5 | Develop Party_Customer_Create / Configure Tibco Environment (Service Mediation, Logging, EMS, existing DBs)
Party Customer Create | Develop Error Flows | Back End | Kevin, Yao Guang | 6 Jun, Thu | 6 Jun, Thu | 3 | 6 Jun, Thu | 6 Jun, Thu | 3 | Teamviewer
BRMS | Analyze | PM & BA | Kevin | 8 Jun, Sat | 8 Jun, Sat | 3 | 8 Jun, Sat | 8 Jun, Sat | 3 | Comparing different technologies recommended by Steven Nunez (Jess, Drools, FICO)
BRMS Drools Server & Rules Repository Guvnor | Setup | Back End | Kevin | 8 Jun, Sat | 8 Jun, Sat | 6 | 8 Jun, Sat | 8 Jun, Sat | 6 | Setup functional local deployment of Drools Server Endpoint and Guvnor REST Endpoints
BRMS Drools Server & Rules Repository Guvnor | Learn | Back End | Kevin | 8 Jun, Sat | 8 Jun, Sat | 3 | 8 Jun, Sat | 8 Jun, Sat | 3 | Testing Drools Endpoints to cater towards multiple Operations on same Endpoint (for different Rule sets and Domains)
FYP Wk 7 |  |  |  | 10 Jun, Mon | 16 Jun, Sun
Party Customer Update | Develop Base Case | Back End | Kevin | 10 Jun, Mon | 10 Jun, Mon | 4 | 10 Jun, Mon | 10 Jun, Mon | 4
Party Customer Update | Develop Error Flows | Back End | Kevin | 11 Jun, Tue | 11 Jun, Tue | 2 | 10 Jun, Mon | 10 Jun, Mon | 2
Account Create | Develop Base Case | Back End | Kevin, Yao Guang | 12 Jun, Wed | 12 Jun, Wed | 5 | 12 Jun, Wed | 12 Jun, Wed | 5 | Scope changed, add hours to Account Deposit Create (No. 5)
TIBCO Environment | Setup | Back End | Jon, Kevin, Yao Guang | 16 Jun, Sun | 16 Jun, Sun | 3 | 16 Jun, Sun | 16 Jun, Sun | 3 | Kevin & Yao Guang teach Jon
FYP Wk 8 |  |  |  | 17 Jun, Mon | 23 Jun, Sun |  |  |  |  | Proposal (20 June, Fri)
Account Update | Develop Base Case | Back End | Kevin | 17 Jun, Mon | 21 Jun, Fri | 12 | 17 Jun, Mon | 21 Jun, Fri | 12 | Scope changed, add hours to Account Deposit Update (No. 5)
BRMS Drools Server & Rules Repository Guvnor | Develop | Back End | Kevin | 22 Jun, Sat | 22 Jun, Sat | 4 | 22 Jun, Sat | 22 Jun, Sat | 4 | Develop Basic Framework for Drools Integration with Tibco Cross-Selling use case (Xml, parse, render interaction with drools REST endpoint), with test rule set
Next Best Offer | Develop Base Case | Back End | Kevin | 22 Jun, Sat | 22 Jun, Sat | 4 | 22 Jun, Sat | 22 Jun, Sat | 4
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3 | [5 empty] | 27 |  |  | 28
FYP Wk 9 |  |  |  | 24 Jun, Mon | 30 Jun, Sun
Account Deposit Create | Develop Base Case | Back End | Kevin, Yao Guang | 24 Jun, Mon | 24 Jun, Mon | 1 | 24 Jun, Mon | 24 Jun, Mon | 1
Account Deposit Read | Develop Base Case | Back End | Kevin, Yao Guang | 25 Jun, Tue | 25 Jun, Tue | 1 | 25 Jun, Tue | 25 Jun, Tue | 1
Account Deposit Update | Develop Base Case | Back End | Kevin, Yao Guang | 26 Jun, Wed | 26 Jun, Wed | 1 | 26 Jun, Wed | 26 Jun, Wed | 1
Account List Read | Develop Base Case | Back End | Kevin, Yao Guang | 27 Jun, Thu | 30 Jun, Sun | 2 | 27 Jun, Thu | 30 Jun, Sun | 2
FYP Wk 10 |  |  |  | 1 Jul, Mon | 7 Jul, Sun
Party Customer Create | Deploy to Server | Back End | Kevin, Yao Guang | 1 Jul, Mon | 2 Jul, Tue | 2 | 1 Jul, Mon | 1 Jul, Mon | 3
Party Customer Read | Deploy to Server | Back End | Kevin, Yao Guang | 2 Jul, Tue | 3 Jul, Wed | 2 | 2 Jul, Tue | 2 Jul, Tue | 2
Party Customer Update | Deploy to Server | Back End | Kevin, Yao Guang | 3 Jul, Wed | 4 Jul, Thu | 2 | 3 Jul, Wed | 3 Jul, Wed | 2
Account Deposit Create | Modify Base Case | Back End | Kevin, Yao Guang | 4 Jul, Thu | 4 Jul, Thu | 2 | 4 Jul, Thu | 4 Jul, Thu | 2 | Scope changed (No. 2)
Account Deposit Read | Modify Base Case | Back End | Kevin, Yao Guang | 5 Jul, Fri | 5 Jul, Fri | 2 | 5 Jul, Fri | 5 Jul, Fri | 2 | Scope changed (No. 2)
Account Deposit Update | Modify Base Case | Back End | Kevin, Yao Guang | 6 Jul, Sat | 6 Jul, Sat | 2 | 6 Jul, Sat | 6 Jul, Sat | 2 | Scope changed (No. 2)
Account List Read | Modify Base Case | Back End | Kevin, Yao Guang | 7 Jul, Sun | 7 Jul, Sun | 2 | 7 Jul, Sun | 7 Jul, Sun | 2 | Scope changed (No. 2)
Common Data Model - Transaction | Modify | Back End | Kevin, Yao Guang | 6 Jul, Sat | 6 Jul, Sat | 2 | 6 Jul, Sat | 6 Jul, Sat | 2 | Scope changed (No. 3)
Account Loan Create | Develop Base Case | Back End | Kevin, Yao Guang | 4 Jul, Thu | 5 Jul, Fri | 2 | 8 Jul, Mon | 8 Jul, Mon | 2
Account Loan Read | Develop Base Case | Back End | Kevin, Yao Guang | 5 Jul, Fri | 6 Jul, Sat | 2 | 8 Jul, Mon | 8 Jul, Mon | 2
Account Loan Update | Develop Base Case | Back End | Kevin, Yao Guang | 6 Jul, Sat | 6 Jul, Sat | 2 | 8 Jul, Mon | 8 Jul, Mon | 2
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4 | [5 empty] | 50 |  |  | 52
FYP Wk 11 |  |  |  | 8 Jul, Mon | 14 Jul, Sun
Party Customer Create | Develop Integration Code | Back End | Kevin, Yao Guang | 8 Jul, Mon | 11 Jul, Thu | 4 | 8 Jul, Mon | 11 Jul, Thu | 4
Party Customer Create | Modify Whole Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 12 Jul, Fri | 12 Jul, Fri | 3 | Scope changed (No. 4)
Party Customer Read | Modify Whole Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 12 Jul, Fri | 12 Jul, Fri | 1 | Scope changed (No. 4)
Party Customer Update | Modify Whole Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 12 Jul, Fri | 12 Jul, Fri | 1 | Scope changed (No. 4)
Account Deposit Create | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 13 Jul, Sat | 13 Jul, Sat | 1 | Scope changed (No. 4)
Account Deposit Read | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 13 Jul, Sat | 13 Jul, Sat | 1 | Scope changed (No. 4)
Account Deposit Update | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 13 Jul, Sat | 13 Jul, Sat | 1 | Scope changed (No. 4)
Account Loan Create | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account Loan Read | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account Loan Update | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account List Read | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account Deposit Create | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 13 Jul, Sat | 13 Jul, Sat | 2
Account Deposit Read | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 13 Jul, Sat | 13 Jul, Sat | 2
Account Deposit Update | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 13 Jul, Sat | 13 Jul, Sat | 2
Account List Read | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
Account Loan Create | Develop Error Flows | Back End | Kevin, Yao Guang | 14 Jul, Sun | 14 Jul, Sun | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
Account Loan Read | Develop Error Flows | Back End | Kevin, Yao Guang | 14 Jul, Sun | 14 Jul, Sun | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
Account Loan Update | Develop Error Flows | Back End | Kevin, Yao Guang | 14 Jul, Sun | 14 Jul, Sun | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
FYP Wk 12 |  |  |  | 15 Jul, Mon | 21 Jul, Sun
Account Deposit Create | Deploy to Server | Back End | Kevin, Yao Guang | 15 Jul, Mon | 15 Jul, Mon | 1 | 15 Jul, Mon | 15 Jul, Mon | 1
Account Deposit Read | Deploy to Server | Back End | Kevin, Yao Guang | 15 Jul, Mon | 16 Jul, Tue | 1 | 15 Jul, Mon | 16 Jul, Tue | 1
Account Deposit Update | Deploy to Server | Back End | Kevin, Yao Guang | 16 Jul, Tue | 16 Jul, Tue | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Account List Read | Deploy to Server | Back End | Kevin, Yao Guang | 16 Jul, Tue | 17 Jul, Wed | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Account Loan Create | Deploy to Server | Back End | Kevin, Yao Guang | 18 Jul, Thu | 18 Jul, Thu | 1 | 18 Jul, Thu | 18 Jul, Thu | 1
Account Loan Read | Deploy to Server | Back End | Kevin, Yao Guang | 18 Jul, Thu | 18 Jul, Thu | 1 | 18 Jul, Thu | 18 Jul, Thu | 1
Account Loan Update | Deploy to Server | Back End | Kevin, Yao Guang | 19 Jul, Fri | 19 Jul, Fri | 1 | 19 Jul, Fri | 19 Jul, Fri | 1
Party Customer Create | Modify Integration Code | Back End | Kevin, Yao Guang | 16 Jul, Tue | 19 Jul, Fri | 2 | 16 Jul, Tue | 19 Jul, Fri | 2 | Scope changed (No. 4)
Party Customer Read | Develop Integration Code | Back End | Kevin, Yao Guang | 17 Jul, Wed | 21 Jul, Sun | 3 | 17 Jul, Wed | 21 Jul, Sun | 3
Party Customer Update | Develop Integration Code | Back End | Kevin, Yao Guang | 19 Jul, Fri | 21 Jul, Sun | 3 | 19 Jul, Fri | 21 Jul, Sun | 3
FYP Wk 13 |  |  |  | 22 Jul, Mon | 28 Jul, Sun
Account Deposit Create | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account Deposit Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account Deposit Update | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account List Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account Loan Create | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 27 Jul, Sat | 27 Jul, Sat | 1 | 27 Jul, Sat | 27 Jul, Sat | 1 | Scope changed (No. 5)
Account Loan Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 27 Jul, Sat | 27 Jul, Sat | 1 | 27 Jul, Sat | 27 Jul, Sat | 1 | Scope changed (No. 5)
Account Loan Update | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 27 Jul, Sat | 27 Jul, Sat | 1 | 27 Jul, Sat | 27 Jul, Sat | 1 | Scope changed (No. 5)
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5 | [5 empty] | 54 |  |  | 78.5
FYP Wk 14 |  |  |  | 29 Jul, Mon | 4 Aug, Sun
Account Deposit Create | Develop Integration Code | Back End | Kevin, Yao Guang | 1 Aug, Thu | 1 Aug, Thu | 2 | 1 Aug, Thu | 1 Aug, Thu | 3
Account Deposit Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2 Aug, Fri | 2 Aug, Fri | 2 | 2 Aug, Fri | 2 Aug, Fri | 3
Account Deposit Update | Develop Integration Code | Back End | Kevin, Yao Guang | 2 Aug, Fri | 2 Aug, Fri | 2 | 2 Aug, Fri | 2 Aug, Fri | 3
Account List Read | Develop Integration Code | Back End | Kevin, Yao Guang | 3 Aug, Sat | 7 Feb, Tue | 2 | 3 Aug, Sat | 7 Feb, Tue | 3
Account Loan Create | Develop Integration Code | Back End | Kevin, Yao Guang | 3 Aug, Sat | 3 Aug, Sat | 2 | 3 Aug, Sat | 3 Aug, Sat | 3
Account Loan Read | Develop Integration Code | Back End | Kevin, Yao Guang | 4 Aug, Sun | 4 Aug, Sun | 2 | 4 Aug, Sun | 4 Aug, Sun | 3
Account Loan Update | Develop Integration Code | Back End | Kevin, Yao Guang | 4 Aug, Sun | 4 Aug, Sun | 2 | 4 Aug, Sun | 4 Aug, Sun | 3
FYP Wk 15 |  |  |  | 5 Aug, Mon | 11 Aug, Sun |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Transaction Deposit | Develop Base Case | Back End | Kevin | 5 Aug, Mon | 5 Aug, Mon | 2 | 5 Aug, Mon | 5 Aug, Mon | 2
Transaction Withdrawal | Develop Base Case | Back End | Kevin | 5 Aug, Mon | 6 Aug, Tue | 2 | 5 Aug, Mon | 5 Aug, Mon | 2
Transaction History Read | Develop Base Case | Back End | Kevin, Yao Guang | 6 Aug, Tue | 6 Aug, Tue | 2 | 6 Aug, Tue | 6 Aug, Tue | 2
BRMS, Next Best Offer | Hand Over | PM & BA | Geraldine, Jon, Kevin | 6 Aug, Tue | 6 Aug, Tue | 2 | 6 Aug, Tue | 6 Aug, Tue | 2 | Scope changed (No. 7 & 8); Met FYP Team Creagend
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 5 Aug, Mon | 11 Aug, Sun | 6 | 5 Aug, Mon | 11 Aug, Sun | 16
FYP Wk 16 |  |  |  | 12 Aug, Mon | 18 Aug, Sun |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 16
Transaction Deposit | Develop Error Flows | Back End | Kevin | 12 Aug, Mon | 12 Aug, Mon | 1 | 12 Aug, Mon | 12 Aug, Mon | 1
Transaction Withdrawal | Develop Error Flows | Back End | Kevin | 12 Aug, Mon | 12 Aug, Mon | 1 | 13 Aug, Tue | 13 Aug, Tue | 1
Transaction History Read | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Aug, Tue | 13 Aug, Tue | 1 | 13 Aug, Tue | 13 Aug, Tue | 1
Credit Approval | Develop Spreadsheet | Back End | Kevin | 13 Aug, Tue | 13 Aug, Tue | 1 | 13 Aug, Tue | 13 Aug, Tue | 1.5 | Scope changed (No. 15)
Account Deposit Create | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 1 | Scope changed (No. 13, 17)
Account Deposit Update | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 2 | Scope changed (No. 13, 17)
Account Loan Create | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 1 | Scope changed (No. 12 & 17)
Account Loan Read | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 1 | Scope changed (No. 12)
Account Loan Update | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 2 | Scope changed (No. 17)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 17 Aug, Sat | 19 Aug, Mon | 10 | 17 Aug, Sat | 19 Aug, Mon | 6 | Spillover to next iteration
MDM Customer Type Read | Taking Over | Back End | Kevin | 17 Aug, Sat | 17 Aug, Sat | 0.5 |  |  |  | Scope changed (No. 13) | Alan didn't deliver on time
MDM Product Type Read | Taking Over | Back End | Kevin | 17 Aug, Sat | 17 Aug, Sat | 0.5 |  |  |  | Scope changed (No. 13) | Alan didn't deliver on time
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6 | [5 empty] | 42 |  |  | 33.5 | (17 August - 1 September) - SMU Week 1 & 2
FYP Wk 17 / SMU Wk 1 |  |  |  | 19 Aug, Mon | 25 Aug, Sun |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 4 | 19 Aug, Mon | 19 Aug, Mon | 4 | Task from previous iteration, replanned
MDM Customer Type Read | Develop Integration Code | Back End | Kevin | 20 Aug, Tue | 20 Aug, Tue | 2 | 20 Aug, Tue | 20 Aug, Tue | 2
MDM Product Type Read | Develop Integration Code | Back End | Kevin | 20 Aug, Tue | 20 Aug, Tue | 2 | 20 Aug, Tue | 20 Aug, Tue | 2.5
Transaction Deposit | Modify Whole Case | Back End | Kevin, Yao Guang | 20 Aug, Tue | 20 Aug, Tue | 0.5 | 20 Aug, Tue | 20 Aug, Tue | 0.5 | Scope changed (No. 6)
Transaction Withdrawal | Modify Whole Case | Back End | Kevin, Yao Guang | 20 Aug, Tue | 20 Aug, Tue | 0.5 | 20 Aug, Tue | 20 Aug, Tue | 0.5 | Scope changed (No. 6)
Transaction SMS Notification | Taking Over | Back End | Kevin | 20 Aug, Tue | 20 Aug, Tue | 0.5 | 20 Aug, Tue | 20 Aug, Tue | 1
Transaction Deposit | Deploy to Server | Back End | Kevin, Yao Guang | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction Withdrawal | Deploy to Server | Back End | Kevin, Yao Guang | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction History Read | Deploy to Server | Back End | Kevin, Yao Guang | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction Deposit | Develop Integration Code | Back End | Kevin | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction Withdrawal | Develop Integration Code | Back End | Kevin | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction History Read | Develop Integration Code | Back End | Kevin | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Login Use Case | Debugging | UI | Juntao, Kevin | 24 Aug, Sat | 24 Aug, Sat | 2 | 26 Aug, Mon | 24 Aug, Sat | 0
Party Create Use Case | Debugging | UI | Juntao, Kevin | 24 Aug, Sat | 24 Aug, Sat | 2 | 24 Aug, Sat | 24 Aug, Sat | 0
Party Read & Update | Debugging | UI | Juntao, Kevin | 24 Aug, Sat | 24 Aug, Sat | 2 | 24 Aug, Sat | 24 Aug, Sat | 0.5
Acceptance | Gather Back End Tutorial Requirements from Other Teams | Back End | Jon, Kevin, Yao Guang | 23 Aug, Fri | 23 Aug, Fri | 2 | 23 Aug, Fri | 23 Aug, Fri | 2
FYP Wk 18 / SMU Wk 2 |  |  |  | 26 Aug, Mon | 1 Sep, Sun
Account Deposit Create | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 1
Account Deposit Update | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 0.5
Account Loan Create | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 1
Account Loan Read | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 0.5
Account Loan Update | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 1
Product Parameters Read | Taking Over | Back End | Kevin | 30 Aug, Fri | 30 Aug, Fri | 0.5 | 29 Aug, Thu | 29 Aug, Thu | 0.5 | Scope changed (No. 14)
Product Parameters Read | Develop Integration Code | Back End | Kevin, Yao Guang | 30 Aug, Fri | 30 Aug, Fri | 1 | 29 Aug, Thu | 29 Aug, Thu | 1
Transaction SMS Notification | Integrate | Back End | Kevin | 31 Aug, Sat | 31 Aug, Sat | 2 | 31 Aug, Sat | 31 Aug, Sat | 2
Payment Credit Transfer | Develop Base Case | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 2 | 31 Aug, Sat | 31 Aug, Sat | 2
Payment Loan Repayment Full | Develop Base Case | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 2 | 1 Sep, Sun | 1 Sep, Sun | 2
Payment Loan Repayment Partial | Develop Base Case | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 4 | 1 Sep, Sun | 1 Sep, Sun | 3
Payment Credit Transfer | Develop Error Flows | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 1 | 1 Sep, Sun | 1 Sep, Sun | 1
Payment Loan Repayment Full | Develop Error Flows | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 1 | 1 Sep, Sun | 1 Sep, Sun | 2
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 | [5 empty] | 32 |  |  | 31.5
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Payment Loan Repayment Partial | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 2
Payment Credit Transfer | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Full | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Partial | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Credit Transfer | Deploy to Server | Back End | Kevin | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Full | Deploy to Server | Back End | Kevin, Yao Guang | 2013-09-05 | 2013-09-05 | 1 | 2013-09-06 | 2013-09-06 | 1
Payment Loan Repayment Partial | Deploy to Server | Back End | Kevin, Yao Guang | 2013-09-05 | 2013-09-05 | 1 | 2013-09-06 | 2013-09-06 | 1
Direct Debit Authorization Service | Taking Over | Back End | Kevin | 2013-09-01 | 2013-09-06 | 0.5 | 2013-09-06 | 2013-09-06 | 0.5
Direct Debit Authorization | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-06 | 2013-09-06 | 1 | 2013-09-06 | 2013-09-06 | 1
Account Deposit Create Use Case - Product Parameters Read | Develop Basic UI | UI | James, Kevin | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Read & Update Use Case - Product Parameters Read | Develop Basic UI | UI | James, Kevin | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Project Scope | Change Management | PM & BA | Jon, Kevin | 2013-09-02 | 2013-09-07 | 2 | 2013-09-02 | 2013-09-07 | 2
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-10 | 2013-09-11 | 10 | 2013-09-10 | 2013-09-11 | 10.5
MDM Billing Organization Read List Service | Taking Over | Back End | Kevin | 2013-09-01 | 2013-09-01 | 0.5 | 2013-09-10 | 2013-09-10 | 0.5
MDM Billing Organization Read List | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-13 | 2013-09-13 | 1 | 2013-09-12 | 2013-09-12 | 1
Direct Debit Authorization | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-12 | 2013-09-12 | 3 | 2013-09-12 | 2013-09-12 | 3
Technology Research | Normalised vs Denormalized Database Comparision | Back End | Kevin | 2013-09-10 | 2013-09-10 | 2 | 2013-09-10 | 2013-09-10 | 2
Debugging | Product Parameters Read |  | Kevin, James | 2013-09-13 | 2013-09-13 | 1 | 2013-09-13 | 2013-09-13 | 1
Market Research | Comparing with Oracle Branch Teller | PM & BA | Jon, Kevin | 2013-09-13 | 2013-09-13 | 3 | 2013-09-13 | 2013-09-13 | 1 | Market Research Incomplete due to Inability to Access Oracle Software
Iteration 8 | [5 empty] | 48 |  |  | 51.5
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Transaction SMS Notification | Assist Client | Back End | Kevin | 2013-09-17 | 2013-09-17 | 1 | 2013-09-17 | 2013-09-17 | 1
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-19 | 2013-09-22 | 9 | 2013-09-19 | 2013-09-22 | 12
Party Login Create | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-21 | 2013-09-21 | 2 | 2013-09-21 | 2013-09-21 | 2
Party Login Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-21 | 2013-09-21 | 1.5 | 2013-09-21 | 2013-09-21 | 1.5
Debugging & Modifications | Modified MDM Billing Organization Read List | Back End | Kevin | 2013-09-22 | 2013-09-22 | 2 | 2013-09-22 | 2013-09-22 | 2
Credit Approval | Develop Base Case | Back End | Kevin | 2013-09-22 | 2013-09-22 | 6 | 2013-09-22 | 2013-09-22 | 6.5
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
User Test 1 |  |  |  | 2013-09-20 | 2013-09-20 | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Debugging & Modifications | Assist Client with Taking Over | Back End | Kevin | 2013-09-23 | 2013-09-23 | 0.5 | 2013-09-23 | 2013-09-23 | 0.5
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-23 | 2013-09-26 | 6 | 2013-09-23 | 2013-09-26 | 8
Wiki | Technical writeup for account & party services for wiki | PM & BA | Kevin | 2013-09-23 | 2013-09-23 | 3 | 2013-09-23 | 2013-09-23 | 3
Debugging & Modifications | Modified SMU Core Services for Lab Walkthrough Standardization | Back End | Kevin, Yao Guang | 2013-09-27 | 2013-09-27 | 4 | 2013-09-27 | 2013-09-27 | 4
Debugging & Modifications | Debug Transaction_History_Read (2 bugs) | Back End | Kevin | 2013-09-29 | 2013-09-29 | 1 | 2013-09-29 | 2013-09-29 | 1
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4

## Yao Guang
Yao Guang
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1 | [5 empty] | 15 |  |  | 16
FYP Wk 1 |  |  |  | 29 Apr, Mon | 5 May, Sun |  |  |  |  | Labour Day (1 May, Wed)
SharePoint | Install & Learn | Back End | Yao Guang | 5 May, Sun | 5 May, Sun | 6 | 5 May, Sun | 5 May, Sun | 6 | Scope dropped (No. 1)
FYP Wk 2 |  |  |  | 6 May, Mon | 12 May, Sun
FYP Wk 3 |  |  |  | 13 May, Mon | 19 May, Sun
FYP Wk 4 |  |  |  | 20 May, Mon | 26 May, Sun |  |  |  |  | Vesak Day (24 May, Fri)
SharePoint | Learn Http Basic Authentication | Back End | Yao Guang | 22 May, Wed | 22 May, Wed | 3 | 22 May, Wed | 22 May, Wed | 3 | Scope dropped (No. 1)
TIBCO Environment | Install & Setup | Back End | Kevin, Yao Guang | 25 May, Sat | 25 May, Sat | 3 | 25 May, Sat | 25 May, Sat | 3
FYP Wk 5 |  |  |  | 27 May, Mon | 2 Jun, Sun
Project Scope | Conceptualize Use Cases | PM & BA | Jon, Kevin, Yao Guang | 2 Jun, Sun | 2 Jun, Sun | 3 | 2 Jun, Sun | 2 Jun, Sun | 4 | SIS Level 3 Benches
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2 | [5 empty] | 35 |  |  | 35
FYP Wk 6 |  |  |  | 3 Jun, Mon | 9 Jun, Sun
TIBCO Environment | Setup | Back End | Kevin, Yao Guang | 4 Jun, Tue | 4 Jun, Tue | 5 | 4 Jun, Tue | 4 Jun, Tue | 5
Party Customer Create | Develop Base Case | Back End | Kevin, Yao Guang | 5 Jun, Wed | 5 Jun, Wed | 5 | 5 Jun, Wed | 5 Jun, Wed | 5 | Develop Party_Customer_Create / Configure Tibco Environment (Service Mediation, Logging, EMS, existing DBs)
Party Customer Create | Develop Error Flows | Back End | Kevin, Yao Guang | 6 Jun, Thu | 6 Jun, Thu | 3 | 6 Jun, Thu | 6 Jun, Thu | 3 | Teamviewer
FYP Wk 7 |  |  |  | 10 Jun, Mon | 16 Jun, Sun
Party Customer Read | Develop Base Case | Back End | Yao Guang | 10 Jun, Mon | 10 Jun, Mon | 4 | 10 Jun, Mon | 10 Jun, Mon | 4 | Teamviewer
Party Customer Read | Develop Error Flows | Back End | Yao Guang | 11 Jun, Tue | 11 Jun, Tue | 2 | 10 Jun, Mon | 10 Jun, Mon | 2
Account Create | Develop Base Case | Back End | Kevin, Yao Guang | 12 Jun, Wed | 12 Jun, Wed | 5 | 12 Jun, Wed | 12 Jun, Wed | 5 | Scope changed, add hours to Account Deposit Create (No. 5)
TIBCO Environment | Setup | Back End | Jon, Kevin, Yao Guang | 16 Jun, Sun | 16 Jun, Sun | 3 | 16 Jun, Sun | 16 Jun, Sun | 3 | Kevin & Yao Guang teach Jon
FYP Wk 8 |  |  |  | 17 Jun, Mon | 23 Jun, Sun |  |  |  |  | Proposal (20 June, Fri)
Account Create | Develop Base Case | Back End | Yao Guang | 17 Jun, Mon | 17 Jun, Mon | 4 | 17 Jun, Mon | 17 Jun, Mon | 4 | Scope changed, add hours to Account Deposit Create (No. 5)
Account Read | Develop Base Case | Back End | Yao Guang | 19 Jun, Wed | 19 Jun, Wed | 4 | 19 Jun, Wed | 19 Jun, Wed | 4 | Scope changed, add hours to Account Deposit Read (No. 5)
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3 | [5 empty] | 27 |  |  | 28
FYP Wk 9 |  |  |  | 24 Jun, Mon | 30 Jun, Sun
Account Deposit Create | Develop Base Case | Back End | Kevin, Yao Guang | 24 Jun, Mon | 24 Jun, Mon | 1 | 24 Jun, Mon | 24 Jun, Mon | 1
Account Deposit Read | Develop Base Case | Back End | Kevin, Yao Guang | 25 Jun, Tue | 25 Jun, Tue | 1 | 25 Jun, Tue | 25 Jun, Tue | 1
Account Deposit Update | Develop Base Case | Back End | Kevin, Yao Guang | 26 Jun, Wed | 26 Jun, Wed | 1 | 26 Jun, Wed | 26 Jun, Wed | 1
Account List Read | Develop Base Case | Back End | Kevin, Yao Guang | 27 Jun, Thu | 30 Jun, Sun | 2 | 27 Jun, Thu | 30 Jun, Sun | 2
FYP Wk 10 |  |  |  | 1 Jul, Mon | 7 Jul, Sun
Party Customer Create | Deploy to Server | Back End | Kevin, Yao Guang | 1 Jul, Mon | 2 Jul, Tue | 2 | 1 Jul, Mon | 1 Jul, Mon | 3
Party Customer Read | Deploy to Server | Back End | Kevin, Yao Guang | 2 Jul, Tue | 3 Jul, Wed | 2 | 2 Jul, Tue | 2 Jul, Tue | 2
Party Customer Update | Deploy to Server | Back End | Kevin, Yao Guang | 3 Jul, Wed | 4 Jul, Thu | 2 | 3 Jul, Wed | 3 Jul, Wed | 2
Account Deposit Create | Modify Base Case | Back End | Kevin, Yao Guang | 4 Jul, Thu | 4 Jul, Thu | 2 | 4 Jul, Thu | 4 Jul, Thu | 2 | Scope changed (No. 2)
Account Deposit Read | Modify Base Case | Back End | Kevin, Yao Guang | 5 Jul, Fri | 5 Jul, Fri | 2 | 5 Jul, Fri | 5 Jul, Fri | 2 | Scope changed (No. 2)
Account Deposit Update | Modify Base Case | Back End | Kevin, Yao Guang | 6 Jul, Sat | 6 Jul, Sat | 2 | 6 Jul, Sat | 6 Jul, Sat | 2 | Scope changed (No. 2)
Account List Read | Modify Base Case | Back End | Kevin, Yao Guang | 7 Jul, Sun | 7 Jul, Sun | 2 | 7 Jul, Sun | 7 Jul, Sun | 2 | Scope changed (No. 2)
Common Data Model - Transaction | Modify | Back End | Kevin, Yao Guang | 6 Jul, Sat | 6 Jul, Sat | 2 | 6 Jul, Sat | 6 Jul, Sat | 2 | Scope changed (No. 3)
Account Loan Create | Develop Base Case | Back End | Kevin, Yao Guang | 4 Jul, Thu | 5 Jul, Fri | 2 | 8 Jul, Mon | 8 Jul, Mon | 2
Account Loan Read | Develop Base Case | Back End | Kevin, Yao Guang | 5 Jul, Fri | 6 Jul, Sat | 2 | 8 Jul, Mon | 8 Jul, Mon | 2
Account Loan Update | Develop Base Case | Back End | Kevin, Yao Guang | 6 Jul, Sat | 6 Jul, Sat | 2 | 8 Jul, Mon | 8 Jul, Mon | 2
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4 | [5 empty] | 50 |  |  | 52
FYP Wk 11 |  |  |  | 8 Jul, Mon | 14 Jul, Sun
Party Customer Create | Develop Integration Code | Back End | Kevin, Yao Guang | 8 Jul, Mon | 11 Jul, Thu | 4 | 8 Jul, Mon | 11 Jul, Thu | 4
Party Customer Create | Modify Whole Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 12 Jul, Fri | 12 Jul, Fri | 3 | Scope changed (No. 4)
Party Customer Read | Modify Whole Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 12 Jul, Fri | 12 Jul, Fri | 1 | Scope changed (No. 4)
Party Customer Update | Modify Whole Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 12 Jul, Fri | 12 Jul, Fri | 1 | Scope changed (No. 4)
Account Deposit Create | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 13 Jul, Sat | 13 Jul, Sat | 1 | Scope changed (No. 4)
Account Deposit Read | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 13 Jul, Sat | 13 Jul, Sat | 1 | Scope changed (No. 4)
Account Deposit Update | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 13 Jul, Sat | 13 Jul, Sat | 1 | Scope changed (No. 4)
Account Loan Create | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account Loan Read | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account Loan Update | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account List Read | Modify Base Case | Back End | Kevin, Yao Guang | 12 Jul, Fri | 12 Jul, Fri | 1 | 14 Jul, Sun | 14 Jul, Sun | 1 | Scope changed (No. 4)
Account Deposit Create | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 13 Jul, Sat | 13 Jul, Sat | 2
Account Deposit Read | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 13 Jul, Sat | 13 Jul, Sat | 2
Account Deposit Update | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 13 Jul, Sat | 13 Jul, Sat | 2
Account List Read | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Jul, Sat | 13 Jul, Sat | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
Account Loan Create | Develop Error Flows | Back End | Kevin, Yao Guang | 14 Jul, Sun | 14 Jul, Sun | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
Account Loan Read | Develop Error Flows | Back End | Kevin, Yao Guang | 14 Jul, Sun | 14 Jul, Sun | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
Account Loan Update | Develop Error Flows | Back End | Kevin, Yao Guang | 14 Jul, Sun | 14 Jul, Sun | 2 | 14 Jul, Sun | 14 Jul, Sun | 2
FYP Wk 12 |  |  |  | 15 Jul, Mon | 21 Jul, Sun
Account Deposit Create | Deploy to Server | Back End | Kevin, Yao Guang | 15 Jul, Mon | 15 Jul, Mon | 1 | 15 Jul, Mon | 15 Jul, Mon | 1
Account Deposit Read | Deploy to Server | Back End | Kevin, Yao Guang | 15 Jul, Mon | 16 Jul, Tue | 1 | 15 Jul, Mon | 16 Jul, Tue | 1
Account Deposit Update | Deploy to Server | Back End | Kevin, Yao Guang | 16 Jul, Tue | 16 Jul, Tue | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Account List Read | Deploy to Server | Back End | Kevin, Yao Guang | 16 Jul, Tue | 17 Jul, Wed | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Account Loan Create | Deploy to Server | Back End | Kevin, Yao Guang | 18 Jul, Thu | 18 Jul, Thu | 1 | 18 Jul, Thu | 18 Jul, Thu | 1
Account Loan Read | Deploy to Server | Back End | Kevin, Yao Guang | 18 Jul, Thu | 18 Jul, Thu | 1 | 18 Jul, Thu | 18 Jul, Thu | 1
Account Loan Update | Deploy to Server | Back End | Kevin, Yao Guang | 19 Jul, Fri | 19 Jul, Fri | 1 | 19 Jul, Fri | 19 Jul, Fri | 1
Party Customer Create | Modify Integration Code | Back End | Kevin, Yao Guang | 16 Jul, Tue | 19 Jul, Fri | 2 | 16 Jul, Tue | 19 Jul, Fri | 2 | Scope changed (No. 4)
Party Customer Read | Develop Integration Code | Back End | Kevin, Yao Guang | 17 Jul, Wed | 21 Jul, Sun | 3 | 17 Jul, Wed | 21 Jul, Sun | 3
Party Customer Update | Develop Integration Code | Back End | Kevin, Yao Guang | 19 Jul, Fri | 21 Jul, Sun | 3 | 19 Jul, Fri | 21 Jul, Sun | 3
FYP Wk 13 |  |  |  | 22 Jul, Mon | 28 Jul, Sun
Account Deposit Create | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account Deposit Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account Deposit Update | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account List Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 22 Jul, Mon | 22 Jul, Mon | 1 | 22 Jul, Mon | 22 Jul, Mon | 1 | Scope changed (No. 5)
Account Loan Create | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 27 Jul, Sat | 27 Jul, Sat | 1 | 27 Jul, Sat | 27 Jul, Sat | 1 | Scope changed (No. 5)
Account Loan Read | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 27 Jul, Sat | 27 Jul, Sat | 1 | 27 Jul, Sat | 27 Jul, Sat | 1 | Scope changed (No. 5)
Account Loan Update | Modify & Redeploy to Server | Back End | Kevin, Yao Guang | 27 Jul, Sat | 27 Jul, Sat | 1 | 27 Jul, Sat | 27 Jul, Sat | 1 | Scope changed (No. 5)
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5 | [5 empty] | 56 |  |  | 99
FYP Wk 14 |  |  |  | 29 Jul, Mon | 4 Aug, Sun
Account Deposit Create | Develop Integration Code | Back End | Kevin, Yao Guang | 1 Aug, Thu | 1 Aug, Thu | 2 | 1 Aug, Thu | 1 Aug, Thu | 3
Account Deposit Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2 Aug, Fri | 2 Aug, Fri | 2 | 2 Aug, Fri | 2 Aug, Fri | 3
Account Deposit Update | Develop Integration Code | Back End | Kevin, Yao Guang | 2 Aug, Fri | 2 Aug, Fri | 2 | 2 Aug, Fri | 2 Aug, Fri | 3
Account List Read | Develop Integration Code | Back End | Kevin, Yao Guang | 3 Aug, Sat | 7 Feb, Tue | 2 | 3 Aug, Sat | 7 Feb, Tue | 3
Account Loan Create | Develop Integration Code | Back End | Kevin, Yao Guang | 3 Aug, Sat | 3 Aug, Sat | 2 | 3 Aug, Sat | 3 Aug, Sat | 3
Account Loan Read | Develop Integration Code | Back End | Kevin, Yao Guang | 4 Aug, Sun | 4 Aug, Sun | 2 | 4 Aug, Sun | 4 Aug, Sun | 3
Account Loan Update | Develop Integration Code | Back End | Kevin, Yao Guang | 4 Aug, Sun | 4 Aug, Sun | 2 | 4 Aug, Sun | 4 Aug, Sun | 3
FYP Wk 15 |  |  |  | 5 Aug, Mon | 11 Aug, Sun |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Transaction History Read | Develop Base Case | Back End | Kevin, Yao Guang | 6 Aug, Tue | 6 Aug, Tue | 2 | 6 Aug, Tue | 6 Aug, Tue | 2
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 6 Aug, Tue | 14 Aug, Wed | 6 | 6 Aug, Tue | 14 Aug, Wed | 20
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 5 Aug, Mon | 11 Aug, Sun | 6 | 5 Aug, Mon | 11 Aug, Sun | 16
FYP Wk 16 |  |  |  | 12 Aug, Mon | 18 Aug, Sun |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 10
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 16
Transaction History Read | Develop Error Flows | Back End | Kevin, Yao Guang | 13 Aug, Tue | 13 Aug, Tue | 1 | 13 Aug, Tue | 13 Aug, Tue | 1
Account Deposit Create | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 1 | Scope changed (No. 13, 17)
Account Deposit Update | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 2 | Scope changed (No. 13, 17)
Account Loan Create | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 1 | Scope changed (No. 12 & 17)
Account Loan Read | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 1 | Scope changed (No. 12)
Account Loan Update | Modify Whole Case | Back End | Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 1 | 18 Aug, Sun | 19 Aug, Mon | 2 | Scope changed (No. 17)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 17 Aug, Sat | 19 Aug, Mon | 10 | 17 Aug, Sat | 19 Aug, Mon | 6 | Spillover to next iteration
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6 | [5 empty] | 26 |  |  | 23.5 | (17 August - 1 September) - SMU Week 1 & 2
FYP Wk 17 / SMU Wk 1 |  |  |  | 19 Aug, Mon | 25 Aug, Sun |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 4 | 19 Aug, Mon | 19 Aug, Mon | 4 | Task from previous iteration, replanned
Transaction Deposit | Modify Whole Case | Back End | Kevin, Yao Guang | 20 Aug, Tue | 20 Aug, Tue | 0.5 | 20 Aug, Tue | 20 Aug, Tue | 0.5 | Scope changed (No. 6)
Transaction Withdrawal | Modify Whole Case | Back End | Kevin, Yao Guang | 20 Aug, Tue | 20 Aug, Tue | 0.5 | 20 Aug, Tue | 20 Aug, Tue | 0.5 | Scope changed (No. 6)
Transaction Deposit | Deploy to Server | Back End | Kevin, Yao Guang | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction Withdrawal | Deploy to Server | Back End | Kevin, Yao Guang | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Transaction History Read | Deploy to Server | Back End | Kevin, Yao Guang | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 0.5
Acceptance | Gather Back End Tutorial Requirements from Other Teams | Back End | Jon, Kevin, Yao Guang | 23 Aug, Fri | 23 Aug, Fri | 2 | 23 Aug, Fri | 23 Aug, Fri | 2
FYP Wk 18 / SMU Wk 2 |  |  |  | 26 Aug, Mon | 1 Sep, Sun
Account Deposit Create | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 1
Account Deposit Update | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 0.5
Account Loan Create | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 1
Account Loan Read | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 0.5
Account Loan Update | Debugging & Redeploy | Back End | Kevin & Yao Guang | 26 Aug, Mon | 26 Aug, Mon | 1 | 26 Aug, Mon | 26 Aug, Mon | 1
Product Parameters Read | Develop Integration Code | Back End | Kevin, Yao Guang | 30 Aug, Fri | 30 Aug, Fri | 1 | 29 Aug, Thu | 29 Aug, Thu | 1
Payment Credit Transfer | Develop Base Case | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 2 | 31 Aug, Sat | 31 Aug, Sat | 2
Payment Loan Repayment Full | Develop Base Case | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 2 | 1 Sep, Sun | 1 Sep, Sun | 2
Payment Loan Repayment Partial | Develop Base Case | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 4 | 1 Sep, Sun | 1 Sep, Sun | 3
Payment Credit Transfer | Develop Error Flows | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 1 | 1 Sep, Sun | 1 Sep, Sun | 1
Payment Loan Repayment Full | Develop Error Flows | Back End | Kevin, Yao Guang | 31 Aug, Sat | 1 Sep, Sun | 1 | 1 Sep, Sun | 1 Sep, Sun | 2
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 | [5 empty] | 28 |  |  | 29
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Payment Loan Repayment Partial | Develop Error Flows | Back End | Kevin, Yao Guang | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 2
Payment Credit Transfer | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Full | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Partial | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-03 | 2013-09-03 | 1 | 2013-09-03 | 2013-09-03 | 1
Payment Loan Repayment Full | Deploy to Server | Back End | Kevin, Yao Guang | 2013-09-05 | 2013-09-05 | 1 | 2013-09-06 | 2013-09-06 | 1
Payment Loan Repayment Partial | Deploy to Server | Back End | Kevin, Yao Guang | 2013-09-05 | 2013-09-05 | 1 | 2013-09-06 | 2013-09-06 | 1
Direct Debit Authorization | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-06 | 2013-09-06 | 1 | 2013-09-06 | 2013-09-06 | 1
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-10 | 2013-09-11 | 10 | 2013-09-10 | 2013-09-11 | 10.5
MDM Billing Organization Read List | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-13 | 2013-09-13 | 1 | 2013-09-12 | 2013-09-12 | 1
Direct Debit Authorization | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-12 | 2013-09-12 | 3 | 2013-09-12 | 2013-09-12 | 3
Debugging | Payment_CreditTransfer_Create fix beneficiary ID error |  | Yao Guang | 2013-09-11 | 2013-09-11 | 1 | 2013-09-11 | 2013-09-11 | 0.5
Modifications | Redeploy Transaction Services |  | Yao Guang | 2013-09-10 | 2013-09-10 | 2 | 2013-09-10 | 2013-09-10 | 2
Meetings | Weekly Client, Supervisor Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-09 | 2013-09-14 | 4 | 2013-09-09 | 2013-09-14 | 4
Iteration 8 | [5 empty] | 43.5 |  |  | 46
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Debugging & Modifications | Party_CustomerAccountList_Read leading zeroes | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Payment_CreditTransfer_Create accountFrom mapping error | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Account_Loan_Read & Account_Deposit_Read maturitydate error | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Redeployed Account & Transaction Services | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 0.5 | 2013-09-16 | 2013-09-16 | 0.5
Debugging & Modifications | Payment_CreditTransfer_Create error code fix | Back End | Yao Guang | 2013-09-16 | 2013-09-16 | 1 | 2013-09-16 | 2013-09-16 | 1
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-19 | 2013-09-22 | 9 | 2013-09-19 | 2013-09-22 | 12
Debugging & Modifications | Redeployed Party_Customer_ReadIC | Back End | Yao Guang | 2013-09-20 | 2013-09-20 | 0.5 | 2013-09-20 | 2013-09-20 | 0.5
Credit Approval | Develop Base Case | Back End | Yao Guang | 2013-09-20 | 2013-09-20 | 1 | 2013-09-20 | 2013-09-20 | 1
Party Login Create | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-21 | 2013-09-21 | 2 | 2013-09-21 | 2013-09-21 | 2
Party Login Read | Develop Integration Code | Back End | Kevin, Yao Guang | 2013-09-21 | 2013-09-21 | 1.5 | 2013-09-21 | 2013-09-21 | 1.5
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
User Test 1 |  |  |  | 2013-09-20 | 2013-09-20 | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Debugging & Modifications | Edited Transaction_LoanRepayment_Create & Transaction_LoanPartialRepayment_Create to include settlement account | Back End | Yao Guang | 2013-09-23 | 2013-09-23 | 1 | 2013-09-23 | 2013-09-23 | 1
Credit Approval | Develop Base Case | Back End | Yao Guang | 2013-09-23 | 2013-09-28 | 3 | 2013-09-23 | 2013-09-28 | 2.5 | Re-wrote Credit Rules from mvel to java dialect
Business Rules | Develop Base Case | Back End | Kevin, Yao Guang | 2013-09-23 | 2013-09-26 | 6 | 2013-09-23 | 2013-09-26 | 8
Debugging & Modifications | Modified SMU Core Services for Lab Walkthrough Standardization | Back End | Kevin, Yao Guang | 2013-09-27 | 2013-09-27 | 4 | 2013-09-27 | 2013-09-27 | 4
Debugging & Modifications | Modified Payment Loan Repayment Full and Partial | Back End | Yao Guang | 2013-09-28 | 2013-09-28 | 0.5 | 2013-09-28 | 2013-09-28 | 0.5
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4

## James
James
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1 | [5 empty] | 0 |  |  | 0
FYP Wk 1 |  |  |  | 29 Apr, Mon | 5 May, Sun |  |  |  |  | Labour Day (1 May, Wed)
FYP Wk 2 |  |  |  | 6 May, Mon | 12 May, Sun
FYP Wk 3 |  |  |  | 13 May, Mon | 19 May, Sun
FYP Wk 4 |  |  |  | 20 May, Mon | 26 May, Sun |  |  |  |  | Vesak Day (24 May, Fri)
FYP Wk 5 |  |  |  | 27 May, Mon | 2 Jun, Sun
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2 | [5 empty] | 0 |  |  | 0
FYP Wk 6 |  |  |  | 3 Jun, Mon | 9 Jun, Sun
FYP Wk 7 |  |  |  | 10 Jun, Mon | 16 Jun, Sun
FYP Wk 8 |  |  |  | 17 Jun, Mon | 23 Jun, Sun |  |  |  |  | Proposal (20 June, Fri)
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3 | [5 empty] | 14 |  |  | 14
FYP Wk 9 |  |  |  | 24 Jun, Mon | 30 Jun, Sun
Lo-Fi Prototype | Design | UI | James, Juntao | 24 Jun, Mon | 25 Jun, Tue | 2 | 24 Jun, Mon | 25 Jun, Tue | 2
Backbone JavaScript | Learn | UI | James, Juntao | 26 Jun, Wed | 29 Jun, Sat | 8 | 26 Jun, Wed | 29 Jun, Sat | 8
Bug Metrics | Develop | PM & BA | James | 30 Jun, Sun | 30 Jun, Sun | 2 | 30 Jun, Sun | 30 Jun, Sun | 2
FYP Wk 10 |  |  |  | 1 Jul, Mon | 7 Jul, Sun
Lo-Fi Prototype | Revise | UI | James, Juntao | 1 Jul, Mon | 6 Jul, Sat | 2 | 1 Jul, Mon | 7 Jul, Sun | 2
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4 | [5 empty] | 28 |  |  | 27
FYP Wk 11 |  |  |  | 8 Jul, Mon | 14 Jul, Sun
FYP Wk 12 |  |  |  | 15 Jul, Mon | 21 Jul, Sun
Login Use Case | Develop Basic UI | UI | James, Juntao | 16 Jul, Tue | 19 Jul, Fri | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Party Create Use Case - Party Customer Create | Develop Basic UI | UI | James, Juntao | 16 Jul, Tue | 19 Jul, Fri | 8 | 16 Jul, Tue | 19 Jul, Fri | 7
Party Read & Update Use Case - Party Customer Read | Develop Basic UI | UI | James, Juntao | 20 Jul, Sat | 21 Jan, Sat | 6 | 20 Jul, Sat | 21 Jan, Sat | 6
Party Read & Update Use Case - Party Customer Update | Develop Basic UI | UI | James, Juntao | 20 Jul, Sat | 21 Jan, Sat | 6 | 20 Jul, Sat | 21 Jan, Sat | 6
Login Use Case | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Party Create Use Case - Party Customer Create | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 2 | 22 Jul, Mon | 22 Jul, Mon | 2
Party Read & Update Use Case - Party Customer Read | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 2 | 22 Jul, Mon | 22 Jul, Mon | 2
Party Read & Update Use Case - Party Customer Update | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 2 | 22 Jul, Mon | 22 Jul, Mon | 2
FYP Wk 13 |  |  |  | 22 Jul, Mon | 28 Jul, Sun
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5 | [5 empty] | 50 |  |  | 84
FYP Wk 14 |  |  |  | 29 Jul, Mon | 4 Aug, Sun
Account Deposit Create Use Case - Account Deposit Create | Develop Basic UI | UI | James | 1 Aug, Thu | 1 Aug, Thu | 3 | 23 Jul, Tue | 1 Aug, Thu | 3
Manage Customer's Deposit Accounts Use Case - Account List Read | Develop Basic UI | UI | James | 1 Aug, Thu | 1 Aug, Thu | 3 | 1 Aug, Thu | 1 Aug, Thu | 3
Account Deposit Read & Update - Account Deposit Read | Develop Basic UI | UI | James | 1 Aug, Thu | 1 Aug, Thu | 3 | 1 Aug, Thu | 1 Aug, Thu | 3
Account Deposit Read & Update - Account Deposit Update | Develop Basic UI | UI | James | 1 Aug, Thu | 1 Aug, Thu | 3 | 1 Aug, Thu | 1 Aug, Thu | 3
Account Deposit Create Use Case - Account Deposit Create | Develop Complete UI | UI | James | 3 Aug, Sat | 3 Aug, Sat | 1 | 3 Aug, Sat | 3 Aug, Sat | 1
Manage Customer's Deposit Accounts Use Case - Account List Read | Develop Complete UI | UI | James | 3 Aug, Sat | 3 Aug, Sat | 1 | 3 Aug, Sat | 3 Aug, Sat | 1
Account Deposit Read & Update - Account Deposit Read | Develop Complete UI | UI | James | 3 Aug, Sat | 3 Aug, Sat | 1 | 3 Aug, Sat | 3 Aug, Sat | 1
Account Deposit Read & Update - Account Deposit Update | Develop Complete UI | UI | James | 3 Aug, Sat | 3 Aug, Sat | 1 | 3 Aug, Sat | 3 Aug, Sat | 1
FYP Wk 15 |  |  |  | 5 Aug, Mon | 11 Aug, Sun |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 6 Aug, Tue | 14 Aug, Wed | 6 | 6 Aug, Tue | 14 Aug, Wed | 20
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 5 Aug, Mon | 11 Aug, Sun | 6 | 5 Aug, Mon | 11 Aug, Sun | 16
FYP Wk 16 |  |  |  | 12 Aug, Mon | 18 Aug, Sun |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 10
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 16
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 17 Aug, Sat | 19 Aug, Mon | 10 | 17 Aug, Sat | 19 Aug, Mon | 6 | Spillover to next iteration
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6 | [5 empty] | 24 |  |  | 19 | (17 August - 1 September) - SMU Week 1 & 2
FYP Wk 17 / SMU Wk 1 |  |  |  | 19 Aug, Mon | 25 Aug, Sun |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 4 | 19 Aug, Mon | 19 Aug, Mon | 4 | Task from previous iteration, replanned
Party Create Use Case - MDM Customer Type Read | Develop Basic UI | UI | James | 23 Aug, Fri | 23 Aug, Fri | 1 | 23 Aug, Fri | 23 Aug, Fri | 1
Party Create Use Case - MDM Customer Type Read | Develop Complete UI | UI | James | 23 Aug, Fri | 23 Aug, Fri | 1 | 23 Aug, Fri | 23 Aug, Fri | 1
Transaction Deposit Use Case | Develop Basic UI | UI | James | 22 Aug, Thu | 22 Aug, Thu | 3 | 22 Aug, Thu | 22 Aug, Thu | 1
Transaction Withdrawal Use Case | Develop Basic UI | UI | James | 22 Aug, Thu | 22 Aug, Thu | 3 | 22 Aug, Thu | 22 Aug, Thu | 1
Transaction History Read Use Case | Develop Basic UI | UI | James | 22 Aug, Thu | 22 Aug, Thu | 3 | 22 Aug, Thu | 22 Aug, Thu | 2
Transaction Deposit Use Case | Develop Complete UI | UI | James | 22 Aug, Thu | 22 Aug, Thu | 1 | 22 Aug, Thu | 22 Aug, Thu | 1
Transaction Withdrawal Use Case | Develop Complete UI | UI | James | 22 Aug, Thu | 22 Aug, Thu | 1 | 22 Aug, Thu | 22 Aug, Thu | 1
Transaction History Read Use Case | Develop Complete UI | UI | James | 22 Aug, Thu | 22 Aug, Thu | 1 | 22 Aug, Thu | 22 Aug, Thu | 2
FYP Wk 18 / SMU Wk 2 |  |  |  | 26 Aug, Mon | 1 Sep, Sun
Transaction Deposit Use Case | Develop Complete UI | UI | James | 2013-08-27 | 2013-08-27 | 2 | 2013-08-27 | 2013-08-27 | 2
Transaction Withdrawal Use Case | Develop Complete UI | UI | James | 2013-08-27 | 2013-08-27 | 2 | 2013-08-27 | 2013-08-27 | 2
Transaction History Read Use Case | Develop Complete UI | UI | James | 2013-08-27 | 2013-08-27 | 2 | 2013-08-27 | 2013-08-27 | 1
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 | [5 empty] | 25 |  |  | 22
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Account Deposit Create Use Case - Product Parameters Read | Develop Basic UI | UI | James, Kevin | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Read & Update Use Case - Product Parameters Read | Develop Basic UI | UI | James, Kevin | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Create Use Case Product Parameters Read | Develop Basic UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Read & Update Use Case - Product Parameters Read | Develop Basic UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Create Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Deposit Read & Update Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Create Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
Account Loan Read & Update Use Case - Product Parameters Read | Develop Complete UI | UI | James | 2013-09-03 | 2013-09-03 | 0.5 | 2013-09-03 | 2013-09-03 | 0.5
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
Payment Credit Transfer Bill Payment Use Case | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3 | 2013-09-11 | 2013-09-14 | 2
Payment Loan Repayment Full | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3 | 2013-09-11 | 2013-09-14 | 2
Payment Loan Repayment Partial | Develop Basic UI | UI | James | 2013-09-11 | 2013-09-15 | 3 | 2013-09-11 | 2013-09-14 | 2
Payment Loan Repayment Full | Develop Complete UI | UI | James | 2013-09-11 | 2013-09-15 | 1 | 2013-09-11 | 2013-09-14 | 1
Payment Loan Repayment Partial | Develop Complete UI | UI | James | 2013-09-11 | 2013-09-15 | 1 | 2013-09-11 | 2013-09-14 | 1
Debugging | Product Parameters Read |  | Kevin, James | 2013-09-13 | 2013-09-13 | 1 | 2013-09-13 | 2013-09-13 | 1
Modifications | Added Leading Zeroes to Values |  | James | 2013-09-15 | 2013-09-15 | 2 | 2013-09-15 | 2013-09-15 | 2
Modifications | Reworked Party, Account & Transactions |  | James | 2013-09-15 | 2013-09-15 | 3 | 2013-09-15 | 2013-09-15 | 3
Meetings | Weekly Client, Supervisor Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-09 | 2013-09-14 | 4 | 2013-09-09 | 2013-09-14 | 4
Iteration 8 | [5 empty] | 22 |  |  | 26
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Debugging & Modifications | Transaction Deposit & Withdrawal Penalty Rate, validation issues | UI | James | 2013-09-16 | 2013-09-16 | 4 | 2013-09-16 | 2013-09-16 | 7
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
User Test 1 |  |  |  | 2013-09-20 | 2013-09-20 | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Debugging & Modifications | Standardize & Revamp UI | UI | James | 2013-09-23 | 2013-09-23 | 5 | 2013-09-23 | 2013-09-23 | 7
Debugging & Modifications | Modified Payment Credit Transfer Bill Payment Use Case, adjusted buttonc olour, date calendar changes, minimum amount | UI | James | 2013-09-23 | 2013-09-23 | 1 | 2013-09-23 | 2013-09-23 | 2
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4

## Juntao
Juntao
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 1 | [5 empty] | 0 |  |  | 0
FYP Wk 1 |  |  |  | 29 Apr, Mon | 5 May, Sun |  |  |  |  | Labour Day (1 May, Wed)
FYP Wk 2 |  |  |  | 6 May, Mon | 12 May, Sun
FYP Wk 3 |  |  |  | 13 May, Mon | 19 May, Sun
FYP Wk 4 |  |  |  | 20 May, Mon | 26 May, Sun |  |  |  |  | Vesak Day (24 May, Fri)
FYP Wk 5 |  |  |  | 27 May, Mon | 2 Jun, Sun
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 2 | [5 empty] | 0 |  |  | 0
FYP Wk 6 |  |  |  | 3 Jun, Mon | 9 Jun, Sun
FYP Wk 7 |  |  |  | 10 Jun, Mon | 16 Jun, Sun
FYP Wk 8 |  |  |  | 17 Jun, Mon | 23 Jun, Sun |  |  |  |  | Proposal (20 June, Fri)
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 3 | [5 empty] | 14 |  |  | 14
FYP Wk 9 |  |  |  | 24 Jun, Mon | 30 Jun, Sun
Lo-Fi Prototype | Design | UI | James, Juntao | 24 Jun, Mon | 25 Jun, Tue | 2 | 24 Jun, Mon | 25 Jun, Tue | 2
Backbone JavaScript | Learn | UI | James, Juntao | 26 Jun, Wed | 29 Jun, Sat | 8 | 26 Jun, Wed | 29 Jun, Sat | 8
Bug Metrics | Develop | PM & BA | James | 30 Jun, Sun | 30 Jun, Sun | 2 | 30 Jun, Sun | 30 Jun, Sun | 2
FYP Wk 10 |  |  |  | 1 Jul, Mon | 7 Jul, Sun
Lo-Fi Prototype | Revise | UI | James, Juntao | 1 Jul, Mon | 6 Jul, Sat | 2 | 1 Jul, Mon | 7 Jul, Sun | 2
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 4 | [5 empty] | 28 |  |  | 27
FYP Wk 11 |  |  |  | 8 Jul, Mon | 14 Jul, Sun
FYP Wk 12 |  |  |  | 15 Jul, Mon | 21 Jul, Sun
Login Use Case | Develop Basic UI | UI | James, Juntao | 16 Jul, Tue | 19 Jul, Fri | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Party Create Use Case - Party Customer Create | Develop Basic UI | UI | James, Juntao | 16 Jul, Tue | 19 Jul, Fri | 8 | 16 Jul, Tue | 19 Jul, Fri | 7
Party Read & Update Use Case - Party Customer Read | Develop Basic UI | UI | James, Juntao | 20 Jul, Sat | 21 Jan, Sat | 6 | 20 Jul, Sat | 21 Jan, Sat | 6
Party Read & Update Use Case - Party Customer Update | Develop Basic UI | UI | James, Juntao | 20 Jul, Sat | 21 Jan, Sat | 6 | 20 Jul, Sat | 21 Jan, Sat | 6
Login Use Case | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 1 | 16 Jul, Tue | 16 Jul, Tue | 1
Party Create Use Case - Party Customer Create | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 2 | 22 Jul, Mon | 22 Jul, Mon | 2
Party Read & Update Use Case - Party Customer Read | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 2 | 22 Jul, Mon | 22 Jul, Mon | 2
Party Read & Update Use Case - Party Customer Update | Develop Complete UI | UI | James, Juntao | 22 Jul, Mon | 22 Jul, Mon | 2 | 22 Jul, Mon | 22 Jul, Mon | 2
FYP Wk 13 |  |  |  | 22 Jul, Mon | 28 Jul, Sun
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 5 | [5 empty] | 50 |  |  | 84
FYP Wk 14 |  |  |  | 29 Jul, Mon | 4 Aug, Sun
Account Loan Create Use Case - Account Loan Create | Develop Basic UI | UI | Juntao | 2 Aug, Fri | 2 Aug, Fri | 3 | 2 Aug, Fri | 2 Aug, Fri | 3
Manage Customer's Loan Accouts Use Case - Account List Read | Develop Basic UI | UI | Juntao | 2 Aug, Fri | 2 Aug, Fri | 3 | 2 Aug, Fri | 2 Aug, Fri | 3
Account Loan Read & Update - Account Deposit Read | Develop Basic UI | UI | Juntao | 2 Aug, Fri | 2 Aug, Fri | 3 | 2 Aug, Fri | 2 Aug, Fri | 3
Account Loan Read & Update - Account Deposit Update | Develop Basic UI | UI | Juntao | 2 Aug, Fri | 28 Jul, Sun | 3 | 2 Aug, Fri | 28 Jul, Sun | 3
Account Loan Create Use Case - Account Loan Create | Develop Complete UI | UI | Juntao | 4 Aug, Sun | 4 Aug, Sun | 1 | 4 Aug, Sun | 4 Aug, Sun | 1
Manage Customer's Loan Accouts Use Case - Account List Read | Develop Complete UI | UI | Juntao | 4 Aug, Sun | 4 Aug, Sun | 1 | 4 Aug, Sun | 4 Aug, Sun | 1
Account Loan Read & Update - Account Deposit Read | Develop Complete UI | UI | Juntao | 4 Aug, Sun | 4 Aug, Sun | 1 | 4 Aug, Sun | 4 Aug, Sun | 1
Account Loan Read & Update - Account Deposit Update | Develop Complete UI | UI | Juntao | 4 Aug, Sun | 4 Aug, Sun | 1 | 4 Aug, Sun | 4 Aug, Sun | 1
FYP Wk 15 |  |  |  | 5 Aug, Mon | 11 Aug, Sun |  |  |  |  | Hari Raya Puasa (8 Aug, Thu); National Day (9 Aug, Fri)
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 6 Aug, Tue | 14 Aug, Wed | 6 | 6 Aug, Tue | 14 Aug, Wed | 20
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 5 Aug, Mon | 11 Aug, Sun | 6 | 5 Aug, Mon | 11 Aug, Sun | 16
FYP Wk 16 |  |  |  | 12 Aug, Mon | 18 Aug, Sun |  |  |  |  | Acceptance, (16 Aug, Fri)
Acceptance | Prototype Demo Preparation | UI | James, Juntao, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 10
Acceptance | Presentation Preparation | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 12 Aug, Mon | 14 Aug, Wed | 6 | 12 Aug, Mon | 14 Aug, Wed | 16
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 17 Aug, Sat | 19 Aug, Mon | 10 | 17 Aug, Sat | 19 Aug, Mon | 6 | Spillover to next iteration
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 6 | [5 empty] | 22 |  |  | 23.5 | (17 August - 1 September) - SMU Week 1 & 2
FYP Wk 17 / SMU Wk 1 |  |  |  | 19 Aug, Mon | 25 Aug, Sun |  |  |  |  | Registration (21 Aug, Wed)
Midterm | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 19 Aug, Mon | 19 Aug, Mon | 4 | 19 Aug, Mon | 19 Aug, Mon | 4 | Task from previous iteration, replanned
Account Deposit Create Use Case - MDM Product Type Read Changes | Develop Basic UI | UI | Juntao | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 1
Account Loan Create Use Case - MDM Product Type Read & Changes | Develop Basic UI | UI | Juntao | 21 Aug, Wed | 21 Aug, Wed | 1 | 21 Aug, Wed | 21 Aug, Wed | 1
Account Deposit Create Use Case - MDM Product Type Read & Changes | Develop Complete UI | UI | Juntao | 22 Aug, Thu | 22 Aug, Thu | 1 | 22 Aug, Thu | 22 Aug, Thu | 1
Account Loan Create Use Case - MDM Product Type Read & Changes | Develop Complete UI | UI | Juntao | 22 Aug, Thu | 22 Aug, Thu | 1 | 22 Aug, Thu | 22 Aug, Thu | 1
Login Use Case | Testing - JUnit | UI | Juntao | 23 Aug, Fri | 23 Aug, Fri | 1 | 23 Aug, Fri | 23 Aug, Fri | 2.5
Party Create Use Case | Testing - JUnit | UI | Juntao | 24 Aug, Sat | 24 Aug, Sat | 1 | 24 Aug, Sat | 24 Aug, Sat | 3
Party Read & Update | Testing - JUnit | UI | Juntao | 25 Aug, Sun | 25 Aug, Sun | 1 | 25 Aug, Sun | 25 Aug, Sun | 3
Login Use Case | Debugging | UI | Juntao, Kevin | 24 Aug, Sat | 24 Aug, Sat | 2 | 26 Aug, Mon | 24 Aug, Sat | 0
Party Create Use Case | Debugging | UI | Juntao, Kevin | 24 Aug, Sat | 24 Aug, Sat | 2 | 24 Aug, Sat | 24 Aug, Sat | 0
Party Read & Update | Debugging | UI | Juntao, Kevin | 24 Aug, Sat | 24 Aug, Sat | 2 | 24 Aug, Sat | 24 Aug, Sat | 0.5
FYP Wk 18 / SMU Wk 2 |  |  |  | 26 Aug, Mon | 1 Sep, Sun
Account Deposit Create Use Case | Testing - JUnit | UI | Juntao | 26 Aug, Mon | 27 Aug, Tue | 2 | 26 Aug, Mon | 27 Aug, Tue | 2
Account Deposit Read & Update Use Case | Testing - JUnit | UI | Juntao | 26 Aug, Mon | 27 Aug, Tue | 1 | 26 Aug, Mon | 27 Aug, Tue | 1
Account Loan Create Use Case | Testing - JUnit | UI | Juntao | 26 Aug, Mon | 27 Aug, Tue | 1 | 26 Aug, Mon | 27 Aug, Tue | 2
Account Loan Read & Update Use Case | Testing - JUnit | UI | Juntao | 26 Aug, Mon | 27 Aug, Tue | 1 | 26 Aug, Mon | 27 Aug, Tue | 1.5
Task |  |  |  | Planned |  |  | Actual
Component | Description | Type | Action By | Start Date | End Date | Hours | Start Date | End Date | Hours | Comments
Iteration 7 | [5 empty] | 18 |  |  | 23
FYP Wk 19 / SMU Wk 3 |  |  |  | 2013-09-02 | 2013-09-08
Party Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 3
Party Read & Update | Testing - HTMLUnit | UI | Juntao | 2013-09-02 | 2013-09-02 | 1 | 2013-09-02 | 2013-09-02 | 3
Account Deposit Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Account Deposit Read & Update Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Account Loan Create Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
Account Loan Read & Update Use Case | Testing - HTMLUnit | UI | Juntao | 2013-09-05 | 2013-09-05 | 1 | 2013-09-05 | 2013-09-05 | 1
FYP Wk 20 / SMU Wk 4 |  |  |  | 2013-09-09 | 2013-09-15
Customer's Accounts Dashboard Use Case - Transaction History Read | Develop Basic UI | UI | Juntao | 2013-09-10 | 2013-09-11 | 2 | 2013-09-10 | 2013-09-11 | 3
Customer's Accounts Dashboard Use Case - Account List Read | Develop Basic UI | UI | Juntao | 2013-09-10 | 2013-09-11 | 2 | 2013-09-10 | 2013-09-11 | 2
Customer's Accounts Dashboard Use Case - Transaction History Read | Develop Basic UI | UI | Juntao | 2013-09-14 | 2013-09-15 | 2 | 2013-09-15 | 2013-09-15 | 2
Customer's Accounts Dashboard Use Case - Account List Read | Develop Basic UI | UI | Juntao | 2013-09-14 | 2013-09-15 | 2 | 15 Sep, Sun | 2013-09-15 | 2
Meetings | Weekly Client, Supervisor Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-09 | 2013-09-14 | 4 | 2013-09-09 | 2013-09-14 | 4
Iteration 8 | [5 empty] | 23 |  |  | 23
FYP Wk 21 / SMU Wk 5 |  |  |  | 2013-09-16 | 2013-09-22
Customer's Accounts Dashboard Use Case | Develop Complete UI | UI | Juntao | 2013-09-16 | 2013-09-16 | 5 | 2013-09-16 | 2013-09-16 | 5
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-16 | 2013-09-21 | 4 | 2013-09-16 | 2013-09-21 | 4
User Test 1 |  |  |  | 2013-09-20 | 2013-09-20 | 2
User Test 1 | Addressing Feedback & Findings | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-20 | 2013-09-22 | 2 | 2013-09-20 | 2013-09-22 | 2
FYP Wk 22 / SMU Wk 6 |  |  |  | 2013-09-23 | 2013-09-29
Party User PIN Create | Taking Over | Back End | Juntao | 2013-09-24 | 2013-09-24 | 1.5 | 2013-09-24 | 2013-09-24 | 1.5
Party User PIN Create | Develop Integration Code | Back End | Juntao | 2013-09-24 | 2013-09-24 | 1.5 | 2013-09-24 | 2013-09-24 | 1.5
Party User PIN Create | Develop Basic UI | UI | Juntao | 2013-09-25 | 2013-09-25 | 1 | 2013-09-25 | 2013-09-25 | 1.5
Party User PIN Create | Develop Complete UI | UI | Juntao | 2013-09-25 | 2013-09-25 | 1 | 2013-09-25 | 2013-09-25 | 1.5
Debugging & Modifications | Party User PIN Create | UI | Juntao | 2013-09-27 | 2013-09-27 | 1 | 2013-09-27 | 2013-09-27 | 2
Meetings | Weekly Client & Group | Whole Team | Geraldine, Jon, James, Juntao, Kevin, Yao Guang | 2013-09-23 | 2013-09-29 | 4 | 2013-09-23 | 2013-09-29 | 4