## Summary
Iteration | Low | High | Crtical | Total Score | Ending Score | Action Taken
1 | 0 |  |  |  |  | -
2 | 0 |  |  |  |  | -
3 | 0 |  |  |  |  | -
4 | 4 | 5 | 0 | 9 | 0 | Use the planned debugging time in the iteration
5 | 3 | 2 | 0 | 13 | 5 | Use the planned debugging time in the iteration

## Bug Log
S/N | Bug Description | Impact | Date Found | Found by | Source | Date Resolved | Resolved by | Solution | Status
Iteration 1
No coding
Iteration 2
No coding
Iteration 3
No coding
Iteration 4
1 | NullPointerException' when trying to bypass "Login" page to access other index.jsp while it should be redirected to "Login" page | Low | 2013-07-04 | Akash | Admin Website | - | - | Started working after deployment | Solved
1 | Uncheck/Check box is not working for login page | Low | 2013-07-04 | Akash | Application | 2013-07-10 | Saloni | The checkbox has been resolved due to change of codes | Solved
2 | Buttons are not aligned for the login page | Low | 2013-07-04 | Akash | Application | 2013-07-11 | Akash | Aligned buttons | Solved
3 | When the back buttons is clicked once logged in the app does not quit but goes back to sign in page | Med | 2013-07-04 | Akash | Application | 2013-07-12 | Akash | Added a line of code to prevents from going back to sign in page | Solved
4 | Once logged in the user is not greeted by name | Low | 2013-07-04 | Akash | Application | 2013-07-12 | Roohiya | Allow admin access to everyone | Solved
Iteration 5
1 | When adding admin, the 'View Admin' does not show that a new admin has been added unless page refreshed | High | 2013-08-08 | Akash | Admin Website | - | - |  | Not Solved
2 | On Upload comic hardcopy and softcopy check buttons mis aligned | Low | 2013-08-08 | Akash | Admin Website | 2013-08-18 | Hazirah | Aligned buttons | Solved
3 | Navigation tab not able to highlight to the corrosponding page | Low | 2013-08-08 | Akash | Application | 2013-08-10 | Saraniya | Using Pager TabStrip class | Solved
4 | Not able to view comic when clicking image button | High | 2013-08-08 | Akash | Application | 2013-08-11 | Saraniya | View class | Solved
5 | Gap between navigation tab and pages (UI issue) | Low | 2013-08-08 | Akash | Application | 2013-08-10 | Akash | Made changes to layout | Solved