## Metrics Summary
Iteration | Low Impact | High Impact | Critical Impact | Total Points | Status | Action |  | Iteration | Total Points
1 | 2 | 1 | 0 | 7 | Completed | Solved using allocated debugging time |  | 1 | 7
4 | 1 | 3 | 0 | 16 | Completed | Solved using debugging time. Extended iteration slightly |  | 2 | 0
5 | 1 | 4 | 0 | 21 | Completed | Stop current development to resolve all bugs. Brought forward unsolvable bugs to next iteration -Future iterations rescheduled |  | 3 | 0
6 | 2 | 1 | 0 | 7 | Completed | Solved using allocated debugging time |  | 4 | 16
7 | 1 | 0 | 1 | 11 | Completed | Solved using allocated debugging time |  | 5 | 21
8 | 1 | 2 | 0 | 11 | Completed | Solved using allocated debugging time |  | 6 | 7
9 | 0 | 2 | 0 | 10 | Completed | Solved using allocated debugging time |  | 7 | 11
[8 empty] | 8 | 11
[8 empty] | 9 | 10
Severity | Action | [6 empty] | 10 | 0
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues. | [5 empty] | Totsl Points Formula:
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working. | [5 empty] | 1 low x 1pt + 1 high x 5pt + 1 critical x 10pt
Critical Impact(10 points) | The system is down or is usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points <= 15 | Fix during buffer time only. 2. Review possible pairing & estimation issues.
Points >- 15 | Stop the current development immediately to solve them bug. PM to reschedule future iterations

## Bugs Metrics Details
S/N | Iteration No. | Functionality | Bugs Description | Severity (L/H/C) | Name of Webpage | Root Cause/s | Change/s Made | Solved. Yes/No? | No. of Hours Taken | Metrics Points
1 | 1 | ACH_Bank_Read | Unable to read bank from database, request returns "error invocation" | H | read_update_bank_details.html | Invalid URL in ajax call to invoke method from cloud | Update URL with latest correction | Yes | 2 | 5
2 | 1 | ACH_Bank_Read | Unable to return all values of specific bank | L | read_update_bank_details.html | Invalid print statement to populate parameters | Implement codes changes and html alignments | Yes | 0.5 | 1
3 | 1 | ACH_Bank_Edit | Unable to update bank details | L | read_update_bank_details.html | Invalid ach_id parsed in | Changed primary key in database | Yes | 1 | 1
4 | 4 | ACH_Payment_Orchestrate | Unable to route to desired messaging types after uploading csv files with payment instructions | L | ACH_Payment_Orchestrate (TIBCO Businessworks) | Incorrect mapping of variables | Execute changes to variables mapping with aid from messaging documents | Yes | 2 | 1
5 | 4 | ACH_Payment_Orchestrate | Unable to execute transfer to a bank of different messaging types | H | ACH_Payment_Orchestrate (TIBCO Businessworks) | Invalid routing logic in BW caused by error in mapping variables | Execute changes to variables mapping with aid from messaging documents | Yes | 2.5 | 5
6 | 4 | ACH_Payment_Orchestrate | Unable to complete process in TIBCO BW. Request gets stuck in render xml process | H | ACH_Payment_Orchestrate (TIBCO Businessworks) | Invalid routing logic in BW caused by error in mapping variables | Execute changes to variables mapping with aid from messaging documents | Yes | 3 | 5
7 | 4 | ACH_Payment_Orchestrate | Payment table not updated after executing transaction | H | ACH_Payment_Orchestrate (TIBCO Businessworks) | Invalid SQL indentation | Made ammendments to SQL indentation | Yes | 2 | 5
8 | 4 | ACH_Payment_Orchestrate | Unable to include fee in the payment orchestration process | H | ACH_Payment_Orchestrate (TIBCO Businessworks) | Error in invoking fee from fee table via payment orchestration service | Make changes to SQL statement of payment orchestration and added a new query to retrieve fee | No | 2 | 5 | Brought forward to next iteration
9 | 5 | ACH_Payment_Orchestrate (Phase 2) | ACH Fees get added on to existing fees but tier does not move up to the next tier of quota | H | ACH_Payment_Orchestrate (TIBCO Businessworks) | Incorrect logic when adding new fees to existing fee table caused by variables mapping within TIBCO | Make changes to TIBCO variable mapping | Yes | 3 | 5
10 | 5 | ACH_Payment_Orchestrate (Phase 2) | User unable to upload csv file with datetime field | H | ACH_Payment_Orchestrate (TIBCO Businessworks) | Invalid datetime in TIBCO BW when user updates a csv file with datetime format | Make changes to TIBCO BW to implement formatting to datetime variables | Yes | 2 | 5
12 | 5 | ACH_Fee_Update | User unable to upload ACH fee | H | setup_fees_and_charges.html | Incorrect business logic to update database within setup_fees_and_charges.html | Make changes to values parsed into Businessworks to update DB | Yes | 2 | 5
13 | 5 | ACH_Fee_Create | User unable to create multiple fee | H | ACH_Fee_Create (TIBCO BW) | Duplicate SQL key in fee database caused my primary key | Make changes to sql structure in the table | Yes | 2 | 5
14 | 5 | ACH_Fee_Create | User unable to create fee with commas (ie 100,000) | L | ACH_Fee_Create (TIBCO BW) | Incompatible format with TIBCO | Format front end validation to limit input | Yes | 1 | 1
16 | 6 | ACH_Fee_Update | Unable to edit tier quote for fee | L | Unable to update fee and display successful message | Changes in code to add in validation | Made changes to read_update_bank_details.html to add in js pop up | Yes | 0.5 | 1
17 | 6 | ACH_Fee_Read | Wrong fee type shown upon filter | L | setup_fees_and_charges.html | Incorrect filtering logic when filtering tiers using drop down | Made changes to display logic to tabulate fields of input | Yes | 1 | 1
18 | 6 | ACH_Report_Bucket | Unable to automate writing to database | L | ACH_Report_Bucket (TIBCO BW) | Incorrect sql insert statement | Make changes to sql statement | Yes | 2 | 1
19 | 7 | ACH_Report_Bucket | d3 graph's corrupted the whole website's display | C | All Website | due to changes in the javascript / jquery, all previously done function was not able to show up | redo the d3 with app's before d3 version | Yes | 2 | 10
20 | 7 | ACH Settlement | Unable to compute total amount to be settled to be written into settlement table | L | ACH_Settlement | Incorrect Sql query in iterating through payment tables | Make changes to sql statement | Yes | 2 | 1
22 | 8 | View Payments | Error occurs when user tries to view payments when the number of payments returned is less than 10 entries | L | view_payments.jsp | Unncecessary button to navigate to next page when the number of payment entries returned is less than 10 | Add in condition to hide button when the number of entries returned is less than 10 | Yes | 2 | 1
23 | 8 | ACH_Report_Bucket | Graph is unable to display when users chooses to view hourly transaction volume | H | home.jsp | Incorrect logic in report bucket codes | Make changes to align legend to display graphs in intuitive manner | Yes | 2 | 2
24 | 8 | View and Invoke Settlement | Date of Settlement shown in dropdown is truncated | H | view_invoke_netting_settlement.jsp | Incorrect logic in string extraction method | Implement codes changes to extract required strings from date time | Yes | 2 | 5
25 | 9 | View Payments Status | Payment status shown as settled when there are insufficient funds in settlement account | H | view_invoke_netting_settlement.jsp | Incorrect logic in TIBCO BW Service to execute settlement via payments prioritizarion | Make changes to logic in TIBCO BW Service | Yes | 8 | 8
26 | 9 | Add Exception Handling Rules | Throw error when reading exception handling rules, resulting in error with edit bank functionality | H | read_update_bank_details.html | Storing a rule with empty string results in an error when invoking the service. This error is only seen via the front end UI, and is not visible when invoking the service via SOAPUI | Validate field when adding rule to prevent user from entering an empty string as a rule | Yes | 3 | 3
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255

## Metrics Details (Reference) (hidden)
S/N | Iteration No. | Functionality | Bugs Description | Severity (L/H/C) | Name of Webpage | Root Cause/s | Change/s Made | Solved. Yes/No? | No. of Hours Taken | Metrics Points
1 | 1 | Bootstrap | No .zip file is chosen, system displays wrong error message | Low | Bootstrap.jsp | .zip file validation code | Added sendRedirect to Bootstrap page using parameter | Yes | 3 | 1
2 | 1 | Bootstrap | Missing .csv files in zip folder is not reported | Low | BootstrapController.java | .zip file validation code | Validation for any missing csv file | Yes | 2.5 | 1
3 | 1 | Admin Login | Unable to proceed to AdminHome.jsp after successful login | High | AdminHome.jsp | Missing curly brace | Added necessary code at AdminHome.jsp | Yes | 0.5 | 5
4 | 2 | Admin Logout | Admin still able to access AdminHome.jsp after clicking logout | High | AdminHome.jsp | Incorrect redirection. Fail to invalidate session | Page is now redirected to LogoutController.do instead of Login.jsp | Yes | 0.25 | 5
5 | 2 | Student Logout | Student still able to access Home.jsp after clicking logout | High | Logut.jsp | Incorrect redirection. Fail to invalidate session | Page is now redirected to LogoutController.do instead of Login.jsp | Yes | 0.25 | 5
6 | 2 | View Courses/sections | Student unable to view courses/sections repeatedly | High | ViewCourseServlet.java , ViewSectionServlet.java | Retrieve studentManager session instead of courseManager session | Change studentManager session to courseManager session | Yes | 0.25 | 5
7 | 2 | View Courses/sections | Search textbox is empty. Only headers displayed. | Low | ViewCourse.jsp | Complicated search logic | Search logic is revised | Yes | 0.3 | 1
8 | 2 | View Courses/sections | Students can bid all courses inclusive those not offered by their school in Round 1 | Low | ViewCourse.jsp | School validation is missed out during development stage | School validation added to display message, "Currently not available". | Yes | 0.25 | 1
9 | 2 | View Courses/sections | Search function only display the first record found | Low | ViewCourse.jsp | Complicated search logic | Search logic is revised | Yes | 0.8 | 1
10 | 2 | View Courses/sections | Apache Tomcat error page is displayed if no course selected to view sections | Low | ViewCourse.jsp | Null pointer exception because no parameters passed to ViewSections | Throw error message back to ViewCourse.jsp if no managers is initiated. | Yes | 0.3 | 1
11 | 2 | Place Bids | Amount validation error in PlaceBidsController (unable to parseDouble the amount correctly) | High | ViewCourse.jsp, PlaceBidsController.java | PlaceBidsController is unable to get the correct parameters | Correct the passing parameters logics from ViewCourse.jsp to PlaceBidsController.java | Yes | 1 | 5
12 | 2 | View Courses/sections | Checkboxes for courses do appeared in Round 2 | Low | ViewCourse.jsp | Missing logic to check Round == 2 | Logic added to check for Round 2 | Yes | 0.25 | 1
13 | 2 | Place Bids | PlaceBidsController is unable to read parameters from PlaceBid form | High | PlaceBids.jsp | Form sends over all records displayed in ViewSections as parameters | Use radio buttons in view sections & implement PlaceBidForm | Yes | 2 | 5
14 | 2 | Place Bids | All bids place are redirected to successful page without having to go through validations | High | ViewBids.jsp, PlaceBids.jsp, PlaceBidsController.java, SuccessfulBid.jsp | PlaceBidsController retrieves the wrong entity from the Bid Manager | Add value attribute for radio button | Yes | 2 | 5
15 | 2 | Open/Close Round | Apache Tomcat error page is displayed if student want to view course before Admin bootstrap a fresh data | Low | Home.jsp, ViewCourse.jsp | No managers initiated in context | Throw error message back to Home.jsp if no managers is initiated. | Yes | 0.25 | 1
16 | 2 | Place Bids | Student can still bid for section even though the round is inactive (before bootstrap) | High | ViewCourseController.java | Missing logic to check current round | Added condition if else condition to determine current round | Yes | 0.5 | 5
17 | 2 | Place Bids | Student can still bid for section even though the round is inactive (in between Round 1 & Round 2) | High | ViewCourseController.java | Missing logic to check current round | Added condition if else condition to determine current round | Yes | 0.5 | 5
18 | 3 | View Bid Status | When bootstrap is not done, NullPointerException thrown when retrieving bids | Low | ViewBids.jsp | BidManager is not initialized | Add if-else statement to check for null BidManager. Redirect to Home.jsp if null. Error message is displayed on home page | Yes | 0.5 | 1
19 | 3 | View Bid Status | When bidding round is not open, IllegalStateException is thrown when retrieving bids | Low | ViewBids.jsp | Logic to check for current bidding round throws error message back to Home.jsp but missing Return statement | Add Return statement to ViewBids.jsp after throwing error message to Home page | Yes | 0.5 | 1
20 | 3 | Place Bids | When Placing bids, prerequiste is not checked | Low | PlaceBidsController.java | logic to check for prerequisite is put in wrong sequence in comparison to other logics | Move the code to verify prerequisite to correct position | Yes | 0.5 | 1
21 | 3 | Clearing Round 1 | ClearingRoundResult.jsp doesn't display the sorting of bids, but redirected to Login.jsp | Low | ClearingRoundResult.jsp | Forgot to include file AdminHeader.jsp page to the ClearingRoundResult.jsp page. | Added the line to include AdminHeader.jsp to the page | Yes | 0.25 | 1
22 | 3 | View Bid Status | At Round 2, successful bids from round 1 are displayed as "Pending" | Low | ViewBidsStatus.jsp | Flaw in round 2 display bid status logic | Add in round 2 display bid status logic to ViewBidsStatus.jsp | Yes | 0.25 | 1
23 | 3 | View Time Table | At round 2, failed bids are still displayed in Timetable (should be removed) | High | ViewTimetable.jsp | Flaws in round 2 timetable logic | Added code to remove failed bids to round 2 timetable logic | Yes | 0.25 | 5
24 | 3 | View Bid Status | At round 2, bid status are not displayed | High | ViewBidsStatus.jsp | Flaws in round 2 timetable logic | Edit the View Bid Status logic to retrieve failed bids from round 1. Check if bids are present in failed bids ArrayList and display status accordingly | Yes | 1 | 5
25 | 3 | View Section | After Round 1, the size of some sections are not deducted on account for successful bids | High | ViewSections.jsp | Logic to display Section takes in the size of Section entities, without updating size of Section after clearing round | Added the line to update the section size in the section table in database | Yes | 0.25 | 5
26 | 3 | Closing Round 1 | After round 1 is closed, the available slots in each Section were not deducted | High | ClearingRoundController.java | Lack the logic to update Section available slots | Include the logic to set new section size in ClearingRoundController.java | Yes | 1 | 5
27 | 3 | View Section | No section selected and press Place Bids, no error displayed but the app navigates to TomCat error page | Low | ViewSections.jsp | No code to display error message when no sections are selected | Direct the user back to ViewSection.jsp and display error message "Please select a section to bid" | Yes | 0.5 | 1
28 | 3 | View Time Table | In round 2, successfully bidded sections are not displayed in the timetable | High | ViewTimetable.jsp | Logic for round 2 display is flawed - unable to take in parameters of successful bids from round 1 | Edit the logic for round 2 to take in successful bids and display as enrolled sections | Yes | 1 | 5
29 | 3 | View Time Table | In round 2, failed bids were not removed from the timetable | High | ViewTimetable.jsp | Logic for round 2 display timetable lacks the check for failed bids. | Add the logic to check if bids are failed after clearing round 1. Do not display the section information if student failed to bid for it | Yes | 1 | 5
30 | 3 | View Time Table | In round 2, pending bids are not displayed | High | ViewTimetable.jsp | Incorrect logic to classify pending bids. Boolean value is overridden for every bid. | Change the logic to store the bid status in string instead of boolean. | Yes | 1.5 | 5
31 | 3 | View Time table | After round 2 is closed, successfully bidded sections are displayed in wrong color code | Low | ViewTimeTable.jsp | Boolean used to check for successful bids before printing was missing | Added boolean to check for successful bids before adding into biddedSections array list | Yes | 1 | 1
32 | 3 | View Time table | In round 2, unsuccessful bids are displayed when supposedly not | High | ViewTimeTable.jsp | Boolean used to check for unsucessful bids was put in wrong place. | Edit display logic for round 2 to not take in unsuccessful bids into biddedSections array list | Yes | 1 | 5
33 | 3 | Closing Round 1 | When closing round 1, suppose to populate failed and successful bids in respective tables | High | ClearingRoundController.java | Incorrect logic in clearingRoundController.java | Add in new logic to ensure that the correct bids are stored in appropriate arraylist | Yes | 1.5 | 5
34 | 3 | View Courses/sections | Multiple clicks on search button initiates open/close bidding round function | Low | ViewCourse.jsp | Wrong placement of codes in ViewSection.jsp | Reallocated RoundDAO.getCurrentRound() method | Yes | 0.5 | 1
35 | 3 | View timetable | Redirects to error page when user clicks on timetable | High | ViewTimetable.jsp | Wrong placement of codes in ViewTimetable.jsp | Reallocation of codes in ViewTimetable.jsp | Yes | 0.2 | 5
36 | 4 | Update Bid | Unable to update placed bids | High | UpdateBids.jsp | Incorrect logic in updatebids.jsp and update bids controller | Create logic to update context and database | Yes | 1 | 5
37 | 4 | Update Bid | When bidding round is closed, user can still update bids when they shouldn't be able to | High | UpdateBidsController.java; UpdateBids.jsp | No round checker logic when displaying update bids form | Move bid results to View Last Results and don't allow user to update any further | Yes | 0.5 | 5
38 | 4 | View TImetable | In round 2, failed bids are displayed in time table as a pending section | High | ViewTimetable.jsp and ClearingRoundController | Failed bids are not cleared from database when round 1 closes | Clear failed bids from database when round 1 closes | Yes | 0.5 | 5
39 | 4 | Clearing Round 2 | bid.csv records are not cleared when round 1 is closed | High | ClearingRoundController.java | Lack logic to remove bids from bid.csv file | Add logic to clear bid manager. Add code to use bid DAO to clear bid.csv in database | Yes | 0.5 | 5
40 | 4 | Bootstrap | When deploying to OpenShift, context is not cleared when bootstraping for round 1 | High | BoostrapController.java | Attributes were not removed from context. | Add logic to remove context attributes, including all manager attributes | Yes | 0.5 | 5
41 | 4 | Boostrap | After adding the code to remove context attributes, bidding round cannot be opened | High | BootstrapController.java | Attribute "roundInitiated" which was used to check rounds and open round 1 was removed | Add exception to keep "roundInitiated" attribute | Yes | 0.5 | 5
42 | 4 | View Courses/sections | Unable to search for courses when user enters part of the courseID or title | High | ViewCourseServlet.java | Search function is not functioning correctly after making changes to seaching conditions | Edited correctly the changes to the searching conditions | Yes | 0.5 | 5
43 | 5 | All JSON Web Services | Output order is mixed up | Low | JSONBootstrap.java, OpenRoundController.java, ClearingRoundController.java | JSONObject default sorting | Use LinkHashMap instead | Yes | 0.25 | 1
44 | 5 | Clearing Round 2 | Nullpointer exceptions for MinAmtList | High | ClearingRoundController.java, PlaceBidsController.java, UpdateBidsController.java, ViewCurrentBids.jsp, ViewRealTime.jsp | Try to get values based on possibly invalid key (minAmtList.get(key)) | Add in if statement to check if the list contains the key first before retrieving. | Yes | 0.5 | 5
45 | 5 | View Exam Timetable | Only table header displayed when there is no exam details available | Low | ExamTimetable.jsp | No check to validate if SectionStudentManager has been initiated. | Added an if statement to only load the exam timetable if SectionStudentManager has been initiated & the size of the successful bids of a student is > 0 | Yes | 0.25 | 1
46 | 5 | View Real Time | Apache TomCat error page loaded & displayed null pointer | High | ViewRealTime.jsp | The variable used to print the old bid amount was initiated inside the for-loop ie not initiated inside print statement | Initiated the bid amount variable to ouside for-loop | Yes | 0.25 | 5
47 | 5 | View Real Time | When there is no bids made in round 2, user cannot place their first bid via ViewRealTime.jsp. Subsequent bids can be placed | Low | ViewRealTime.jsp | Missing statement to check for size of bidList array list | Add statement to check for size of bidList array list and declare formAction accodingly | Yes | 0.5 | 1
48 | 5 | Update Bid from View Real Time | When user update bids from real time bidding window, the change is not reflected | High | UpdateBidsController.java; | When implementing web service, student object is initiated using the parameters in URL. However, this feature doesn't work when user logs in. | Implement initiation of student object using both URL parameters and session attribute userId | Yes | 0.5 | 5
49 | 5 | Dump Bid | Row number when dumping is that of unfiltered array list | Low | JSONBidDump.java | No variable to keep track of row number of each result set | Add variable to keep track of row number for each result set returned to admin | Yes | 0.5 | 1
50 | 5 | Dump Section | Incorrect error message displayed when entering invalid course/section | High | JSONSectionDump.java | No logic to select correct error message to be populated | Add logic to separate invalid section and invalid course messages | Yes | 0.5 | 1
51 | 5 | Dump Section | Multiple errors messages appear when querying web service | High | JSONSectionDump.java | Incorrect logic in JSONSectionDump.java to process query | Implemented a new set of conditions to process the parameters taken in according to given requirement | Yes | 0.5 | 1
52 | 5 | Dump Bid | Row number does not start from 0 when querying the data of different modules | High | JSONBidDump.java | Did not set the count back to 0 after displaying bids of different module | Implemented a reset process to set the count back to 0 after each query | Yes | 0.5 | 5
53 | 5 | Update Bid, Delete Bid, Drop Section Web Services | Nullpointer exceptions for empty & missing fields in JSON input string | High | UpdateBidsController.java; DeleteBidsController.java; DropSectionsController.java | No validation to check if a particular attribute (e.g. userid) is null | Added if statement to check the particular (e.g. userid) exist in the JSON input String before invoking any method | Yes | 1 | 5
54 | 5 | Update Bid Web Services | Duplicated error message displayed | Low | UpdateBidsController.java | JSON parsing exception was not caught | Added a try catch to contains all the input validations and catch any parsing error to display the correct error message | Yes | 1 | 1
55 | 5 | Bootstrap | Apache null pointer error displayed after boostrap | Low | BootstrapController.java | Page is redirected to /ghjkn/JSONBootstrap | change the url to redirect to /JSONBootstrap | Yes | 0.1 | 1
56 | 5 | View Real Time | Does not get redirected to view bids when user edit bids during round 2 | High | ViewRealTime.jsp | Page is redirected to /ghjkn/stop | Added in new condition to redirect page to view current bids when round is 2 | Yes | 0.25 | 1
57 | 6 | Bootstrap | Clashing Timetable validation error | High | BootstrapController.java | Wrong logic to check for clashing of Exam Timetable and Class Timetable | Change the logic for checking clashing; 4 checks to check for clashing | Yes | 0.75 | 5
58 | 6 | Bootstrap | Invalid bid amount if in decimal place | High | BootstrapController.java | Incorrect substring index of "." for bid amount | Added -1 to get the index of "." of the bid amount | Yes | 0.25 | 5
59 | 6 | Bootstrap | Unable to bid due to incomplete prerequiste even though prerequiste is recorded in database | High | BootstrapController.java | Trimmed attributes are not stored and inserted into database | Overwrite string array row using the trimmed attributes | Yes | 0.25 | 5
60 | 6 | Bootstrap | Exam date more than 8 characters is auto converted to some invalid Date | High | BootstrapController.java | No validations for Date length | Add validations to check if the length of the Date is 8, and also to check whether the Year, Month, Day are valid | Yes | 0.75 | 5
61 | 6 | View Section | User is able to bid for the section but the available slot shown in ViewSection.jsp is zero instead of 1 | Low | ViewSections.jsp | Extra codes that deduct the slots | Remove the for loop that deduct the slots again | Yes | 1 | 1
62 | 7 | Update Bid | JSON Error Message is not displayed in order | High | UpdateBidsController.java | Validation not according to wiki specification | Rearrange validation checks according to wiki | Yes | 2 | 5
63 | 7 | Bootstrap | Invalid code is shown when courseId exist but sectionId does not exist | High | BootstrapController.java | CourseId is only match to Section table | Add validations to check courseId against Course table then against Section table | Yes | 1 | 5
64 | 7 | Bootstrap | School cannot be more than 6 characters | High | BootstrapController.java, BootstrapDAO.java | Data type of school field is set to varchar(6) | Change the data type to varchar(50) | Yes | 0.2 | 5
65 | 7 | Open Round | Round 15 is reflected even though round 2 has been open | High | OpenRoundController.java | Current round is not updated and retrieve after open the round | After opening the round, the current round is updated and stored in context | Yes | 0.25 | 5
66 | 7 | Dump Table | Time is reflected in HHmm format | Low | JSONDump.java | SimpleDateTime format used is HHmm not Hmm | Change time format to Hmm | Yes | 0.1 | 1
67 | 7 | Dump Table | All size and amount reflected in Dump are in String | Low | JSONDump.java | All integers & double are reflected as String | Change the amount and size to double and integer | Yes | 0.1 | 1
68 | 7 | Clearing Round 2 | Available slot is not updated correctly | High | ClearingRoundController.java | SectionList is retrieved from SectionDAO | SectionList is retrieve from context | Yes | 1.5 | 5
69 | 7 | Dump Bid | Incorrect display of attribute name of "bid" | Low | JSONBidDump.java | Typo error | Change "bid" to "bids" | Yes | 0.1 | 1
70 | 7 | Bootstrap | Incorrect section id (S01) is input into database | High | BootstrapController.java | Lack of validation to check for the integer of the section ID | Added an additional check to validate the length of the integer in the section ID and the number accordingly | Yes | 0.5 | 5
71 | 7 | Drop Section | Incorrect message displayed for Drop Section | High | DropSectionsController.java | Incorrect logic to validate input only if there is any blank or missing attribute | Remove extra exclamation mark in the if condition | Yes | 0.2 | 5
72 | 7 | Delete Bid | Incorrect message displayed for Delete Bid | High | DeleteBidsController.java | Incorrect logic to validate input only if there is any blank or missing attribute | Remove extra exclamation mark in the if condition | Yes | 0.2 | 5
73 | 7 | View Bid Status | Extra error message shown when a bid is deleted & no other bids exist | Low | ViewCurrentBids.jsp | Error message is displayed in two different parts of the code | Add in an if-else statement to display the correct error message | Yes | 0.25 | 1
74 | 7 | Drop Section | Section not supposed to be dropped in inactive round | High | ViewTimetable.jsp | Incorrect logic to validate dropping of section in rounds | Added validation to display the drop button only during active round | Yes | 0.2 | 5
75 | 7 | JSON Section Dump | Sections not sorted according to alphabetical order | High | JSONSectionDump.java | Lack of sorting logic to sort the sections retrived from SectionStudent | Implement customized comparator to sort sections | Yes | 0.5 | 5
76 | 7 | JSON Dump | JSON Dump output not sorted according to requirements | High | JSONDump.java | Lack of sorting logic to sort output from JSONDump | Implement customized comparator to sort all output in terms of alphabetical/course code | Yes | 0.5 | 5
77 | 7 | View Real Time Bids | Null pointer exception in Round 2 when there is no bids made by any user | High | ViewRealTime.jsp | Did not catch the exception to display appropriate content | Implements a try catch method to catch the null pointer and display an appropriate paget to the user | Yes | 0.5 | 5
78 | 7 | View Real Time bids | Bid status (in/ out) were not displayed correctly | Low | ViewRealTime.jsp | Bid amount is not correctly compared to get the correct status | Cross check with successfulBids & failedBids list instead to get the correct status | Yes | 0.5 | 1
79 | 7 | View Real Time bids | Bid Status is still in even though bid has been deleted | Low | ViewRealTime.jsp | Bids only deleted from bidList not successful & failed list | Added a check to ensure that for a bid to has status "in" must be in both bidList as well as successful/failed list | Yes | 0.5 | 1