## Sheet1
Iteration 1: 20/05/2013 to 26/05/2013 (7 days)
Tasks | Duration | Start | Finish | Resources
Gather user requirements | 1 day | 2013-05-20 | 2013-05-20 | Team
Research on requirements
Market Research | 6 days | 2013-05-21 | 2013-05-26
Define goals | 1 day | 2013-05-22 | 2013-05-22
Define priorities
Define project scope
Allocate roles and responsibilities
Develop schedule | 4 days | 2013-05-23 | 2013-05-26
Proposal write-up |  |  |  | Roohiya & Priya
Research on technology |  |  |  | Team
Iteration 2: 27/05/2013 to 09/06/2013 (14 days)
Tasks | Duration | Start | Finish | Resources
Define milestones | 1 day | 2013-05-27 | 2013-05-27 | Team
Define deliverables
Use case diagram
Use case Scenario
Account management | 4 days | 2013-05-28 | 2013-05-31 | Hazirah & Saloni
Content Management
Comic Management |  |  |  | Priya & Roohiya
Purchase Management
Search Management |  |  |  | Roohiya & Saraniya
Analytics
Video Management |  |  |  | Priya & Saloni
Notifications Management
confirmation | 1 day | 2013-05-31 | 2013-05-31 | Team
System Sequence Diagram
Account management | 2 days | 2013-06-01 | 2013-06-02 | Hazirah & Saloni
Content Management
Comic Management |  |  |  | Priya & Roohiya
Purchase Management
Search Management |  |  |  | Roohiya & Saraniya
Analytics
Video Management |  |  |  | Priya & Saloni
Notifications Management
confirmation | 1 day | 2013-06-03 | 2013-06-03 | Team
Sequence Diagram
Account management | 2 days | 2013-06-04 | 2013-06-05 | Hazirah & Saloni
Content Management
Comic Management |  |  |  | Priya & Roohiya
Purchase Management
Search Management |  |  |  | Roohiya & Saraniya
Analytics
Video Management |  |  |  | Priya & Saloni
Notifications Management
confirmation | 1 day | 2013-06-06 | 2013-06-06 | Team
Class diagram | 2 days | 2013-06-07 | 2013-06-08
ER Diagram | 1 day | 2013-06-09 | 2013-06-09
Proposal write-up | 7 days | 2013-06-03 | 2013-06-09 | Roohiya & Priya
Iteration 3: 10/06/2013 to 23/06/2013 (14 days)
Tasks | Duration | Start | Finish | Resources
Define parameters for schedule metric | 1 day | 2013-06-10 | 2013-06-10 | Team
Define parameters for bug metric
Risk management
System architecture | 1 day | 2013-06-11 | 2013-06-11
Storyboard (Admin website) | 1 day | 2013-06-12 | 2013-06-12
Storyboard (App) | 1 day | 2013-06-13 | 2013-06-13
Paper Prototype (Admin website) | 2 days | 2013-06-14 | 2013-06-15 | Hazirah
Paper Prototype (App) |  |  |  | Roohiya & Saloni
Confirmation of UI | 1 day | 2013-06-16 | 2013-06-16 | Team
Update UI | 1 day | 2013-06-17 | 2013-06-17
Proposal write-up | 2 days | 2013-06-18 | 2013-06-19 | Priya & Roohiya
Research on technology | 4 days | 2013-06-20 | 2013-06-23 | Team
17
Proposal submission | 1 day | 2013-06-20 | 2013-06-20 | Team
Iteration 4: 24/06/2013 to 07/07/2013 (14 days)
Tasks | Duration | Start | Finish | Resources
Setup database | 1 day | 2013-06-24 | 2013-06-24 | Hazirah
Website layout | 1 day | 2013-06-25 | 2013-06-25 | Priya
Account Management
Website - Login/Logout | 1 day | 2013-06-26 | 2013-06-26 | Hazirah
Website - Create admin | 2 days | 2013-06-27 | 2013-06-28 | Priya
Website - Delete admin | 1 day | 2013-06-29 | 2013-06-29 | Hazirah
Website - Edit admin | 2 days | 2013-06-30 | 2013-07-01 | Priya
App - Login/Logout | 8 days | 2013-06-24 | 2013-07-01 | Roohiya, Saraniya & Saloni
Others
Integration | 2 days | 2013-07-02 | 2013-07-03 | Hazirah & Priya
Testing | 1 day | 2013-07-04 | 2013-07-04 | Akash
Debugging - Website | 3 days | 2013-07-05 | 2013-07-07 | Hazirah & Priya
Debugging - App |  |  |  | Roohiya, Saraniya & Saloni
Buffer | 2 days | 2013-07-08 | 2013-07-09 | -
Iteration 5: 10/07/2013 to 11/08/2013 (33 days)
Tasks | Duration | Start | Finish | Resources
Content Management
Website - Upload comic | 16 days | 2013-07-10 | 2013-07-25 | Hazirah & Priya
Purchase Management
App - Enter purchase details | 16 days | 2013-07-10 | 2013-07-25 | Saloni & Akash
App - Make payment
Comic Management
Connect application to database | 5 days | 2013-07-17 | 2013-07-21 | Saraniya & Roohiya
App - View comic | 10 days | 2013-07-22 | 2013-07-31
Layout
App page layout | 5 days | 2013-08-01 | 2013-08-05 | Saloni
App navigation |  |  |  | Akash
Others
Integration | 2 days | 2013-08-06 | 2013-08-07 | Team
Testing | 1 day | 2013-08-08 | 2013-08-08
Debugging - Website | 3 days | 2013-08-09 | 2013-08-11
Debugging - App
Buffer | 3 days | 2013-08-12 | 2013-08-14 | -
Acceptance
preparation | 5 days | 2013-08-15 | 2013-08-19 | Team
Presentation | 1 day | 2013-08-20 | 2013-08-20 | Team
Iteration 6: 23/08/2013 to 08/09/2013 (8 days)
Tasks | Duration | Start | Finish | Resources
Account Management
Website - Validations (Iteration 4 and 5) | 2 days | 2013-08-23 | 2013-08-24 | Priya
Content Management
Website - View comic details (Details and images) | 2 days | 2013-08-23 | 2013-08-24 | Roohiya
Website - Edit comic details | 2 days | 2013-08-23 | 2013-08-24 | Hazirah
Website - Delete comic by Issue | 2 days | 2013-08-25 | 2013-08-26 | Roohiya
Comic Management
App - Pinch Zoom | 5 days | 2013-08-23 | 2013-08-27 | Saraniya
Purchase Management
App - Google Play Billing | 3 days | 2013-08-23 | 2013-08-25 | Akash
App - Settings (Choose payment mode) | 3 days | 2013-08-26 | 2013-08-28
Video Management
Website - Upload video details | 2 days | 2013-08-25 | 2013-08-26 | Hazirah
App - YouTube | 3 days | 2013-08-29 | 2013-08-30 | Akash
Layout
App - Carousel | 4 days | 2013-08-23 | 2013-08-26 | Saloni
App - Colour for swipe navigation | 2 days | 2013-08-27 | 2013-08-28 | Saloni
App - Enter personal details | 3 days | 2013-08-25 | 2013-08-26 | Priya
App - Browse (Categories) | 3 days | 2013-08-28 | 2013-08-30 | Saraniya
App - Browse (Creator's List) | 3 days | 2013-08-31 | 2013-09-02 | Saraniya
App - Browse (List of Series) | 3 days | 2013-08-27 | 2013-08-29 | Roohiya
App - Browse (Series details) | 3 days | 2013-08-27 | 2013-08-29 | Hazirah
App - What's New (Main layout) | 3 days | 2013-08-27 | 2013-08-29 | Priya
App - What's New (Expandables - Head) | 3 days | 2013-08-28 | 2013-08-30 | Saloni
App - What's New (Expandables - Content) | 4 days | 2013-08-31 | 2013-09-03 | Saloni
Others
Integration | 2 days | 2013-09-04 | 2013-09-05 | Team
Testing | 1 day | 2013-09-06 | 2013-09-06
Debugging - Website | 2 days | 2013-09-07 | 2013-09-08
Debugging - App
Buffer | 2 days | 2013-08-09 | 2013-09-10 | -
Iteration 7: 11/09/2013 to 27/09/2013 (17 days)
Tasks | Duration | Start | Finish | Resources
Deployment 1 | 5 days | 2013-09-11 | 2013-09-15 | AKash
Comic Management
App - Download comic | 3 days | 2013-09-11 | 2013-09-13 | Roohiya
App - View downloaded comic in My Comics | 3 days | 2013-09-14 | 2013-09-16
App - Single touch | 3 days | 2013-09-11 | 2013-09-13 | Saraniya
App - Settings (Choose view mode) | 3 days | 2013-09-11 | 2013-09-13 | Hazirah
Layout
Website - Add cover image | 1 day | 2013-09-14 | 2013-09-14 | Priya
App - Featured | 2 days | 2013-09-15 | 2013-09-16 | Akash
App - What's new | 2 days | 2013-09-14 | 2013-09-15 | Hazirah
App - Comic details (Expandable) | 3 days | 2013-09-14 | 2013-09-16 | Saloni
App - Comic details (Group Header)
App - Comic details (Child Layout 1)
App - Comic details (Child Layout 2)
App - Comic details (Child Layout 3)
App - View comic details | 2 days | 2013-09-15 | 2013-09-16 | Priya
App - Settings (Action bar) | 2 days | 2013-09-17 | 2013-09-18 | Saloni
App - Search | 2 days | 2013-09-14 | 2013-09-15 | Saraniya
Purchase Management
App - Connection between application and datastore | 8 days | 2013-09-15 | 2013-09-22 | Hazirah
App - Send customer Personal details to datastore |  |  |  | Hazirah
Search Management
Website - Add creator and image | 1 day | 2013-09-17 | 2013-09-17 | Akash
Website - View creator and Image | 1 day | 2013-09-18 | 2013-09-18 | Akash
App - Browse (Creator list) | 3 days | 2013-09-15 | 2013-09-17 | Priya
App - Browse (Details) | 3 days | 2013-09-18 | 2013-09-20 | Priya
App - Browse (Rating list) | 2 days | 2013-09-17 | 2013-09-18 | Roohiya
App - Browse (Details) | 3 days | 2013-09-19 | 2013-09-21 | Roohiya
App - Browse (Genre list) | 3 days | 2013-09-16 | 2013-09-18 | Saraniya
App - Browse (Details) | 2 days | 2013-09-19 | 2013-09-20 | Saraniya
Website - Add series image | 1 day | 2013-09-21 | 2013-09-21 | Priya
Website - View and delete series image | 1 days | 2013-09-22 | 2013-09-22 | Roohiya
App - Browse (Series list) | 3 days | 2013-09-19 | 2013-09-21 | Saloni and Akash
App - Browse (Details)
Others
Integration | 3 days | 2013-09-23 | 2013-09-24 | team
Testing | 1 day | 2013-09-25 | 2013-09-25
Debugging - Website | 2 days | 2013-09-26 | 2013-09-27
Debugging - App
Buffer | 2 days | 2013-09-28 | 2013-09-29 | -
User Test 1
Preparation | 1 day | 2013-09-30 | 2013-09-30 | Team
User testing | 1 day | 2013-10-01 | 2013-10-01
Consolidation of feedback
Implement Feedback | 2 days | 2013-10-02 | 2013-10-03
Integration | 1 days | 2013-10-04 | 2013-10-05
Testing | 1 days
Debugging | 1 days
Deployment 2 | 2 days | 2013-10-06 | 2013-10-07 | AKash
Mid-terms
Preparation | 3 days | 2013-10-05 | 2013-10-07 | Team
Presentation | 1 day | 2013-10-08 | 2013-10-08
Iteration 8: 09/10/2013 to 29/10/2013 (21 days)
Tasks | Duration | Start | Finish | Resources
Deployment 3 | 1 day | 2013-10-09 | 2013-10-09 | AKash
Account Management
App - Facebook Login / Logout | 5 days | 2013-10-09 | 2013-10-13 | Saloni
App - Facebook session | 5 days | 2013-10-14 | 2013-10-18
Content Management
Website - Edit comic images | 5 days | 2013-10-09 | 2013-10-13 | Hazirah
Website - Edit creator name | 1 day | 2013-10-09 | 2013-10-09 | Priya
Comic Management
App - Donwload comic | 5 days | 2013-10-19 | 2013-10-23 | Saloni
App - Enhanced viewing Part 1: Zoom into and out of panels | 16 days | 2013-10-09 | 2013-10-24 | Roohiya
Website - Enhanced viewing Part 2: Choose coordinates | 7 days | 2013-10-14 | 2013-10-20 | Hazirah
Purchase Management
App - PayPal | 5 days | 2013-10-09 | 2013-10-13 | Akash
App - In-App Billing | 5 days | 2013-10-14 | 2013-10-18
App - Send purchase details to datastore | 5 days | 2013-10-19 | 2013-10-23
Website - View purchase details | 1 day | 2013-10-24 | 2013-10-24 | Priya
Search Management
App - Search | 8 days | 2013-10-10 | 2013-10-17 | Priya
App - Hardcopy | 5 days | 2013-10-09 | 2013-10-13 | Saraniya
App - Free | 5 days | 2013-10-14 | 2013-10-18
Others
Integration | 2 days | 2013-10-25 | 2013-10-26 | Team
Testing | 1 day | 2013-10-27 | 2013-10-27
Debugging - Website | 2 days | 2013-10-28 | 2013-10-29
Debugging - App
Buffer | 2 days | 2013-10-30 | 2013-10-31 | -
Iteration 9: 01/11/2013 to 24/11/2013 (24 days)
Tasks | Duration | Start | Finish | Resources
Deployment 4 | 1 day | 2013-11-01 | 2013-11-01 | AKash
Comic Management
App - Delete comics | 5 days | 2013-11-01 | 2013-11-05 | Saloni
App - Enhanced viewing Part 3: Connect appt to datastore | 10 days | 2013-11-01 | 2013-11-10 | Roohiya
App - Settings: Choose vewing type | 5 days | 2013-11-11 | 2013-11-15 | Roohiya / Akash
App - Related comics | 5 days | 2013-11-01 | 2013-11-05 | Saraniya
Purchase Management
App - Settings (Edit personal details) | 5 days | 2013-11-06 | 2013-11-10 | Saloni
Website - View customer personal details | 2 days | 2013-11-01 | 2013-11-02 | Priya
Website - View hardcopy order details | 2 days | 2013-11-03 | 2013-11-04 | Priya
Analytics Management
Website - Collate most popular | 5 days | 2013-11-05 | 2013-11-10 | Priya
App - Most popular: Free | 5 days | 2013-11-11 | 2013-11-15 | Hazirah
App - Most popular: Paid |  |  |  | Hazirah
Others
Performance and Touch Up | 2 days | 2013-11-16 | 2013-11-18 | Priya
Integration | 2 days | 2013-11-20 | 2013-11-21 | Team
Testing | 1 day | 2013-11-22 | 2013-11-22
Debugging - Website | 2 days | 2013-10-23 | 2013-11-24
Debugging - App
Buffer | 2 days | 2013-11-25 | 2013-11-26 | -
Deployment 5 | 1 day | 2013-11-25 | 2013-11-26 | AKash
User Test 2
User testing | 1 day | 2013-11-27 | 2013-11-27 | Team
Consolidation of feedback
Implement Feedback | 2 days | 2013-11-28 | 2013-11-29
Integration | 1 day | 2013-11-30 | 2013-11-30
Testing | 1 days | 2013-12-01 | 2013-12-01
Debugging
Final
PreperatioN | 2 days | 2013-12-01 | 2013-12-02 | Team
Finals | 1 day | 2013-12-03 | 2013-12-03