## Schedule Metric
Iteration 1: 20/05/2013 to 26/05/2013 (7 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Gather user requirements | 1 day | 2013-05-20 | 2013-05-20 | 1 day | 2013-05-20 | 2013-05-20 | 100 percent
Research on requirements
Market Research | 6 days | 2013-05-21 | 2013-05-26 | 6 days | 2013-05-21 | 2013-05-26 | 100 percent
Define goals | 1 day | 2013-05-22 | 2013-05-22 | 1 day | 2013-05-22 | 2013-05-22 | 100 percent
Define priorities
Define project scope
Allocate roles and responsibilities
Develop schedule | 4 days | 2013-05-23 | 2013-05-26 | 4 days | 2013-05-23 | 2013-05-26 | 100 percent
Proposal write-up
Research on technology
Schedule Metric: | [7 days (planned) / 7 days (actual)] x 100 = 100 %
Iteration 2: 27/05/2013 to 09/06/2013 (14 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Define milestones | 1 day | 2013-05-27 | 2013-05-27 | 1 day | 2013-05-27 | 2013-05-27 | 100 percent
Define deliverables
Use case diagram
Use case Scenario
Account management | 4 days | 2013-05-28 | 2013-05-31 | 4 days | 2013-05-28 | 2013-05-31 | 100 percent
Content Management
Comic Management
Purchase Management
Search Management
Social Interaction Management
Video Management
confirmation | 1 day | 2013-05-31 | 2013-05-31 | 1 day | 2013-05-31 | 2013-05-31 | 100 percent
System Sequence Diagram
Account management | 2 days | 2013-06-01 | 2013-06-02 | 2 days | 2013-06-01 | 2013-06-02 | 100 percent
Content Management
Comic Management
Purchase Management
Search Management
Social Interaction Management
Video Management
confirmation | 1 day | 2013-06-03 | 2013-06-03 | 1 day | 2013-06-03 | 2013-06-03 | 100 percent
Sequence Diagram
Account management | 2 days | 2013-06-04 | 2013-06-05 | 2 days | 2013-06-04 | 2013-06-05 | 100 percent
Content Management
Comic Management
Purchase Management
Search Management
Social Interaction Management
Video Management
confirmation | 1 day | 2013-06-06 | 2013-06-06 | 1 day | 2013-06-06 | 2013-06-06 | 100 percent
Class diagram | 2 days | 2013-06-07 | 2013-06-08 | 2 days | 2013-06-07 | 2013-06-08 | 100 percent
ER Diagram | 1 day | 2013-06-09 | 2013-06-09 | 1 day | 2013-06-09 | 2013-06-09 | 100 percent
Proposal write-up | 7 days | 2013-06-03 | 2013-06-09 | 7 days | 2013-06-03 | 2013-06-09 | 100 percent
Schedule Metric: | [14 days (planned) / days (actual)] x 100 = 100 %
Iteration 3: 10/06/2013 to 23/06/2013 (14 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Define parameters for schedule metric | 1 day | 2013-06-10 | 2013-06-10 | 1 day | 2013-06-10 | 2013-06-10 | 100 percent
Define parameters for bug metric
Risk management
System architecture | 1 day | 2013-06-11 | 2013-06-11 | 1 day | 2013-06-11 | 2013-06-11 | 100 percent
Storyboard (Admin website) | 1 day | 2013-06-12 | 2013-06-12 | 1 day | 2013-06-12 | 2013-06-12 | 100 percent
Storyboard (App) | 1 day | 2013-06-13 | 2013-06-13 | 1 day | 2013-06-13 | 2013-06-13 | 100 percent
Paper Prototype (Admin website) | 2 days | 2013-06-14 | 2013-06-15 | 2 days | 2013-06-14 | 2013-06-15 | 100 percent
Paper Prototype (App)
Confirmation of UI | 1 day | 2013-06-16 | 2013-06-16 | 1 day | 2013-06-16 | 2013-06-16 | 100 percent
Update UI | 1 day | 2013-06-17 | 2013-06-17 | 1 day | 2013-06-17 | 2013-06-17 | 100 percent
Proposal write-up | 2 days | 2013-06-18 | 2013-06-19 | 2 days | 2013-06-18 | 2013-06-19 | 100 percent
Research on technology | 4 days | 2013-06-20 | 2013-06-23 | 4 days | 2013-06-20 | 2013-06-23 | 100 percent
ProposaL
Proposal submission | 1 day | 2013-06-20 | 2013-06-20 | Team
Schedule Metric: | [14 days (planned) / days (actual)] x 100 = 100 %
Iteration 4: 24/06/2013 to 12/07/2013 (19 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Setup database | 1 day | 2013-06-24 | 2013-06-24 | 1 day | 2013-06-25 | 2013-06-25 | 100 percent
Website layout | 1 day | 2013-06-25 | 2013-06-25 | 1 day | 2013-06-27 | 2013-06-27 | 100 percent
Account Management
Website - Login/Logout | 1 day | 2013-06-26 | 2013-06-26 | 1 day | 2013-06-28 | 2013-06-28 | 66.7 percent
Website - Create admin | 2 days | 2013-06-27 | 2013-06-28 | 2 days | 2013-06-29 | 2013-06-30
Website - Delete admin | 1 day | 2013-06-29 | 2013-06-29 | 1 day | 2013-07-02 | 2013-07-02 | 66.7 percent
Website - Edit admin | 2 days | 2013-06-30 | 2013-07-01 | 2 days | 2013-07-04 | 2013-07-05
App - Login/Logout | 8 days | 2013-06-24 | 2013-07-01 | 8 days | 2013-06-29 | 2013-07-06 | 25 percent
Integration | 2 days | 2013-07-02 | 2013-07-03 | 2 days | 2013-07-07 | 2013-07-08 | 100 percent
Testing | 1 day | 2013-07-04 | 2013-07-04 | 1 day | 2013-07-09 | 2013-07-09 | 100 percent
Debugging - Website | 3 days | 2013-07-05 | 2013-07-07 | 3 days | 2013-07-10 | 2013-07-12 | 100 percent
Debugging - App
Buffer | 2 days | 2013-07-08 | 2013-07-09 | Used up
Schedule Metric: | [14 days (planned) / 19 days (actual)] x 100 = 73.7 %
Action Plan For Iteration 5: | 1. The team did not drop any functions for Iteration 5
2. "Website - Edit Comic Details" Pushed from Iteration 5 to Iteration 6
Iteration 5: 13/07/2013 to 18/08/2013 (37 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Content Management
Website - Upload comic | 16 days | 2013-07-10 | 2013-07-25 | 16 days | 2013-07-13 | 2013-07-28 | 100 percent
Purchase Management
Customer - Enter purchase details | 16 days | 2013-07-10 | 2013-07-25 | Shifted to Iteration 7 |  |  | 100 percent
Customer - Make payment |  |  |  | 16 days | 2013-07-13 | 2013-07-28
Comic Management
Google End Points | 5 days | 2013-07-17 | 2013-07-21 | 7 days | 2013-07-17 | 2013-07-21 | 71.43 percent
APp - View comic (Basic) | 10 days | 2013-07-22 | 2013-07-31 | 10 days | 2013-07-22 | 2013-07-31 | 100 percent
App page layout | 5 days | 2013-08-01 | 2013-08-05 | 5 days | 2013-08-01 | 2013-08-05 | 100 percent
App navigation
Integration | 2 days | 2013-08-06 | 2013-08-07 | 2 days | 2013-08-06 | 2013-08-07 | 66.7 percent
Testing | 1 day | 2013-08-08 | 2013-08-08 | 1 day | 2013-08-08 | 2013-08-08 | 66.7 percent
Debugging - Admin | 3 days | 2013-08-09 | 2013-08-11 | 3 days | 2013-08-09 | 2013-08-11 | 75 percent
Debugging - App
Buffer | 3 days | 2013-08-12 | 2013-08-14 | Used for google end points |  |  | -
Google End Points | - |  |  | 2 days | 2013-08-15 | 2013-08-16 | Please see above
Integration |  |  |  | 1 day | 2013-08-17 | 2013-08-17
Testing and Debugging |  |  |  | 1 day | 2013-08-18 | 2013-08-18
Acceptance
preparation | 5 days | 2013-08-15 | 2013-08-19 | 5 days | 2013-08-15 | 2013-08-19 | 100 Percent
Acceptance | 1 day | 2013-08-20 | 2013-08-20 | 1 day | 2013-08-20 | 2013-08-20 | 100 Percent
Schedule Metric: | [33 days (planned) / 37 days (actual)] x 100 = 89.2 %
Action Plan For Iteration 6: | 1. The team did not drop any functions for Iteration 5
3. "App - Enter personal details" Pushed to Iteration 7
Iteration 6: 23/08/2013 to 08/09/2013 (17 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Account Management
Website - Validations (Iteration 4 and 5) | 2 days | 2013-08-23 | 2013-08-24 | 2 days | 2013-08-23 | 2013-08-24 | 100 Percent
Content Management
Website - View comic details (Details and images) | 2 days | 2013-08-23 | 2013-08-24 | 2 days | 2013-08-23 | 2013-08-24 | 100 Percent
Website - Edit comic details | 2 days | 2013-08-23 | 2013-08-24 | 2 days | 2013-08-23 | 2013-08-24
Website - Delete comic by Issue | 2 days | 2013-08-25 | 2013-08-26 | 2 days | 2013-08-25 | 2013-08-26
Comic Management
App - Pinch Zoom | 5 days | 2013-08-23 | 2013-08-27 | 6 days | 2013-08-23 | 2013-08-28 | 83.3 Percent
Purchase Management
App - Google Play Billing | 3 days | 2013-08-23 | 2013-08-25 | 4 days | 2013-08-23 | 2013-08-26 | 75 Percent
App - Settings (Choose payment mode) | 3 days | 2013-08-26 | 2013-08-28 | 4 days | 2013-08-27 | 2013-08-30 | 75 Percent
Video Management
Website - Upload video details | 2 days | 2013-08-25 | 2013-08-26 | 2 days | 2013-08-25 | 2013-08-26 | 100 Percent
App - YouTube | 3 days | 2013-08-29 | 2013-08-30 | 4 days | 2013-08-30 | 2013-09-03 | 75 Percent
Layout
App - Carousel | 4 days | 2013-08-23 | 2013-08-26 | 11 days | 2013-08-24 | 2013-09-03 | 109.1 Percent
App - Colour for swipe navigation | 2 days | 2013-08-27 | 2013-08-28
App - Enter personal details | 3 days | 2013-08-25 | 2013-08-26
App - Browse (Categories) | 3 days | 2013-08-28 | 2013-08-30
App - Browse (Creator's List) | 3 days | 2013-08-31 | 2013-09-02
App - Browse (List of Series) | 3 days | 2013-08-27 | 2013-08-29
App - Browse (Series details) | 3 days | 2013-08-27 | 2013-08-29
App - What's New (Main layout) | 3 days | 2013-08-27 | 2013-08-29
App - What's New (Expandables - Head) | 3 days | 2013-08-28 | 2013-08-30
App - What's New (Expandables - Content) | 4 days | 2013-08-31 | 2013-09-03
Others
Integration | 2 days | 2013-09-04 | 2013-09-05 | 2 days | 2013-09-04 | 2013-09-05 | 100 Percent
Testing | 1 day | 2013-09-06 | 2013-09-06 | 1 day | 2013-09-06 | 2013-09-06
Debugging - Website | 2 days | 2013-09-07 | 2013-09-08 | 2 days | 2013-09-07 | 2013-09-08
Debugging - App
Schedule Metric: | [17 days (planned) / 17 days (actual)] x 100 = 100 %
Action Plan For Iteration 6: | The team is on time
Iteration 7: 09/09/2013 to 27/09/2013 (19 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
Deployment 1 | 5 days | 2013-09-09 | 2013-09-13 | 5 days | 2013-09-11 | 2013-09-15 | 100 Percent
Comic Management
App - Download comic | 3 days | 2013-09-09 | 2013-09-11 | 3 days | 2013-09-09 | 2013-09-11 | 100 Percent
App - View downloaded comic in My Comics | 3 days | 2013-09-12 | 2013-09-14 | 3 days | 2013-09-12 | 2013-09-14
App - Single touch | 3 days | 2013-09-09 | 2013-09-11 | 3 days | 2013-09-09 | 2013-09-11
Layout
Website - Add cover image | 1 day | 2013-09-12 | 2013-09-12 | 2 days | 2013-09-12 | 2013-09-13 | 50 Percent
App - Featured | 2 days | 2013-09-13 | 2013-09-14 | 9 days | 2013-09-13 | 2013-09-21 | 44.44 Percent
App - What's new | 2 days | 2013-09-12 | 2013-09-13
App - Comic details (Expandable) | 3 days | 2013-09-12 | 2013-09-14
App - Comic details (Group Header)
App - Comic details (Child Layout 1)
App - Comic details (Child Layout 2)
App - Comic details (Child Layout 3)
App - View comic details | 2 days | 2013-09-13 | 2013-09-14
App - Settings (Action bar) | 2 days | 2013-09-15 | 2013-09-16
App - Search | 2 days | 2013-09-12 | 2013-09-13
Purchase Management
App - Connection between application and datastore | 8 days | 2013-09-15 | 2013-09-22 | 11 days | 2013-09-15 | 2013-09-25 | 72.72 Percent
App - Send customer Personal details to datastore
Search Management
Website - Add creator and image | 1 day | 2013-09-15 | 2013-09-15 | 1 day | 2013-09-15 | 2013-09-15 | 100 Percent
Website - View creator and Image | 1 day | 2013-09-16 | 2013-09-16 | 1 day | 2013-09-16 | 2013-09-16 | 100 Percent
App - Browse (Creator list) | 6 days | 2013-09-13 | 2013-09-18 | 7 days | 2013-09-13 | 2013-09-19 | 86 Percent
App - Browse (Details)
App - Browse (Rating list) | 5 days | 2013-09-15 | 2013-09-19 | 3 days | 2013-09-15 | 2013-09-17 | 167 Percent
App - Browse (Details)
App - Browse (Genre list) | 5 days | 2013-09-14 | 2013-09-18 | 7 days | 2013-09-14 | 2013-09-20 | 71 Percent
App - Browse (Details)
Website - Add series image | 1 day | 2013-09-19 | 2013-09-19 | 1 day | 2013-09-19 | 2013-09-19 | 100 Percent
Website - View and delete series image | 1 days | 2013-09-20 | 2013-09-20 | 1 days | 2013-09-20 | 2013-09-20 | 100 Percent
App - Browse (Series list) | 3 days | 2013-09-17 | 2013-09-21 | 4 days | 2013-09-17 | 2013-09-22 | 75 Percent
App - Browse (Details)
Others
Integration | 3 days | 2013-09-22 | 2013-09-22 | 2 days | 2013-08-23 | 2013-09-24 | 100 Percent
Testing | 1 day | 2013-09-23 | 2013-09-23 | 1 day | 2013-09-25 | 2013-09-25
Debugging - Website | 2 days | 2013-09-24 | 2013-09-25 | 2 days | 2013-09-26 | 2013-09-27
Debugging - App
Buffer | 2 days | 2013-09-24 | 2013-09-25 | Used for google end points |  |  | -
Schedule Metric: | [17 days (planned) / 19 days (actual)] x 100 = 89.5 %
Action Plan For Iteration 7: | The team was able to completed the Iteration with buffer days hence no action taken
User Test 1: 30/09/2013 to 07/10/2013 (19 days)
Tasks | Planned Duration | Planned Start | Planned Finish | Actual duration | Actual Start | Actual Finish | Performance
User Test 1
Preparation | 1 day | 2013-09-30 | 2013-09-30 | 2 days | 2013-09-30 | 31/09/2013 | 50 Percent
User testing | 1 day | 2013-10-01 | 2013-10-01 | 2 days | 2013-10-01 | 2013-10-02
Consolidation of feedback
Implement Feedback | 2 days | 2013-10-02 | 2013-10-03 | 3 days | 2013-10-03 | 2013-10-05 | 67 Percent
Integration | 2 days | 2013-10-04 | 2013-10-05 | 2 days | 2013-10-06 | 2013-10-07 | 100 Percent
Testing
Debugging