## Dashboard
Bug Summary | [6 empty] | Bug Prioritisation
Iteration | Low | High | Critical | Total bugs found | Total Score | Action Taken | Severity | Score | Description | Y
1 | 0 | 0 | 0 | 0 | 0 | - | Low | 1 | Unimportant. Typo error or small user interface alignment issues. | N
2 | 0 | 0 | 0 | 0 | 0 | - | High | 5 | The system runs. However, some non-critical functionalities are not working.
3 | 0 | 0 | 0 | 0 | 0 | - | Critical | 10 | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
4 | 2 | 2 | 0 | 4 | 12 | Fix Bugs during the planned debugging time
5 | 4 | 1 | 0 | 5 | 9 | ? | Mitigation Plan
6 |  |  |  | 0 | 0 | ? | Total Bug Score | Action
7 |  |  |  | 0 | 0 |  | Score < 10 | Fix Bugs during the planned debugging time
8 |  |  |  | 0 | 0 |  | Score >= 10 | Stop all developments. All members contribute to resolve the bug urgently. PM have to re-schdule the next iteration if necessary.
9 |  |  |  | 0 | 0
10 |  |  |  | 0 | 0
11 |  |  |  | 0 | 0

## Iter 4
S/N | Bug Description | Module | Impact | Score | Date Found | Found by | Resolved? | Resolved by | Date Resolved
1 | The view controllers doesn't link properly (e.g. icons not responding) | Onboarding | Low | 1 | 2014-12-29 | Teng | Y | Teng | 2015-01-09
2 | Push of data doesn't work | Onboarding | High | 5 | 2014-12-29 | Teng | Y | Teng | 2015-01-09
3 | Data is not properly passed from FirstViewController to the SecondViewController | Onboarding | High | 5 | 2014-12-29 | Teng | Y | Teng | 2015-01-10
4 | Words go out of screen if name is too long | Onboarding | Low | 1 | 2015-01-01 | Teng | Y | Teng | 2015-01-10

## Iter 5
S/N | Bug Description | Module | Impact | Score | Date Found | Found by | Resolved? | Resolved by | Date Resolved
1 | Application crashes when background is being tapped on after the email is keyed in | Onboarding | High | 5 | 2015-02-08 | Zhizhong | Y | Teng | 2015-02-08
2 | Null pointer when user has a period start date but do not have a period end date | Period Tracker | Low | 1 | 2015-02-08 | Zhizhong | Y | Terence | 2015-02-10
3 | Unable to save symptoms | Period Tracker | Low | 1 | 2015-02-08 | Zhizhong | Y | Terence | 2015-02-10
4 | Runtime error when back button is pressed from symptoms page | Period Tracker | Low | 1 | 2015-02-08 | Zhizhong | Y | Terence | 2015-02-10
5 | Null pointer when user press 'Period started' | Period Tracker | Low | 1 | 2015-02-08 | Zhizhong | Y | Terence | 2015-02-10
6 | Fertile Start Day wrong | Period Tracker | Low | 1 | 2015-02-10 | Zhizhong | Y | Terence | 2015-02-10
7 | Fertile End Day wrong | Period Tracker | Low | 1 | 2015-02-10 | Zhizhong | Y | Terence | 2015-02-10

## Iter 6
S/N | Bug Description | Module | Impact | Score | Date Found | Found by | Resolved? | Resolved by | Date Resolved
1 | Period Stage but show 'Have your period started?' | Period Tracker | Low | 1 | 2015-02-14 | Zhizhong | Y | Terence | 2015-02-14
2 | PMS start date wrong | Period Tracker | Low | 1 | 2015-02-14 | Zhizhong | Y | Terence | 2015-02-14
3 | Press 'End' but still 'Have period end' | Period Tracker | Low | 1 | 2015-02-14 | Zhizhong | Y | Terence | 2015-02-14
4 | Period did not auto end after 5 days from forecast | Period Tracker | Low | 1 | 2015-02-14 | Zhizhong | Y | Terence | 2015-02-14
5 | Unable to scroll down to contact number when editing last name | Profile | High | 5 | 2015-02-15 | Zhizhong | N

## Iter 7
S/N | Bug Description | Module | Impact | Score | Date Found | Found by | Resolved? | Resolved by | Date Resolved
1