## Schedule (New)
SPRINT NO | Task ID |  | Module | DESCRIPTION | ESTIMATED TIME TAKEN | HOURS SPENT ACTUAL | STORY POINTS | STATUS | TAKEN BY
1 | 1 |  | - | Finalize Project Scope | 2 | 1.5 | 2 | Completed
1 | 2 |  |  | Use Case Diagram | 2 | 2 | 2 | Completed
1 | 3 |  |  | ER Diagram | 2 | 3 | 2 | Completed
1 | 4 |  |  | As-Is Diagram | 0.5 | 0.5 | 0.5 | Completed
1 | 5 |  |  | To-Be Diagram | 1 | 1.5 | 1 | Completed
1 | 6 |  |  | Navigation Diagram - Web App | 3.5 | 5 | 3.5 | Completed
1 | 7 |  |  | Navigation Diagram - Mobile App | 4 | 3.5 | 4 | Completed
1 | 8 |  |  | Lo-Fi Wireframing - Admin Web App | 5 | 6 | 5 | Completed
1 | 9 |  |  | Lo-Fi Wireframing - Mobile App | 6 | 6 | 6 | Completed
1 | 10 |  |  | Technical Research-React Native | 3 | 5 | 3 | Completed
1 | 11 |  |  | Technical Research-Nodejs | 3 | 4 | 3 | Completed
2 | 1 | Web App | Web Admin Module (Backend) | WebApp - Login/Logout | 2 | 4 | 2 | Completed
2 | 2 |  |  | WebApp - Change Password | 1 | 1 | 1 | Completed
2 | 3 |  | Web Admin Module (Frontend) | WebApp - Login/Logout | 2 | 4 | 2 | Completed
2 | 4 |  |  | WebApp - Change Password | 1 | 1 | 1 | Completed
2 | 5 | Nodejs | App Account Module (Backend) | MobileApp - Login | 4 | 4 | 4 | Completed
2 | 6 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3 | Completed
2 | 7 | Android | App Account Module (Frontend) | MobileApp - Login | 4 | 4 | 4 | Completed
2 | 8 |  |  | MobileApp - Auto-Login (Session) | 3 | 5 | 3 | Completed
2 | 9 |  | - | Scenario | 1 | 0.5 | 1 | Completed
2 | 10 |  |  | Persona | 1 | 0.5 | 1 | Completed
2 | 11 |  |  | Git and Viroreact set-up | 0.5 | 0.5 | 0.5 | Completed
2 | 12 |  |  | Proposal Preparation | 2 | 2 | 2 | Completed
3 | 1 | Nodejs | App Account Module (Backend) | MobileApp - Connect to Trail | 0.5 | 0.5 | 0.5 | Completed
3 | 2 |  |  | MobileApp - View Narrative | 1 | 0.75 | 1 | Completed
3 | 3 |  |  | MobileApp - Complete Missions(Quiz, Wefie) | 2 | 3 | 2 | Completed
3 | 4 |  |  | MobileApp -View Past Submissions | 4 | 5 | 4 | Completed
3 | 5 |  |  | MobileApp - Upload Submissions | 1 | 2.5 | 1 | Completed
3 | 6 |  |  | MobileApp - View map with pinned location(with location tracking) | 3.5 | 3 | 3.5 | Completed
3 | 7 | Android | App Account Module (Frontend) | MobileApp -Connect to Trail | 1 | 0.5 | 1 | Completed
3 | 8 |  |  | MobileApp - View Narrative | 0.5 | 0.5 | 0.5 | Completed
3 | 9 |  |  | MobileApp - Complete Missions(Quiz, Wefie) | 2 | 3 | 2 | Completed
3 | 10 |  |  | MobileApp - View Past Submissions | 4 | 3 | 4 | Completed
3 | 11 |  |  | MobileApp - Upload Submissions | 3 | 2 | 3 | Completed
3 | 12 |  |  | MobileApp -View map with pinned location(with location tracking) | 2 | 1 | 2 | Completed
3 | 13 |  | - | MobileApp - Sequence Diagrams | 0.5 | 0.5 | 0.5 | Completed
3 | 14 |  |  | WebApp - Sequence Diagram | 1 | 1 | 1 | To Be Done
3 | 15 |  |  | User Testing Preparation | 1.5 | 2 | 1.5 | Completed
3 | 16 |  |  | Acceptance Preparation | 3 | 3 | 3 | Completed
B
4 | 1 | WebApp | Admin Trail Monitoring Module (Backend) | WebApp - Monitor Groups' Progress | 0.5 | 0 | 0.5 | To Be Done
4 | 2 |  |  | WebApp - Monitor Groups' Location | 2 | 0 | 2 | To Be Done
4 | 3 |  |  | WebApp - Monitor and manage Leaderboard | 0.5 | 0.5 | 0.5 | Completed
4 | 4 |  |  | WebApp - Monitor and manage Activity Feed | 1.5 | 0 | 1.5 | To Be Done
4 | 5 |  |  | WebApp - Monitor and manage Mission Submission | 1 | 1 | 1 | Completed
4 | 6 |  |  | WebApp - Monitor Trail Duration | 1.5 | 1.5 | 1.5 | Completed
4 | 7 |  | Admin Upload Module Backend | WebApp - Upload Multimedia (Images and Videos) | 2.5 | 2.5 | 2.5 | Completed
4 | 8 |  |  | WebApp - View Uploads | 2 | 2 | 2 | Completed
4 | 9 |  | Admin Trail Monitoring Module Frontend | WebApp - Monitor Groups' Progress | 1 | 0 | 1 | To Be Done
4 | 10 |  |  | WebApp - Monitor Groups' Location | 2.5 | 0 | 2.5 | To Be Done
4 | 11 |  |  | WebApp - Monitor and manage Leaderboard | 1 | 1 | 1 | Completed
4 | 12 |  |  | WebApp - Monitor and manage Activity Feed | 1 | 0 | 1 | To Be Done
4 | 13 |  |  | WebApp - Monitor and manage Mission Submission | 1.5 | 1.5 | 1.5 | Completed
4 | 14 |  |  | WebApp - Monitor Trail Duration | 1 | 1 | 1 | Completed
4 | 15 |  | Admin Upload Module Frontend | WebApp - Upload Multimedia (Images and Videos) | 0.5 | 0.5 | 0.5 | Completed
4 | 16 |  |  | WebApp - View Uploads | 1.5 | 1.5 | 1.5 | Completed
4 | 17 | Android | User Trail Module (Frontend) | MobileApp - View Activity Feed | 1.5 | 1.5 | 1.5 | Completed
4 | 18 |  |  | MobileApp - View Leaderboard | 1 | 1 | 1 | Completed
4 | 19 |  | User Trail Module (Backend) | MobileApp - View Activity Feed | 2 | 2 | 2 | Completed
4 | 20 |  |  | MobileApp - View Leaderboard | 1 | 1 | 1 | Completed
5 | 1 | Web App | Admin Trail Monitoring Module (Backend) | WebApp - Monitor Groups' Progress | 0.5 |  | 0.5 | To Be Done
5 | 2 |  |  | WebApp - Monitor Groups' Location | 2 |  | 2 | To Be Done
5 | 3 |  |  | WebApp - Monitor and manage Activity Feed | 1.5 |  | 1.5 | To Be Done
5 | 4 |  | Admin Trail Monitoring Module (Front end) | WebApp - Monitor Groups' Progress | 1 |  | 0.5 | To Be Done
5 | 5 |  |  | WebApp - Monitor Groups' Location | 2.5 |  | 2 | To Be Done
5 | 6 |  |  | WebApp - Monitor and manage Activity Feed | 1 |  | 1.5 | To Be Done
5 | 7 |  | Hotspot Module (Backend) | WebApp - Add/Edit/Remove Hotspot Location | 0.5 |  | 0.5 | To Be Done
5 | 8 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 0.5 |  | 0.5 | To Be Done
5 | 9 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 0.5 |  | 0.5 | To Be Done
5 | 10 |  | Hotspot Module (Frontend) | WebApp - Add/Edit/Remove Hotspot Location | 1 |  | 1 | To Be Done
5 | 11 |  |  | WebApp - Add/Edit/Remove Description of Hotspot | 1 |  | 1 | To Be Done
5 | 12 |  |  | WebApp - Add/Edit/Remove Photo of hotspot | 1.5 |  | 1.5 | To Be Done
5 | 13 | IOS | App Account Module (Backend) | MobileApp - Login | 4 |  | 4 | To Be Done
5 | 14 |  |  | MobileApp - Auto-Login (Session) | 3 |  | 3 | To Be Done
5 | 15 |  | App Account Module (Frontend) | MobileApp - Login | 4 |  | 4 | To Be Done
5 | 16 |  |  | MobileApp - Auto-Login (Session) | 3 |  | 3 | To Be Done
6 | 7 |  | Narrative Module (Backend) | WebApp - Add/Edit/Remove Text/Story | 1.25 |  | 1.25 | To Be Done
6 | 8 |  |  | WebApp - Attach photos or videos to Narrative | 2 |  | 2 | To Be Done
6 | 9 |  | Narrative Module (Frontend) | WebApp - Add/Edit/Remove Text/Story | 1 |  | 1 | To Be Done
6 | 10 |  |  | WebApp - Attach photos or videos to Narrative | 2.5 |  | 2.5 | To Be Done
6 | 11 | Nodejs | Complete Mission Module (Backend) | MobileApp - Drag and Drop | 2 |  | 2 | To Be Done
6 | 12 |  |  | MobileApp - CrossWord | 1.5 |  | 1.5 | To Be Done
6 | 13 | Android | Complete Mission Module (Frontend) | MobileApp - Drag and Drop | 1 |  | 1 | To Be Done
6 | 14 |  |  | MobileApp - CrossWord | 2.5 |  | 2.5 | To Be Done
6 | 15 | IOS | User Trail Module (Backend) | Connect to Trail | 0.5 |  | 0.5 | To Be Done
6 | 16 |  |  | View Narrative | 2 |  | 2 | To Be Done
6 | 17 |  |  | Complete Missions(Quiz, Wefie) | 0.5 |  | 0.5 | To Be Done
6 | 18 |  |  | View Past Submissions | 1.5 |  | 1.5 | To Be Done
6 | 19 |  |  | Upload Submissions | 1 |  | 1 | To Be Done
6 | 20 |  |  | View map with pinned location(with location tracking) | 1.5 |  | 1.5 | To Be Done
6 | 21 |  | User Trail Module (Frontend) | Connect to Trail | 1 |  | 1 | To Be Done
6 | 22 |  |  | View Narrative | 2.5 |  | 2.5 | To Be Done
6 | 23 |  |  | Complete Missions(Quiz, Wefie) | 1 |  | 1 | To Be Done
6 | 24 |  |  | View Past Submissions | 1 |  | 1 | To Be Done
6 | 25 |  |  | Upload Submissions | 1.5 |  | 1.5 | To Be Done
6 | 26 |  |  | View map with pinned location(with location tracking) | 1 |  | 1 | To Be Done
7 | 1 | Web App | Mission Module (Backend) | WebApp - Add/Edit/Remove mission description | 1 |  | 1 | To Be Done
7 | 2 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 |  | 2 | To Be Done
7 | 3 |  | Mission Module (Frontend) | WebApp - Add/Edit/Remove mission description | 1.5 |  | 1.5 | To Be Done
7 | 4 |  |  | WebApp - Add/Edit/Remove mission type: - Quiz - Wefie - Drag & Drop | 2 |  | 2 | To Be Done
7 | 5 |  | Admin Trail Creation Module (Backend) | WebApp - Add Trail Info | X |  | X | To Be Done
7 | 6 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 0.5 |  | 0.5 | To Be Done
7 | 7 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 0.5 |  | 0.5 | To Be Done
7 | 8 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 0.5 |  | 0.5 | To Be Done
7 | 9 |  |  | WebApp - Add/Edit/Remove Participants | X |  | X | To Be Done
7 | 10 |  |  | WebApp - Add/Edit/Remove Groups | 0.5 |  | 0.5 | To Be Done
7 | 11 |  | Admin Trail Creation Module (Frontend) | WebApp - Add Trail Info | X |  | X | To Be Done
7 | 12 |  |  | WebApp - Add/Edit/Remove Hotspots to trail map | 1 |  | 1 | To Be Done
7 | 13 |  |  | WebApp - Add/Edit/Remove Narrative to trail map | 1 |  | 1 | To Be Done
7 | 14 |  |  | WebApp - Add/Edit/Remove Mission to trail map | 1 |  | 1 | To Be Done
7 | 15 |  |  | WebApp - Add/Edit/Remove Participants | X |  | X | To Be Done
7 | 16 |  |  | WebApp - Add/Edit/Remove Groups | 1 |  | 1 | To Be Done
7 | 17 | Nodejs | Mission Module (Backend) | MobileApp - Complete missions - Word Search - Anagram - Drawing | 2.5 |  | 2.5 | To Be Done
7 | 18 | Android | Mission Module (Frontend) | MobileApp - Complete missions - Word Search - Anagram - Drawing | 2 |  | 2 | To Be Done
7 | 19 | IOS | User Trail Module (Backend) | View Activity Feed |  |  |  | To Be Done
7 | 20 |  |  | View Leaderboard |  |  |  | To Be Done
7 | 21 |  | User Trail Module (Frontend) | View Activity Feed
7 | 22 |  |  | View Leaderboard
7 | 23 | Others | - | User Testing Preparation
8 | 1 | Web App | Notification Module (Backend) | WebApp - Announcer Feature | 2.5 |  | 2.5
8 | 2 |  |  | WebApp - Reminder Feature | 2 |  | 2
8 | 3 |  | Feedback Module (Backend) | WebApp - Collate and generate feedback report | .1.5 |  | .1.5
8 | 4 |  | Notification Module (Frontend) | WebApp - Announcer Feature | 1 |  | 1
8 | 5 |  |  | WebApp - Reminder Feature | 1 |  | 1
8 | 6 |  | Feedback Module (Frontend) | WebApp - Collate and generate feedback report | 2 |  | 2
8 | 7 | Nodejs | Notification Module (Backend) | MobileApp - View Notification | 2 |  | 2
8 | 8 |  |  | MobileApp - Receive Notification | 1.5 |  | 1.5
8 | 9 |  | Feedback Module (Backend) | MobileApp - Feedback form submission | 1 |  | 1
8 | 10 | Android | Notification Module (Frontend) | MobileApp - View Notification | 1.5 |  | 1.5
8 | 11 |  |  | MobileApp - Receive Notification | 2 |  | 2
8 | 12 |  | Feedback Module (Frontend) | MobileApp - Feedback form submission | 1.5 |  | 1.5
8 | 13 | IOS | Complete Mission Module (Backend) | MobileApp - Complete missions - Drag & Drop - Crossword
8 | 14 | IOS | Complete Mission Module (Frontend) | MobileApp - Complete missions - Drag & Drop - Crossword
9 | 1 | Web App | Mission Module (Backend) | MobileApp - Complete missions - Word Search - Anagram - Drawing - Crossword | 1 |  | 1
9 | 2 |  | Mission Module (Frontend) | MobileApp - Complete missions - Word Search - Anagram - Drawing - Crossword | 1 |  | 1
9 | 3 | IOS | Mission Module (Backend) | MobileApp - Complete missions - Word Search - Anagram - Drawing | 2 |  | 2
9 | 4 |  | Mission Module (Frontend) | MobileApp - Complete missions - Word Search - Anagram - Drawing - Crossword | 3 |  | 3
10 | 1 | Web App | Usability Module (Backend) | WebApp - Admin Help Page | 3 |  | 3
10 | 2 |  | Usability Module (Frontend) | WebApp - Admin Help Page | 3 |  | 3
10 | 3 | Nodejs | Usability Module (Backend) | MobileApp - User Help Page | 3 |  | 3
10 | 4 | Android | Usability Module (Frontend) | MobileApp - User Help Page | 3 |  | 3
10 | 5 | IOS | Notification Module (Backend) | MobileApp - View Notification | 1.5 |  | 1.5
10 | 6 |  |  | MobileApp - Receive Notification | 2 |  | 2
10 | 7 |  | Feedback Module (Backend) | MobileApp - Feedback form submission | 1.5 |  | 1.5
10 | 8 |  | Usability Module (Backend) | MobileApp - User Help Page | 3 |  | 3
10 | 9 |  | Notification Module (Frontend) | MobileApp - View Notification
10 | 10 |  |  | MobileApp - Receive Notification | 2 |  | 2
10 | 11 |  | Feedback Module (Frontend) | MobileApp - Feedback form submission | 1.5 |  | 1.5
10 | 12 |  | Usability Module (Frontend) | MobileApp - User Help Page | 3 |  | 3
10 | 13 |  | - | User Testing Preparation | 3 |  | 3
10 | 14 |  | - | MidTerm Preparation | 4 |  | 4
11 | 1 | Web App | Additional Game - Mini Hotspots (Backend) | WebApp - Add/Edit/Remove Mini Hotspots | 1 |  | 1
11 | 2 |  |  | WebApp - Add/Edit/Remove Narrative to mini hotspot | 1 |  | 1
11 | 3 |  | Additional Game - Mini Hotspots (Frontend) | WebApp - Add/Edit/Remove Mini Hotspots | 1.5 |  | 1.5
11 | 4 |  |  | WebApp - Add/Edit/Remove Narrative to mini hotspot | 1.5 |  | 1.5
11 | 5 | Others | - | MIDTERM
12 | 1 | Web App | Additional Trail Modes (Backend) | UI Improvement (Webapp, MobileApp) | 1 |  | 1
12 | 2 |  | Additional Trail Modes (Frontend) | Debugging | 2 |  | 2
12 | 3 | Nodejs | Additional AR implementation (Backend) | Optimization | 3 |  | 3
13 | 1 |  | - | UI Improvement (Webapp, MobileApp) | 10 |  | 10
13 | 2 |  | - | Debugging | 5 |  | 5
13 | 3 |  |  | Poster Preparation
14 | 1 |  | - | Documentation Review | 3 |  | 3
14 | 2 |  | - | Preparation for Project Handover | 4 |  | 4
14 | 3 |  | - | FINAL PRESENTATION PREPARATION | 5 |  | 5
15 | 1 |  | - | Preparation for Final Presentation | 4 |  | 4

## Metrics(NEW)
Product Burndown
Sprint | Estimated Story Points | Actual Story Points Completed | Story Points Remaining |  | Sprint | Estimated Story Points | Actual Story Points Completed | Story Points Remaining
0 | 287.75 | 0 | 287.75 |  | 0 | #REF! | 0 | #REF!
1 | 255.75 | 32 | 255.75 |  | 1 | #REF! | #REF! | #REF!
2 | 231.25 | 24.5 | 231.25 |  | 2 | #REF! | #REF! | #REF!
3 | 200.75 | 29.5 | 201.75 |  | 3 | #REF! | #REF! | #REF!
4 | 173.75 | 18.5 | 183.25 |  | 4 | #REF! | #REF! | #REF!
5 | 146.75 | 0 | 183.25 |  | 5 | #REF! | #REF! | #REF!
6 | 118 | 0 | 183.25 |  | 6 | #REF! | #REF! | #REF!
7 | 101 | 0 | 183.25 |  | 7 | #REF! | #REF! | #REF!
8 | 83 | 0 | 183.25 |  | 8 | #REF! | #REF! | #REF!
9 | 76 | 0 | 183.25 |  | 9 | #REF! | #REF! | #REF!
10 | 42.5 | 0 | 183.25 |  | 10 | #REF! | #REF! | #REF!
11 | 37.5 | 0 | 183.25 |  | 11 | #REF! | #REF! | #REF!
12 | 31.5 | 0 | 183.25 |  | 12 | #REF! | #REF! | #REF!
13 | 16.5 | 0 | 183.25 |  | 13 | #REF! | #REF! | #REF!
14 | 4.5 | 0 | 183.25 |  | 14 | #REF! | #REF! | #REF!
15 | 0.5 | 0 | 183.25
Sprint | Story Points Completed
0 | 0
1 | 32
2 | 24.5
3 | 29.5
4 | 18.5
5 | 0
6 | 0
7 | 0
8 | 0
9 | 0
10 | 0
11 | 0
12 | 0
13 | 0
14 | 0
15 | 0
Average | 6.5312
Rolling Avg. | 18.8333
Bug Metric
Iteration No. | Low | High | Critical | Bug Score
1 | 0 | 0 | 0 | 0
2 | 0 | 0 | 0 | 0
3 | 1 | 3 | 1 | 26
4 | 0 | 0 | 0 | 0
5
6
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Config
To Be Done
In Progress
To Be Reviewed
Completed

## Bugs
Bugs
1 | Submission lags and app clashes | Critical Level
2 | Start Selfie instead of start quiz | Low Level
3 | Missing Narrative | High Impact
4 | Blank Map | High Impact
5 | Narrative and Buttons Misaligned | High Impact