## Sheet1
Task Name | Scheduled Duration | Scheduled Start Date | Scheduled End Date | In-Charge | Actual Start Date | Actual End Date | Actual Duration | Actual Duration/ Scheduled Duration | Remarks
Preparation
Meetings
Team Meeting 1 | - | 2014-05-20 | - | All | 2014-05-20 | - | -
Team Meeting 2 | - | 2014-05-24 | - | All | 2014-05-24 | - | -
Client Meeting 1 | - | 2014-06-07 | - | All | 2014-06-07 | - | -
Team Meeting 3 | - | 2014-06-07 | - | All | 2014-06-07 | - | -
Client Meeting 2 | - | 2014-06-14 | - | All | 2014-06-14 | - | -
Team Meeting 4 | - | 2014-06-14 | - | All | 2014-06-14 | - | -
Team Meeting 5 | - | 2014-06-15 | - | All | 2014-06-15 | - | -
Team Meeting 6 | - | 2014-06-18 | - | All | 2014-06-18 | - | -
18/6/2014: Milestone 1 - Proposal Submission
Iteration 1 | 16 | 2014-06-19 | 2014-07-07 |  | 2014-06-19 | 2014-07-07 | 16
Meetings
Team Meeting 1 | - | 2014-06-19 | - | All | 2014-06-19 | - | -
Planning
Use Case | 2 | 2014-06-19 | 2014-06-20 | Surya | 2014-06-19 | 2014-06-20 | 2 | 1
Sequence Diagram | 3 | 2014-06-19 | 2014-06-21 | Jessica | 2014-06-19 | 2014-06-21 | 3 | 1
Schedule | 5 | 2014-06-19 | 2014-06-24 | Jia Ying | 2014-06-19 | 2014-06-25 | 6 | 1.2
Bug Metrics | 1 | 2014-06-25 | 2014-06-25 | Jia Ying | 2014-06-27 | 2014-06-27 | 1 | 1 | Delayed by schedule
Design
Lo-Fi Prototype | 5 | 2014-06-19 | 2014-06-24 | Shirley | 2014-06-19 | 2014-06-25 | 6 | 1.2 | Change of design
Login/ Logout | 2 | 2014-06-23 | 2014-06-25 | Jessica | 2014-06-23 | 2014-06-25 | 2 | 1
Register (Personal Details) | 3 | 2014-06-21 | 2014-06-24 | Surya | 2014-06-21 | 2014-06-23 | 2 | 0.66667
Integration, Testing | 3 | 2014-06-26 | 2014-06-28 | Jessica, Surya | 2014-06-26 | 2014-06-28 | 3 | 1
Debugging | 3 | 2014-06-30 | 2014-07-02 | Jessica, Surya | 2014-06-30 | 2014-07-02 | 3 | 1
Buffer | 3 | 2014-07-03 | 2014-07-07 | - | 2014-07-03 | 2014-07-07 | 3 | 1
Iteration 2 | 16 | 2014-07-08 | 2014-07-25 |  | 2014-07-08 | 2014-07-25 | 16 | 1
Meetings
Team Meeting 1 | - | 2014-07-24 | - | All | 2014-06-19 | - | -
Planning
Hi-Fi Prototype | 3 | 2014-07-10 | 2014-07-12 | Shirley | 2014-07-10 | 2014-07-12 | 3
Reviews
Sequence Diagram | 2 | 2014-07-08 | 2014-07-09 | Surya | 2014-07-08 | 2014-07-09 | 2 | 1
Wiki | 3 | 2014-07-14 | 2014-07-16 | Shirley | 2014-07-14 | 2014-07-16 | 3 | 1
Schedule | 2 | 2014-07-08 | 2014-07-09 | Jia Ying | 2014-07-08 | 2014-07-09 | 2 | 1
Design
Customized Table View (Job Seeker Search) | 5 | 2014-07-08 | 2014-07-12 | Jessica | 2014-07-08 | 2014-07-12 | 5 | 1 | Change of design
Register (Job Profile) | 3 | 2014-07-10 | 2014-07-12 | Surya | 2014-07-10 | 2014-07-12 | 3 | 1
View Personal Profile | 2 | 2014-07-08 | 2014-07-10 | Shirley | 2014-07-08 | 2014-07-10 | 3 | 1.5
Edit Personal Profile (By Job Seeker) | 2 | 2014-07-11 | 2014-07-12 | Shirley | 2014-07-11 | 2014-07-12 | 2 | 1
Search Job Seeker | 3 | 2014-07-14 | 2014-07-16 | Surya, Jessica | 2014-07-14 | 2014-07-16 | 3 | 1
Integration, Testing | 3 | 2014-07-17 | 2014-07-19 | All | 2014-07-17 | 2014-07-19 | 3 | 1
Debugging | 3 | 2014-07-21 | 2014-07-23 | All | 2014-07-21 | 2014-07-24 | 4 | 1.3333
Buffer | 2 | 2014-07-24 | 2014-07-25 | - | 2014-07-25 | 2014-07-25 | 1 | 0.5
Iteration 3 | 16 | 2014-07-26 | 2014-08-13 |  | 2014-07-26 | 2014-08-13 | 16
Meetings
Team Meeting 1 | - | 2014-07-29 | - | All | 2014-07-29 | - | - | -
Team Meeting 2 | - | 2014-08-04 | - | All | 2014-08-04 | - | - | -
Team Meeting 3 | - | 2014-08-12 | - | All | 2014-08-12 | - | - | -
Supervisor Meeting 1 | - | 2014-08-12 | - | All | 2014-08-12 | - | - | -
Reviews
Wiki | 3 | 2014-08-02 | 2014-08-05 | Shirley | 2014-07-31 | 2014-08-02 | 3 | 1
Schedule | 2 | 2014-07-26 | 2014-07-28 | Jia Ying | 2014-07-26 | 2014-07-28 | 2 | 1
Design
Add Jobs | 2 | 2014-07-26 | 2014-07-28 | Surya | 2014-07-26 | 2014-07-28 | 2 | 1 | Change of design
Edit Jobs | 2 | 2014-07-29 | 2014-07-30 | Shirley | 2014-07-29 | 2014-07-30 | 2 | 1
Delete Jobs | 2 | 2014-07-29 | 2014-07-30 | Surya | 2014-07-29 | 2014-07-30 | 2 | 1
Search Jobs | 4 | 2014-07-31 | 2014-08-04 | Surya, Jessica | 2014-07-31 | 2014-08-04 | 4 | 1
UI | 4 | 2014-07-26 | 2014-07-30 | Jessica, Jia Ying | 2014-07-26 | 2014-07-30 | 4 | 1
Add Admin | 2 | 2014-07-31 | 2014-08-01 | Shirley | 2014-07-31 | 2014-08-01 | 2 | 1
Integration, Testing | 3 | 2014-08-05 | 2014-08-07 | All | 2014-08-05 | 2014-08-07 | 3 | 1
Debugging | 3 | 2014-08-08 | 2014-08-11 | All | 2014-08-08 | 2014-08-13 | 5 | 1.6667
Buffer | 2 | 2014-08-12 | 2014-08-13 | - | - | - |  | 0
Preparation for Acceptance | 4 | 2014-08-13 | 2014-08-16 |  | 2014-08-13 |  |  | 0
18/8/2014: Milestone 2 - Project Acceptance
Iteration 4 | 14 | 2014-08-19 | 2014-09-02
Planning
Test Script | 3 | 2014-08-29 | 2014-09-01 | Jia Ying
Reviews
Acceptance Feedback | 2 | 2014-08-19 | 2014-08-20 | All
Schedule | 5 | 2014-08-21 | 2014-08-25 | Jia Ying
Wiki | 3 | 2014-08-27 | 2014-08-29 | Shirley
Deployment | 5 | 2014-08-21 | 2014-08-25 | Jessica, Surya
Design
Delete Admin (Master only) | 1 | 2014-08-22 | 2014-08-22 | Shirley
Delete Job Seeker (Admin only) | 1 | 2014-08-23 | 2014-08-23 | Shirley
Edit Admin Profile | 2 | 2014-08-24 | 2014-08-29 | Shirley
Add Client | 1 | 2014-08-21 | 2014-08-21 | Surya
Edit Client | 1 | 2014-08-22 | 2014-08-22 | Surya
Delete Client | 1 | 2014-08-23 | 2014-08-23 | Surya
Search Client | 3 | 2014-08-24 | 2014-08-26 | Surya
UI - Search Job Seeker | 2 | 2014-08-21 | 2014-08-22 | Jessica
UI - Search Jobs | 2 | 2014-08-23 | 2014-08-24 | Jessica
Integration, Testing | 3 | 2014-08-28 | 2014-08-30 | All
Debugging | 3 | 2014-08-31 | 2014-09-02 | All
Iteration 5 | 14 | 2014-09-03 | 2014-09-17
Planning
Job Match Algorithm | 3 | 2014-09-03 | 2014-09-05 | All
UAT Test Script | 4 | 2014-09-05 | 2014-09-08 | Jia Ying
Reviews
Schedule | 2 | 2014-09-03 | 2014-09-04 | Jia Ying
Wiki | 3 | 2014-09-09 | 2014-09-11 | Shirley
Design
Job Match | 4 | 2014-09-06 | 2014-09-09 | Surya
UI - Register Personal Details | 2 | 2014-09-06 | 2014-09-07 | Jessica
UI - Register Job Profile | 2 | 2014-09-08 | 2014-09-09 | Jessica
UI - Toolbar | 2 | 2014-09-10 | 2014-09-11 | Jessica
Email Notification | 2 | 2014-09-10 | 2014-09-11 | Shirley
Web Notification | 2 | 2014-09-10 | 2014-09-11 | Surya
Import CSV | 1 | 2014-09-11 | 2014-09-11 | Surya
Upload CV | 3 | 2014-09-06 | 2014-09-08 | Shirley
Integration, Testing | 3 | 2014-09-12 | 2014-09-14 | All
Debugging | 3 | 2014-09-15 | 2014-09-17 | All
Iteration 6 | 14 | 2014-09-18 | 2014-10-02
Reviews
Schedule | 2 | 2014-09-18 | 2014-09-19 | Jia Ying
UAT Test Script | 4 | 2014-09-20 | 2014-09-23 | Jia Ying
Wiki | 3 | 2014-09-30 | 2014-10-02 | Shirley
Design
Apply Job (Jobseeker/Admin) | 3 | 2014-09-18 | 2014-09-22 | Surya
View Job Application History (Jobseeker) | 2 | 2014-09-23 | 2014-09-24 | Shirley
UI - Search Client | 2 | 2014-09-18 | 2014-09-19 | Jessica
UI - Web Notification | 3 | 2014-09-20 | 2014-09-22 | Jessica
25/9/2014: Milestone 3 - UAT
Post-UAT Reviews | 5 | 41898 | 41914 | All
Result Analysis | 3 | 2014-09-26 | 2014-09-28 | Shirley, Jia Ying
Improvements based on reviews (TBA) | 3 | 2014-09-26 | 2014-09-28 | Jessica, Surya
Integration, Testing | 2 | 2014-09-29 | 2014-09-30 | All
Debugging | 2 | 2014-10-01 | 2014-10-02 | All
Iteration 7 | 14 | 2014-10-03 | 2014-10-17
Reviews
Schedule | 2 | 2014-10-05 | 2014-10-06 | Jia Ying
Mid Terms Slides | 2 | 2014-10-03 | 2014-10-04 | Jia Ying
Wiki | 2 | 2014-10-03 | 2014-10-04 | Shirley
8/10/2014: Milestone 4 - Mid Terms
Post-Mid Terms Reviews | 5 | 41898 | 41914 | All
Schedule | 3 | 2014-10-09 | 2014-10-11 | Jia Ying
Wiki | 3 | 2014-10-15 | 2014-10-17 | Shirley
Design
View Job Applications (ranked by match) | 2 | 2014-10-03 | 2014-10-04 | Jessica, Shirley
View Archived Job Postings | 3 | 2014-10-03 | 2014-10-05 | Surya
UI - Apply Jobs | 2 | 2014-10-05 | 2014-10-06 | Jessica
Export CSV | 2 | 2014-10-06 | 2014-10-07 | Surya
View Job Seekers - Sorted | 3 | 2014-10-09 | 2014-10-11 | Surya
UI - View Archived Job Postings | 2 | 2014-10-09 | 2014-10-10 | Jessica
Integration, Testing | 3 | 2014-10-12 | 2014-10-14 | All
Debugging | 3 | 2014-10-15 | 2014-10-17 | All