## Bug Log
BUG Log
Sprint | Session | Bug Count |  |  | Total Bug Score | Module | Bug Description | Date | Found By | How is the bug found? | Follow up Action | Has the bug being fixed? | Score
|  | Low Impact | High Impact | Critical Impact | [8 empty] | Low Impact | High Impact | Critical Impact
2 | Session 1 |  |  |  | 0 | Job Management | - | 2018-09-21 | - | - | - | - | 1 | 5 | 10
| Session 2 |  |  |  | 0 | Job Management | - | 2018-09-26 | - | - | - | -
3 | Session 1 |  |  |  | 0 | Job Management | - | 2018-10-06 | - | - | - | -
| Session 2 |  |  |  | 0 | Job Management | - | 2018-10-12 | - | - | - | -
4 | Session 1 | 1 |  |  | 11 | Job Management | Barges have no supplier in database | 2018-10-24 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Management | Unable to pass certain information to GeneralInfomationFormUpload Servlet | 2018-10-24 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Management | Encounter nullpointerexception in updating job information | 2018-10-24 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
5 | Session 1 |  | 1 |  | 10 | Job Management | Tank reports have no grades attache to them, despite them being dependent on it | 2018-10-29 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Management | Unable to pass certain information to TankReportFormUploadServlet from report-surveyor-bunker-condition.html | 2018-10-29 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
| Session 2 | 1 |  |  | 17 | Job Management | Information is not in order in RetrieveTankReportServlet's JSON Object | 2018-11-06 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  |  | 1 |  | Job Management | Updating of information is not possible for report-surveyor-bunker-condition.html | 2018-11-06 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Job Management | Status report input for uploading tank information is flipped. | 2018-11-06 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  | 1 |  |  | Job Management | Unable to pass certain information to TankReportFormUploadServlet from report-surveyor-barge | 2018-11-06 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
| Session 3 |  |  | 1 | 20 | Job Management | report-surveyor-sampling.html and the measurement pages are not able to retrieve null information | 2018-11-08 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  |  | 1 |  | Job Management | Measurement pages are not able to send empty information | 2018-11-08 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
7 | Session 1 |  | 1 |  | 5 | Job Management | Unable to pass in information from report-surveyor-statement.html to servlet | 2018-12-13 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
| Session 2 |  | 1 |  | 5 | Job Management | MassFlowMeterBunkerTankerMeasurementReport page is not able to send empty information | 2018-12-18 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
8 | Session 1 |  |  | 1 | 20 | Job Management | All pages are not able to send empty information | 2019-01-04 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  |  | 1 |  | Job Management | All pages are not able to receive empty information | 2019-01-04 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
9 | Session 1 | 1 |  |  | 26 | Profile Management | No whitespace allowed for fields | 2019-01-09 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  | 1 |  |  | Profile Management | No data is retrieved if user leaves a field blank when updating profile | 2019-01-09 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  |  | 1 |  | Profile Management | Program crashed when user did not upload any signature | 2019-01-09 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  |  | 1 |  | Profile Management | Program crashed when user did not upload any stamp | 2019-01-09 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
| Session 2 |  | 1 |  | 6 | Job Management | Date validation not in palce for StatementOfFactsDAO | 2019-01-11 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Information is not in order in RetrieveMassFlowMeterServletJSON Object | 2019-01-11 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
| Session 3 |  | 1 |  | 5 | Job Management | Timelog revamp was unable to pull information | 2019-01-19 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
10 | Session 1 |  |  | 1 | 10 | Job Management | DAO are not returning null for numerical values | 2019-01-23 | Ozzy | Internal Testing | Stop current development and resolve the bug immediately | ✓
| Session 2 |  | 1 |  | 14 | Job Management | TImelog, Seals Checklist Page cannot toggle between different grades. | 2019-01-26 | Yi Fang | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Job Management | NULL fields appeared as undefined | 2019-01-26 | Yi Fang | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  | 1 |  |  | User Management | Password is not encrypted in the database. | 2019-01-26 | Yi Fang | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | User Management, Job Management | Validation pattern does not satisfy requirement. | 2019-01-26 | Yi Fang | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Job Management | Sampling Report UI Issues | 2019-01-26 | Yi Fang | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Job Management | Timelog date and time formatting and fails to auto populate. | 2019-01-26 | Yi Fang | Internal Testing | Stop current development and resolve the bug immediately | ✓
| Session 3 |  | 1 |  | 5 | Job Management | Float values not giving accurate calculation | 2019-01-28 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
| Session 4 |  | 1 |  | 5 | Job Management | RetrieveNonCargoInspectionDeclarationServlet.java not able to insert data when empty | 2019-02-01 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
11 | Session 1 |  | 1 |  | 17 | Profile Management | Non-Admin Users currently are allowed to change their User Role (To lock it) | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | User Role should be drop down list instead of text entry | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | First Name, Last Name & Country currently allow numbers and special characters as input | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | Company currently allows special characters as input | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | Contact Number currently allows alphabets and special characters as input | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | e-Signature and e-Stamp currently allows any file type to be uploaded | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | Surveyor Licence field is currently shown for all User Roles (Super Admin, Admin, Surveyor, Client) in Profile-Edit.html & Admin-Profile-Edit.html Pages | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  | 1 |  |  | Whole Application | Users can currently access URLs directly without logging in | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | User Management tab is not shown for Super Admin and Admin on index.html page when logged in. | 2019-02-07 | Eng Teck | Internal Testing | Stop current development and resolve the bug immediately | ✓
| Session 2 |  | 1 |  | 5 | Job Management | report-surveyor-vessel-measurement-report.html.java not able displaying information correctly | 2019-02-10 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
| Session 3 |  | 1 |  | 11 | Profile Management | Password and Check Password inputs can be different and page will still load. Password is updated only based on value in Password input field | 2019-02-12 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  |  | 1 |  |  | Profile Management | Users can upload non-image type files in the signature and stamp field | 2019-02-12 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
|  | 1 |  |  |  | Profile Management | Users can enter more than 8 digits for contact number | 2019-02-12 | Aloysius | Internal Testing | Stop current development and resolve the bug immediately | ✓
| Session 4 | 1 |  |  | 2 | Job Management | report-surveyor-vessel-measurement-report.html.java and report-surveyor-barge-measurement-report.html.java do not have a default option for dropdown list | 2019-02-14 | Yi Fang | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | report-surveyor-vessel-measurement-report.html.java not able displaying information correctly | 2019-02-14 | Ozzy | Internal Testing | Use planned debugging time in this iteration to fix bugs | ✓
| Session 5 |  |  |  | 0 | Job Management | - | 2019-02-17 | - | - | - | -
12 | Session 1 | 1 |  |  | 2 | Job Management | Statement of fact, no validation to all fields | 2019-02-19 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | General Info, Mandatory field bug. location, date, vessel fields | 2019-02-19 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
| Session 2 | 1 |  |  | 11 | Job Management | Sampling report has 4 rows of fields when there is only 3 grades. | 2019-02-27 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Time value did not update as per desired in Timelog. | 2019-02-27 | Ozzy | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Unable to pass update Vessel Measurement with data in the after receipt section. Empty fields with and without empty tank name does not update into database. Remarks field does not update into database. Draft measurement fields does not update into database. | 2019-02-27 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Trim is not calculated and displayed in field in Vessel Measurement. | 2019-02-27 | Yi Fang | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Unable to update tank name in bunker condition. | 2019-02-27 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Invalid validation pattern for Flow Meter Make / Model, Transmitter Model and Nominated Tanks | 2019-02-27 | Yi Fang | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Management | Unable to upload pictures into database for existing job | 2019-02-27 | Eng Teck | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
13 | Session 1 | 1 |  |  | 8 | Notification | Unable to send email notification when creating job | 2019-03-09 | Aloysious | User Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Security Aspect | Unable to use HTTPS connection | 2019-03-09 | Aloysious | User Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Barge form pages have the wrong calculations | 2019-03-09 | Ozzy | User Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Measurement form pages cannot calculate metric tons total from seperate table | 2019-03-09 | Ozzy | User Testing | Used planned debugging time in this iteration to fix bugs | ✓
| Session 2 |  | 1 |  | 5 | Job Management | Not able to retrieve the information consistenly for barge and vessel measurement pages | 2019-03-12 | Samantha | User Testing | Used planned debugging time in this iteration to fix bugs | ✓
| Session 3 |  |  |  | 0 | Job Management, Notification, Offline Sync | - | 2019-03-24 | - | - | - | -
14 | Session 1 | 1 |  |  | 4 | Job Management | New jobs can be submitted when using past dates. These new jobs created cannot be edited as a result | 2019-03-28 | Rainean (UT Tester) | UT4 | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | "Upload all Vessel Pictures" button looks like it's disabled as it's greyed out | 2019-03-28 | Yan Kai (UT Tester) | UT4 | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | "Next" button on General Info page does not goes to next page when clicked | 2019-03-28 | Patrick (UT Tester) | UT4 | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | User Management | User's Telegram handle only allows numeric characters, instead of alpha-numeric characters | 2019-03-28 | Eng Teck | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
| Session 2 | 1 |  |  | 8 | Job Management | Final report is not linked properly. | 2019-04-01 | Aloysius | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Offline Sync Cache Code for Feedback Form fail to work | 2019-04-01 | Samantha | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Management | Surveyor can see all jobs and reports. Access control is not implemented to jobs and reports. | 2019-04-01 | Yi Fang | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Management | Quantity received volume in Barge and Vessel Measurement Page calculation error | 2019-04-01 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
| Session 3 | 1 |  |  | 6 | Job Management | Bunker Condition Calculation is incomplete as ajax is not working | 2019-04-05 | Samantha | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Management | Generate PDF API method is deprecated. | 2019-04-05 | Ozzy | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
15 | Session 1 | 1 |  |  | 13 | Job Management | Bunker Condition dynamic calculations are not working | 2019-04-08 | Samantha | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Notification Module | Telegram Notification for job completion is not triggered. | 2019-04-08 | Yi Fang | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Module | Report generated shows login interface. | 2019-04-08 | Aloysius | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  |  | 1 |  |  | Job Module | Signature detail are not entering into DB | 2019-04-08 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
|  | 1 |  |  |  | Job Module | Offline retrieval for signature and stamps | 2019-04-08 | Anthony | Internal Testing | Used planned debugging time in this iteration to fix bugs | ✓
| Session 2 |  |  |  | 0 | Job Management, Notification, Offline Sync | - | 2019-04-10 | - | - | - | -