## Review
Date | Abdul Haqqim | Ahmad Saifullah | Deborah Sim | Jack New | Sebastian Choo | Vera Low | Filled in at 9pm daily
2018-03-12 | 1. Enabling multiple booking for WordPress 2. Need to make it go live on the website 3. Test the booking plugin | 1. Rectified booking timings issue 2. None 3. Authentication for before they can access the game server | 1. Storyline for 1 min pitch completed, Updating scrum methodology for wiki 2. None 3. Update prototypes for wiki as well as prepare for poster submission | 1. UI for game room has been partially completed. 2. Unable to edit the beanner to look exactly like the banner in wordpress 3. Complete UI design and move on to bot broker/https | 1. Test cases for regression testing 2. Unable to fully cover all corner cases 3. Improving Game & Promo video | 1. sending error msg from pi to server 2. Unable to use java client to receive had to switch to JavaScriptclient wanted to change broker to hive but pi was unable to receive message using hive as a broker 3. Add the other exceptions to throw error back and make server https | "Example: 1. Progress for task on hand 2. Issues/Challenges Faced 3. Plans for the coming days"
2018-03-13 | 1. Upgrade booking plugin to enable email notification 2. NIL 3. Help Deborah on FYP video | 1. Purchased full version of Weeba plugin 2. None 3. Authentication for before they can access the game server | 1. Prepare for 1 min pitch video during meeting, Updated wiki with meeting minutes 2. Planning collaterals for going live 3. Update prototypes for game server | 1. Integration of UI and code editor ajax and error message 2. None 3. None | 1. Test cases for regression testing 2. Unable to fully cover all corner cases 3. Improving Game & Promo video | 1. Add other error msg and https 2. 3. Add error message and https
2018-03-14 | 1. Upgrade booking plugin to enable email notification 2. NIL 3. Help Deborah on FYP Finals Presentation Slides | 1. Ironing out booking process 2. None 3. Authentication for before they can access the game server | 1. Updated prototypes, Created slides for final presentation 2. None 3. Poster anc go live collaterals + slides | 1. Did 1m pitch video and recording of screens 2. None 3. Tips for Game room | 1. Test cases for regression testing 2. Unable to fully cover all corner cases 3. Improving Game & Promo video | 1. Add other error msg and https 2. 3. Add error message and https
2018-03-15 | 1. Test booking plugin 2. NIL 3. Help Deborah on FYP Finals Presentation Slides | 1. Ironing out booking process 2. None 3. Authentication for before they can access the game server | 1. Update wiki 2. None 3. Prep poster submission documents | 1. Tips for game room UI 2. Understanding ajax funtionality and how to use it for tips in game room 3. Understanding point 2 and complete tips functionality | 1. Test cases for regression testing 2. Unable to fully cover all corner cases 3. Improving Game & Promo video | 1. Add other error msg and https 2. 3. Add error message and https
2018-03-16 | 1. Test booking plugin 2. NIL 3. Help Deborah on FYP Finals Presentation Slides | 1. Ironing out booking process 2. None 3. Authentication for before they can access the game server | 1. Poster submission documents 2. None 3. Finals Presentation documents | 1. Learnt about using ajax 2. Unable to apply ajax for tips functionality 3. Further research to complete tips functionality | 1. Promo video for FYP 2. None 3. Rebuilding of Game logistics | 1. Add other error msg and https 2. Unable to receive velidation message for SSL request 3. Add error message and https
2018-03-17 | 1. Test booking plugin 2. Some bugs faced 3. Help Deborah on FYP Finals Presentation Slides | 1. Ironing out booking process 2. None 3. Authentication for before they can access the game server | 1. Poster submission documents 2. None 3. Finals Presentation documents | 1. Added tips functionality to game room 2. No actual tips for the game room yet 3. Adding in tips as well as making page more interactive | 1. Promo video for FYP 2. None 3. Rebuilding of Game logistics | 1. Add other error msg and https 2. Unable to receive velidation message for SSL request 3. Add error message and https
2018-03-18 | 1. FYP Finals Presentation Slides 2. None 3. Update & Check actions on Trello | 1. Ironing out booking process 2. None 3. Authentication for before they can access the game server | 1. Poster submission documents and video 2. None 3. Finals Presentation documents | 1. Added tips into the learning module 2. None 3. Testing for bugs in tips functionality | 1. Promo video for FYP 2. None 3. Rebuilding of Game logistics | 1. enable site to have https 2. Still unable to receive validation email for SSL cert 3. enable site to have Https and set password for mqtt
2018-03-19 | 1. FYP Finals Presentation Slides 2. None 3. None | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Regression testing for game room 2. None 3. Improvement for game room | 1. Rebuilding of Game logistics, test cases for regression testing 2. None 3. UAT4 preparation | 1. set up own broker 2. unable to self sign cert for broker 3. set up broker
2018-03-20 | 1. FYP Finals Presentation Slides 2. None 3. None | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Included more specific visuals, E.G. colors appearing on buttons when clicked to show that users have successfully selected the option 2. None 3. Work on light sensor measuring the end of the maze | 1. Rebuilding of Game logistics, test cases for regression testing 2. None 3. UAT4 preparation | 1. set up own broker 2. unable to self sign cert for broker 3. set up broker
2018-03-21 | 1. FYP Finals Presentation Slides 2. None 3. Update & Check actions on Trello | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Started studying on sensors on GoPiGo 2. None 3. Continue research or start on coding for sensor on GoPiGo | 1. Rebuilding of Game logistics, test cases for regression testing 2. None 3. UAT4 preparation | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password
2018-03-22 | 1. FYP Finals Presentation Slides 2. None 3. None | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Started studying on sensors on GoPiGo 2. None 3. Continue research or start on coding for sensor on GoPiGo | 1. UAT4 Preparation 2. None 3. Test Cases for regression testing | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password
2018-03-23 | 1. FYP Finals Presentation Slides 2. None 3. None | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Attempt to receive light sensor reading from GoPiGo onto game room page 2. Unable to set up connection 3. Will attempt to solve the connection issue in the following days | 1. UAT4 Preparation 2. None 3. Test Cases for regression testing | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password
2018-03-24 | 1. FYP Finals Presentation Slides 2. None 3. Update & Check actions on Trello | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Attempt to receive light sensor reading from GoPiGo onto game room page 2. Unable to set up connection 3. Will attempt to solve the connection issue in the following days | 1. UAT4 Preparation 2. None 3. Test Cases for regression testing | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password
2018-03-25 | 1. FYP Finals Presentation Slides 2. None 3. None | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Unable to complete function from previous 2 days and back to more research on how to receive light sensor values from GoPiGo and sending it to web page 2. None 3. Either more research or attempt to complete the functionality | 1. UAT4 Preparation 2. None 3. Test Cases for regression testing | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password and to set password for the python code in the raspberry pi
2018-03-26 | 1. FYP Finals Presentation Slides 2. None 3. None | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. User Testing Progress Report 2. None 3. Go Live Preparation | 1. UT, Testing for game room 2. None 3. Review UT feedback and carry out changes | 1. UAT4 2. None 3. Test Cases for regression testing | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password and to set password for the python code in the raspberry pi
2018-03-27 | 1. FYP Finals Presentation Slides 2. None 3. Update & Check actions on Trello | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. User Testing Feedback collation 2. None 3. Go Live Preparation (booking room to host robot) | 1. Made changes to tips section from UT comments 2. None 3. Either more research or attempt to complete light sensor functionality | 1. UAT4 Feedback collation 2. None 3. Test Cases for regression testing | 1. Configure javascript client and java client to set password 2. Unable to set password for javascript client 3. Configure javascript client and java client to set password and to set password for the python code in the raspberry pi
2018-03-28 | 1. Python Tutorial Video 2. NIL 3. FYP Finals Presentation Slides | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Made changes to tips section from UT comments 2. None 3. Either more research or attempt to complete light sensor functionality | 1. UAT4 Feedback collation 2. None 3. Test Cases for regression testing | 1. Configure websocket handshake 2. Unable to set cert path in javascript client 3. configure javascript client websocket handshake
2018-03-29 | 1. FYP Finals Presentation Slides 2. NIL 3. FYP Finals Presentation Rehearsal | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | 1. Made changes to tips section from UT comments 2. None 3. Either more research or attempt to complete light sensor functionality | 1. Test cases for regression testing 2. None 3. None | 1. Configure websocket handshake 2. Unable to set cert path in javascript client 3. configure javascript client websocket handshake
2018-03-30 | PH | PH | PH | PH | PH | PH
2018-03-31 | 1. FYP Finals Presentation Slides 2. NIL 3. FYP Finals Presentation Rehearsal | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update wiki 2. None 3. Prepare finals wiki documentation | "1. Stopped coding tasks and begin preparing for handing over 2. None 3. Preparation of user documents & meeting with sponsor" | 1. Test cases for regression testing 2. None 3. None | 1. Configure websocket handshake 2. Unable to set cert path in javascript client 3. configure javascript client websocket handshake
2018-04-01 | PH | PH | PH | PH | PH | PH
2018-04-02 | 1. Roster for Go Live 2. NIL 3. FYP Finals Presentation Slides | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Go Live Roster 2. None 3. Update wiki | 1. User Documents 2. NIL 3. Roster for Go Live | 1. Test cases for regression testing 2. None 3. FYP Finals Preparation | 1. Configure websocket handshake and also spectate going live of robostudio site 2. Unable to set cert path in javascript client 3. configure javascript client websocket handshake
2018-04-03 | 1. Roster for Go Live 2. NIL 3. FYP Finals Presentation Slides | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Go Live Roster 2. None 3. Update wiki | 1. Preparation of user accounts for handover as well as user documentations 2. Request for sponsor to create Paypal and AWS account 3. User documents | 1. Test cases for regression testing 2. None 3. FYP Finals Preparation | 1. Configure websocket handshake 2. Unable to set cert path in javascript client 3. configure javascript client websocket handshake
2018-04-04 | 1. FYP Finals Presentation Slides 2. NIL 3. Roster for Go Live | 1. Authentication for before they can access the game server 2. None 3. Domain names | 1. Update documentation 2. None 3. Update wiki | 1. User Documents 2. NIL 3. Roster for Go Live | 1. Test cases for regression testing 2. None 3. FYP Finals Preparation | 1. Configure websocket handshake and also spectate going live of robostudio site 2. Unable to set cert path in javascript client 3. configure javascript client websocket handshake